## Grant Pipeline
Waypoint — Grant & Non-Dilutive Funding Pipeline
Verified September 7, 2026. Tier 1 = for-profit eligible and actionable · Tier 2 = blocked behind 501(c)(3) · Tier 3/4 = small grants and in-kind credits · X = ruled out (corrections to the Aug 2026 plan of record)
CRITICAL PATH: every federal row requires a legal entity + EIN, then a 4-6+ week registration chain (SAM.gov -> eRA Commons -> SBA Registry -> Grants.gov). Entity must exist by ~Oct 15, 2026 to make the Jan 5, 2027 NIH deadline.
Tier | Program | Funder | Type | Amount | Next Deadline | Eligibility — can Waypoint apply? | Fit for Waypoint | Next Action | Owner | Status | Source
1 | NIH Parent SBIR (PA-27-100) | NIH / CDC / FDA (NICHD, NIMH) | Grant (non-dilutive) | Per-award caps reach $3M (Phase II); Phase I is the entry point | Jan 5, 2027 (Sep 5/8 2026 passed) | YES — for-profit US small business, >50% US-individual owned, <=500 employees. LLC is an acceptable legal form. SBIR PI must be >50% employed by the company. | Strong. E8 outcomes engine is already scoped as the grant/STTR aim. Fundable question: does AI-guided navigation close the service-access gap for Spanish-speaking families? | Entity + EIN by ~Oct 15 2026; then SAM.gov. Decide SBIR vs STTR by Nov 15. | Owner | Not started | https://seed.nih.gov/small-business-funding/find-funding/sbir-sttr-funding-opportunities
1 | NIH Parent STTR (PA-27-102) | NIH / CDC / FDA | Grant (non-dilutive) | Same caps as SBIR | Jan 5, 2027 | YES — same small-business test, PLUS a research-institution partner: >=30% work at the institution, >=40% at the company. PI may sit at the university (>=10% effort). | Strong IF a UC/CSU partner is real. The partner also answers the credibility problem a solo-founder application has. | Identify a UC/CSU disability-studies or health-services partner before Nov 15, 2026. Do not manufacture a partnership to fit the mechanism. | Owner | Not started | https://seed.nih.gov/small-business-funding/find-funding/sbir-sttr-funding-opportunities
1 | NIDILRR / ACL SBIR (93.433) | Administration for Community Living | Grant (non-dilutive) | Phase I; recent round funded 10 grants | Watch grants.gov for FY27 NOFO | YES — for-profit small business. | STRONGEST mission match in this document. Every funded project must address the needs of people with disabilities and promote health/function, community living, or employment. Small program = winnable. | Set grants.gov saved-search alerts for 'NIDILRR' and '93.433'. No fixed omnibus calendar — must be watched. | Owner | Not started | https://acl.gov/news-and-events/announcements/new-funding-opportunity-small-business-innovation-research-program-2
1 | ED / IES SBIR | US Dept of Education, Institute of Education Sciences | Grant (non-dilutive) | FY26 Phase IA: $250,000 / 9 months. Phase II: $1,000,000 / 2 years | FY27 solicitation expected spring 2027 (FY26 closed Jun 29, 2026) | YES — for-profit small business. | Strong, and aims at the OTHER market: ~850-884k CA students with IEPs vs ~7,459 SDP enrollees. IES explicitly funds special-education technology. | Watch ies.ed.gov for the FY27 solicitation. Phase IA is the entry point. | Owner | Not started | https://ies.ed.gov/funding/research/programs/small-business-innovation-research-sbir/solicitation-information
1 | DDS Service Access & Equity (SAE) | CA Dept of Developmental Services | Grant (non-dilutive) | $11M/year across many awards; >=$200k awards may require a fiscal/management agent | FY2027-29 cycle expected ~fall 2027 (FY2025-27 closed Nov 17, 2025) | YES — a CBO is defined as 'a public or private nonprofit, OR PRIVATE FOR-PROFIT organization'. A qualifying EIN is required. | BEST FIT IN THIS DOCUMENT. DDS is under public pressure (Public Counsel 2022/2025) over the Latino-White POS spending gap. Waypoint's Spanish-first work is exactly what this program buys. | Email SAEgrantprogram@dds.ca.gov now to confirm the cycle and join the notification list. Bundle with the DDS Question-Zero letter. | Owner | Not started | https://www.dds.ca.gov/rc/disparities/disparity-funds-program/
1 | CHCF Innovation Fund | California Health Care Foundation | Investment + grant (PARTLY DILUTIVE) | Up to $3M combined investment + grant per partner company | Rolling — unsolicited LOIs accepted | YES — early- through growth-stage for-profit companies. Does NOT fund life sciences or medical devices. | Strong + strategic. Targets access for low-income Californians in the Medi-Cal ecosystem — the credible door into the CalAIM channel the roadmap defers to Phase 4. Network may be worth more than the capital. | Draft an unsolicited LOI. Only Tier-1 source with no deadline to wait for. | Owner | Not started | https://www.chcf.org/network/chcf-innovation-fund/
2 | Lucile Packard Foundation — CYSHCN | Lucile Packard Foundation for Children's Health | Grant | Varies by cohort | Check lpfch.org | NO as a for-profit — foundation grantmaking, nonprofit-oriented. | Mission-perfect: systems and policy change for children with special health care needs; requires meaningful family engagement AND compensating families for their time. | Park until/unless a 501(c)(3) affiliate exists. FY28 decision. | — | Blocked | https://lpfch.org/program-for-children-and-youth-with-special-health-care-needs/grants/
2 | SCDD Program Development Grants | CA State Council on Developmental Disabilities | Grant | Recent cycle: $300,000 across topic areas | Issued annually; none open as of Sep 2026 | PARTIAL — CA-based agencies/organizations serving people with I/DD. Requires 10% match (poverty areas) or 25% match (non-poverty). | Good mission fit, but the match requirement is real cash exposure for a pre-revenue company. | Monitor scdd.ca.gov/grantinformation. Revisit once there is cash for the match. | — | Monitor | https://scdd.ca.gov/grantinformation/
2 | WITH Foundation | WITH Foundation | Grant | $150,000 - $250,000 | Cycle opens Jul 1, 2026 | NO — 501(c)(3) nonprofits only. | POOR FIT — also scoped to ADULTS with I/DD, not children. Named in the Aug 2026 plan in error. | Remove from the plan of record unless both a nonprofit arm and an adult-transition line exist. | — | Ruled out | https://withfoundation.org/
2 | Blue Shield of CA Foundation | Blue Shield of California Foundation | Grant | Varies | See funding opportunities page | NO — nonprofit / tax-exempt organizations only. | Health equity in California — good thematic fit, structurally ineligible. | Park until/unless a 501(c)(3) affiliate exists. | — | Blocked | https://blueshieldcafoundation.org/grants/funding-opportunities
3 | Hello Alice grant marketplace | Hello Alice + corporate partners | Grant (non-dilutive) | Varies by partner; $57M+ distributed to date | Rolling | YES — open to LLCs and small businesses, no 501(c)(3) required. | Low value, low effort. Background noise, not a plan. | Create an account and set alerts once the entity exists. | Owner | Not started | https://www.helloalice.com/small-business-grants-and-funding
3 | Amber Grant | WomensNet | Grant (non-dilutive) | 3 x $10,000 monthly | Last day of each month, 11:59pm ET | CONDITIONAL — requires a woman aged 18+ owning >=50% of the business. | Only applicable if the cap table meets the ownership test. Do not plan on it otherwise. | OWNER TO CONFIRM: does the cap table satisfy >=50% woman ownership? Yes/no removes this row. | Owner | Needs answer | https://ambergrantsforwomen.com/
4 | Anthropic — Claude for Startups | Anthropic | In-kind credits | ~$25k reported | Rolling | YES — public application, no VC backing required. | Directly offsets the free-tier AI inference cost the roadmap flags as unfunded. Fastest payback in this document. | Apply the week the entity + EIN exist. | Owner | Not started | https://fin.ai/learn/ai-credits-for-startups
4 | AWS Activate | Amazon Web Services | In-kind credits | ~$1,000 self-serve (up to $5,000 select); up to ~$300k GenAI track w/ VC or accelerator | Rolling | YES — self-serve tier needs no VC. | Offsets infrastructure cost. Take the self-serve tier now; larger tiers need VC/accelerator. | Apply the week the entity + EIN exist. | Owner | Not started | https://radgrants.com/cloud-credits
4 | Microsoft for Startups Founders Hub | Microsoft | In-kind credits | ~$1,000 Azure instant; ~$25k baseline; up to ~$150k | Rolling | YES — self-serve tier needs no VC. | Same as above. Low effort. | Apply the week the entity + EIN exist. | Owner | Not started | https://radgrants.com/cloud-credits
4 | Google Cloud for Startups | Google | In-kind credits | ~$200k standard / up to ~$350k AI-first track | Rolling | PARTIAL — largest tiers typically require VC backing or a recognized accelerator. | Worth an application; expect the smaller tier without VC backing. | Apply after the self-serve tiers. | Owner | Not started | https://creditforstartups.com/resources/google-cloud-startup-credits
X | CalOSBA TAP / CIP | CA Office of the Small Business Advocate | NOT a small-business grant | n/a | n/a | NO — TAP funds designated technical-assistance centers (federal designation or 501(c)(3)/(c)(6)); CIP funds only SBDC Lead Centers. Both need 1:1 match. | CORRECTION to the Aug 2026 plan of record: CalOSBA is not a funding source for Waypoint. | Remove from the plan. Watch only for a California Dream Fund renewal. | — | Ruled out | https://www.grants.ca.gov/grants/technical-assistance-program-tap-2025-2026/
X | California Dream Fund | CalOSBA | Microgrant | Up to $10,000 | Original $35M round concluded April 2026 | WOULD BE YES if renewed — <=5 employees, <=$1M receipts, must complete training at an approved TA center. | Dormant. Framework remains as a model for future rounds. | Subscribe to the CalOSBA newsletter for a renewal announcement. | — | Dormant | https://calosba.ca.gov/funding-grants-incentives/california-dream-fund-program/
X | DDS Enhanced Community Integration | CA Dept of Developmental Services | Grant | $12.5M one-time (ARPA) | 2022-23 cycle closed | n/a — closed. | One-time American Rescue Plan Act money for social/recreation programs. Not recurring. | No action. Listed so it is not re-researched. | — | Closed | https://www.dds.ca.gov/initiatives/community-integration-social-rec-grants/
X | FedEx Small Business Grant | FedEx | Grant | n/a | n/a | n/a — retired after 2024. | Do not chase. | No action. | — | Ruled out | —
X | Comcast RISE | Comcast | Grant | n/a | n/a | n/a — no application site as of Aug 31, 2026. | Do not chase. | No action. | — | Ruled out | —

## Critical Path
Critical Path — working backward from the Jan 5, 2027 NIH deadline
Target date | Milestone | Depends on | Typical duration
Week of Sep 7, 2026 | Decide entity path (Path A benefit corp / Path B LLC) | Owner decision | —
Week of Sep 7, 2026 | Book CA business attorney + CPA consults | Path decision | —
Sep 2026 | Email SAEgrantprogram@dds.ca.gov re: next SAE cycle (bundle with DDS Question-Zero letter) | — | —
By ~Oct 15, 2026 | ENTITY FORMED + EIN ISSUED <- binding constraint | Attorney; name clearance | EIN same day
Oct 2026 | Apply for self-serve AI/cloud credits | EIN | Days
Oct 15 - Nov 5, 2026 | SAM.gov registration -> issues UEI (START FIRST) | EIN | 3 wks typical / 6+ worst case
Nov 2026 | eRA Commons (org, then PI account) | SAM.gov | 2+ weeks
Nov 2026 | SBA Company Registry -> SBC Control ID | SAM.gov | 1-2 business days
Nov 2026 | Grants.gov registration | SAM.gov | Days
By Nov 15, 2026 | DECIDE SBIR vs STTR (is a UC/CSU research partner real?) | Partner outreach | —
Oct - Dec 2026 | Draft specific aims, research plan, commercialization plan | — | 80-120 hours
Jan 5, 2027 | NIH SBIR/STTR SUBMISSION | All registrations complete | —
Apr 5, 2027 | Fallback NIH cycle if January slips | — | —
~Spring 2027 | ED/IES SBIR FY27 solicitation expected to open | — | —
~Fall 2027 | DDS SAE FY2027-29 cycle (CONFIRM with DDS) | EIN; relationship built in 2026 | —

## Open Questions
Open questions for the owner — each one changes the plan
# | Question | Why it matters | Answer
1 | Entity path: California Benefit Corporation (Path A, recommended) or California LLC + B Corp certification (Path B)? | Blocks the entire federal lane and the 099 vendorization packet. Nothing below can start until this is decided.
2 | Is there a UC or CSU research contact worth approaching before Nov 15, 2026? | Decides SBIR (no partner) vs STTR (partner required, >=30% of work at the institution). Also answers the credibility gap in a solo-founder application.
3 | Does the cap table satisfy >=50% ownership by a woman aged 18+? | Yes/no determines whether the Amber Grant ($10k monthly) is a real row or should be deleted.
4 | Nonprofit 501(c)(3) affiliate: park until FY28, or scope now? | Unlocks ALL of Tier 2 (Lucile Packard, WITH, Blue Shield CA Foundation). Cost: a second entity, its own board and filings, and arm's-length discipline between the two.
5 | Who writes the NIH application — founder, or a paid grant writer? | A first NIH SBIR is realistically 80-120 hours. This is a cash question, and it is why most solo-founder SBIR plans are never submitted.
6 | Which subfolder should these deliverables live in? | Currently in Operations/. Confirm or reassign before this becomes the reference copy.