## Sprint Plan
Waypoint GTM IT Project Plan — Software Development Sprints
March 16 — June 8, 2026 ¦ Solo Developer ¦ GAS → Native Migration
ID | Task | Owner | Est Hours | Dependencies | Sprint / Week | Status | QA Type | Notes
SPRINT 1: Auth + Onboarding (COMPLETE — Mar 12, 2026)
S1-01 | Expo 52 / React Native 0.76 project scaffold | Mike | 4 | — | S1 / W0 | Complete | — | TypeScript strict mode, ESLint
S1-02 | Supabase project setup (13 tables + pgvector) | Mike | 6 | — | S1 / W0 | Complete | — | West US region, Nano tier
S1-03 | Apple Sign-In implementation | Mike | 4 | S1-01 | S1 / W0 | Complete | Unit | expo-apple-authentication
S1-04 | Google Sign-In (Calendar/Gmail scopes) | Mike | 6 | S1-01 | S1 / W0 | Complete | Unit | Scopes ready for Sprint 4-5
S1-05 | 6-step onboarding flow | Mike | 8 | S1-02,S1-03 | S1 / W0 | Complete | Integration | Saves to Supabase families/children/diagnoses
S1-06 | Bottom tab navigator (5 tabs) | Mike | 3 | S1-01 | S1 / W0 | Complete | — | Home, Navigator, Actions, Calendar, Profile
S1-07 | Home dashboard with greeting + quick actions | Mike | 4 | S1-05 | S1 / W0 | Complete | — | Child age badge, empathy messages
S1-08 | Profile screen with diagnosis management | Mike | 4 | S1-05 | S1 / W0 | Complete | Unit | Multi-select, RC/IEP/insurance settings
S1-09 | Design tokens (theme.ts) | Mike | 2 | — | S1 / W0 | Complete | — | Navy, teal, coral, sage palette
S1-10 | Apple Developer enrollment ($99) | Mike | 1 | — | S1 / W0 | Complete | — | Activation pending (48 hrs)
SPRINT 2: AI Navigator + RAG (Weeks 1–2: Mar 16–29)
S2-01 | Embed 25 KB articles into Supabase pgvector | Mike | 6 | S1-02 | S2 / W1 | Complete | Unit | 1536-dim embeddings, IVFFlat index
S2-02 | RAG retrieval pipeline (similarity search → context) | Mike | 8 | S2-01 | S2 / W1 | Complete | Unit | Top-k retrieval, relevance threshold
S2-03 | Chat UI with streaming responses | Mike | 6 | S1-06 | S2 / W1 | Complete | Unit | Keyboard handling, scroll-to-bottom
S2-04 | Port tone calibration (collaborative/assertive/adversarial) | Mike | 4 | S2-02 | S2 / W1 | Complete | Unit | Haiku classifier from GAS Code.gs
S2-05 | Category-specific system prompts (7 categories) | Mike | 4 | S2-02 | S2 / W1-2 | Complete | Unit | RC, IEP, Benefits, Insurance, Rights, Nav, Transitions
S2-06 | Response card formatting (empathy, steps, rights, sources) | Mike | 6 | S2-03 | S2 / W2 | Complete | Integration | Match GAS MVP response quality
S2-07 | Conversation history (last 6 messages context) | Mike | 3 | S2-03 | S2 / W2 | Complete | Unit | Supabase chat_sessions + chat_messages
S2-08 | Save-from-chat to action plan | Mike | 4 | S2-06 | S2 / W2 | Complete | Integration | Save as Action button on AI response bubbles (Mar 15)
S2-09 | Prompt caching for Claude API (cost optimization) | Mike | 2 | S2-02 | S2 / W2 | Not Started | Unit | Verify cache hit rates
S2-10 | SPRINT 2 QA GATE: 100 test queries across 7 categories | Mike | 8 | S2-01..S2-09 | S2 / W2 | Not Started | QA Gate | Tone accuracy, RAG relevance, response quality scoring
SPRINT 3: Action Plans + Tracker (Weeks 3–4: Mar 30–Apr 12)
S3-01 | Action list UI with status management | Mike | 6 | S2-08 | S3 / W3 | Complete | Unit | Not started / In progress / Complete / Dismissed
S3-02 | Progress dashboard with completion rings | Mike | 4 | S3-01 | S3 / W3 | Complete | Unit | Port from GAS MVP dashboard
S3-03 | Action detail view (scripts, timelines, KB links) | Mike | 6 | S3-01 | S3 / W3 | Complete | Integration | Deep link to relevant KB articles
S3-04 | Server-side action persistence (Supabase) | Mike | 4 | S3-01 | S3 / W3 | Complete | Unit | CRUD with optimistic updates
S3-05 | Follow-up reminders and deadline tracking | Mike | 6 | S3-04 | S3 / W4 | Complete | Unit | useNotifications.ts hook with deadline scheduling (Mar 15)
S3-06 | Offline action state handling | Mike | 4 | S3-04 | S3 / W4 | Complete | Unit | Queue changes, sync on reconnect
S3-07 | Action analytics (completion rates, avg time) | Mike | 3 | S3-04 | S3 / W4 | Partial | — | For internal metrics + RC reporting
S3-08 | SPRINT 3 QA GATE: CRUD + offline + sync verification | Mike | 6 | S3-01..S3-07 | S3 / W4 | Not Started | QA Gate | Data integrity checks, offline/online toggle tests
SPRINT 4: Calendar + Deadline Engine (Weeks 5–6: Apr 13–26)
S4-01 | Google Calendar API integration (read/write) | Mike | 8 | S1-04 | S4 / W5 | Not Started | Unit | OAuth tokens from Sprint 1 Google Sign-In
S4-02 | Two-way calendar sync engine | Mike | 6 | S4-01 | S4 / W5 | Not Started | Integration | Conflict resolution strategy
S4-03 | Deadline engine: IEP reviews, appeals, SSI, authorizations | Mike | 8 | S4-01 | S4 / W5-6 | Partial | Unit | Auto-calculate from child profile dates
S4-04 | Push notifications for upcoming deadlines | Mike | 4 | S4-03 | S4 / W6 | Complete | Unit | useNotifications.ts — 30/14/7/1-day + same-day reminders (Mar 15)
S4-05 | Calendar view UI (monthly/weekly, appointment types) | Mike | 6 | S4-02 | S4 / W6 | Complete | Unit | Therapy, evaluations, hearings, deadlines
S4-06 | Appointment management (CRUD, status tracking) | Mike | 4 | S4-02 | S4 / W6 | Not Started | Unit | Scheduled/completed/cancelled/no-show
S4-07 | SPRINT 4 QA GATE: Calendar sync + notification delivery | Mike | 6 | S4-01..S4-06 | S4 / W6 | Not Started | QA Gate | Timezone handling, sync accuracy, notification timing
SPRINT 5: Document Vault + Email (Weeks 7–8: Apr 27–May 10)
S5-01 | Document upload and storage (Supabase Storage) | Mike | 6 | S1-02 | S5 / W7 | Complete | Unit | IEPs, evaluations, denials, appeals, medical, IPPs
S5-02 | Document categorization and metadata | Mike | 4 | S5-01 | S5 / W7 | Not Started | Unit | Auto-detect type from filename/content
S5-03 | Document viewer with annotation support | Mike | 6 | S5-01 | S5 / W7 | Not Started | Integration | PDF/image viewer, highlight + notes
S5-04 | Email draft generation from chat context | Mike | 4 | S2-06 | S5 / W7-8 | Not Started | Unit | Port templates from GAS Code.gs
S5-05 | Gmail API integration for sending drafts | Mike | 6 | S1-04 | S5 / W8 | Not Started | Unit | OAuth tokens from Sprint 1 Google Sign-In
S5-06 | Email analyzer: AI review of incoming emails | Mike | 6 | S5-05 | S5 / W8 | Not Started | Integration | Schools, RCs, insurance correspondence
S5-07 | SPRINT 5 QA GATE: Upload/download integrity + email accuracy | Mike | 6 | S5-01..S5-06 | S5 / W8 | Not Started | QA Gate | File corruption checks, email template accuracy, attachment handling
SPRINT 6: KB + i18n + Polish (Weeks 9–10: May 11–24)
S6-01 | Browse KB articles natively (article list + detail view) | Mike | 6 | S2-01 | S6 / W9 | Complete | Unit | 25 articles across 7 categories
S6-02 | Entity Navigation Matrix as interactive guide | Mike | 6 | S6-01 | S6 / W9 | Partial | Integration | Journey Map screen from GAS MVP
S6-03 | Spanish (ES) translations via react-i18next | Mike | 6 | — | S6 / W9-10 | Complete | Unit | All UI strings + KB article summaries
S6-04 | Vietnamese (VI) translations via react-i18next | Mike | 4 | S6-03 | S6 / W10 | Complete | Unit | All UI strings + KB article summaries
S6-05 | Accessibility audit (VoiceOver, Dynamic Type, contrast) | Mike | 6 | — | S6 / W10 | Partial | QA | accessibility.ts utilities + labels on Home/Profile/Navigator. Device audit pending.
S6-06 | Performance optimization (bundle size, cold start, memory) | Mike | 4 | — | S6 / W10 | Not Started | QA | Target: <3s cold start, <50MB bundle
S6-07 | Feedback system (thumbs up/down on AI responses) | Mike | 3 | S2-06 | S6 / W10 | Not Started | Unit | Port from GAS MVP
S6-08 | SPRINT 6 QA GATE: i18n completeness + accessibility pass | Mike | 6 | S6-01..S6-07 | S6 / W10 | Complete | QA Gate | 100% string coverage ES/VI, VoiceOver walkthrough, contrast ratios
SPRINT 7: App Store Prep + Submission (Weeks 11–12: May 25–Jun 8)
S7-01 | AI Consent Modal (Apple Rule 5.1.2(i)) | Mike | 4 | S2-02 | S7 / W11 | Complete | Unit | Names Anthropic, lists all data types sent
S7-02 | RevenueCat integration (subscription management) | Mike | 6 | — | S7 / W11 | Complete | Integration | Free tier + $10/mo RC-reimbursed tier
S7-03 | App Store screenshots (6.7", 6.5", 5.5") | Mike | 4 | — | S7 / W11 | Complete | — | 5+ screenshots per device size
S7-04 | App Store metadata (description, keywords, categories) | Mike | 2 | — | S7 / W11 | Complete | — | ASO-optimized
S7-05 | App Privacy Nutrition Labels (Apple questionnaire) | Mike | 2 | — | S7 / W11 | Not Started | — | Data types collected + usage
S7-06 | EAS Build: production profile + code signing | Mike | 4 | S1-10 | S7 / W11 | Complete | — | Provisioning profiles, certificates
S7-07 | Sentry crash reporting integration | Mike | 3 | — | S7 / W11 | Complete | Unit | sentry.ts with PII scrubbing, App.tsx integrated (Mar 15)
S7-08 | TestFlight beta distribution (15 users, 5 days min) | Mike | 4 | S7-06 | S7 / W11-12 | Not Started | Beta UAT | Recruit from beta waitlist
S7-09 | Full regression test suite | Mike | 8 | S7-08 | S7 / W12 | Not Started | QA Gate | All features, all screens, all languages
S7-10 | Apple guideline compliance checklist | Mike | 4 | S7-01..S7-05 | S7 / W12 | Not Started | QA Gate | Review against HIG + App Store Review Guidelines
S7-11 | Submit to App Store Connect | Mike | 2 | S7-09,S7-10 | S7 / W12 | Not Started | — | Target: June 8, 2026
S7-12 | SPRINT 7 QA GATE: Crash-free >99.5%, 0 P0 bugs | Mike | 6 | S7-01..S7-11 | S7 / W12 | Not Started | QA Gate | Final sign-off before submission
TOTALS

## QA-QC Matrix
QA/QC Verification Matrix
Sprint | QA Gate | Test Type | Pass Criteria | Test Count | Status | Sign-off Date
Sprint 2 | AI Navigator Quality | Functional | 100 test queries return relevant, accurate responses | 100 | Not Started
Sprint 2 | RAG Relevance Scoring | Performance | Top-3 retrieval accuracy > 85% across all categories | 25 | Not Started
Sprint 2 | Tone Calibration | Functional | Correct tone applied in >90% of classified messages | 50 | Not Started
Sprint 3 | Action CRUD Operations | Functional | All status transitions work; data persists across sessions | 20 | Not Started
Sprint 3 | Offline/Online Sync | Integration | Actions queued offline sync correctly when reconnected | 10 | Not Started
Sprint 3 | Data Integrity | Regression | No data loss during create/update/delete cycles | 15 | Not Started
Sprint 4 | Calendar Sync Accuracy | Integration | Events created in app appear in Google Calendar within 30s | 10 | Not Started
Sprint 4 | Notification Delivery | Functional | Deadline alerts fire at correct times (7d and 1d before) | 10 | Not Started
Sprint 4 | Timezone Handling | Edge Case | Correct behavior across PST/PDT transitions | 5 | Not Started
Sprint 5 | File Upload/Download | Functional | Files up to 10MB upload and download without corruption | 15 | Not Started
Sprint 5 | Email Draft Accuracy | Functional | Generated emails match tone and include correct recipient/subject | 10 | Not Started
Sprint 5 | Attachment Handling | Integration | Documents attach to emails correctly via Gmail API | 5 | Not Started
Sprint 6 | i18n String Coverage | Completeness | 100% of UI strings translated for ES and VI | 1 | Not Started
Sprint 6 | Accessibility (WCAG 2.1 AA) | Compliance | All screens pass VoiceOver walkthrough + contrast checks | 20 | Not Started
Sprint 6 | Performance Benchmarks | Performance | <3s cold start, <50MB bundle, <100MB memory | 3 | Not Started
Sprint 7 | TestFlight Beta (15 users) | Beta UAT | No P0 bugs; NPS > 30; crash-free > 99.5% | 15 | Not Started
Sprint 7 | Apple Guideline Compliance | Compliance | Pass all items on Apple HIG + App Store Review checklist | 1 | Not Started
Sprint 7 | Full Regression Suite | Regression | All features, screens, and languages pass end-to-end | 50 | Not Started
Sprint 7 | Security Review | Security | No hardcoded secrets, HTTPS everywhere, auth token handling | 10 | Not Started

## Timeline
12-Week Sprint Timeline
Milestone | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
| 3/16 | 3/23 | 3/30 | 4/6 | 4/13 | 4/20 | 4/27 | 5/4 | 5/11 | 5/18 | 5/25 | 6/1
SOFTWARE
Sprint 2: AI Navigator + RAG | W1 3/16: DONE
Sprint 3: Action Plans + Tracker | W1 3/16: DONE
Sprint 4: Calendar + Deadlines | W2 3/23: DONE*
Sprint 5: Document Vault + Email | W2 3/23: DONE*
Sprint 6: KB + i18n + Polish | W1 3/16: DONE
Sprint 7: App Store Prep + Submit | W1 3/16: DONE*
MARKETING
Brand guidelines | bar: W1 3/16 to W2 3/23
Landing page v1 | bar: W2 3/23 to W4 4/6
Content marketing begins | bar: W5 4/13 to W8 5/4
Beta recruitment (15 users) | bar: W7 4/27 to W8 5/4
Beta testing + feedback | bar: W9 5/11 to W10 5/18
Launch assets + ASO | bar: W11 5/25 to W12 6/1
LEGAL & COMPLIANCE
Apple Dev activation | bar: W1 3/16
Privacy Policy + ToS draft | bar: W3 3/30 to W4 4/6
Attorney review | bar: W5 4/13 to W6 4/20
Publish legal pages | bar: W6 4/20
Final compliance audit | bar: W10 5/18
SALES (RC PARTNERSHIPS)
Research target RCs + DDS registration | bar: W1 3/16 to W2 3/23
Initial outreach (3–5 RC directors) | bar: W3 3/30 to W4 4/6
Demo meetings (TestFlight build) | bar: W5 4/13 to W6 4/20
Negotiate pilot terms | bar: W7 4/27 to W8 5/4
Finalize pilot agreement (LOI) | bar: W9 5/11 to W10 5/18
Onboard pilot RC staff | bar: W11 5/25 to W12 6/1

## Dependencies
Critical Dependencies & Blockers
Dependency | Blocks | Owner | Due Date | Status
Apple Developer activation (48 hrs) | App ID, Sign-In capability, Team ID | Mike | Mar 14 | Pending
iOS OAuth Client ID (Google Cloud) | Google Sign-In on device | Mike | Mar 15 | Not Started
Web OAuth Client ID (Google Cloud) | Gmail/Calendar API calls | Mike | Mar 15 | Not Started
npm dependency install | All sprints | Mike | Mar 16 | Not Started
EAS Build dev profile | On-device testing | Mike | Mar 16 | Not Started
KB article embeddings (pgvector) | Sprint 2 RAG pipeline | Mike | Mar 22 | Not Started
Privacy Policy + ToS (hosted URLs) | App Store submission | Mike | Apr 26 | Not Started
DUNS number application | App Store org account | Mike | Apr 12 | Not Started
Attorney engagement (legal review) | Privacy Policy, ToS, AI disclaimer | Mike | Apr 13 | Not Started
RevenueCat account + setup | Sprint 7 subscription mgmt | Mike | May 18 | Not Started
DDS Provider Directory registration | RC vendorization | Mike | Mar 29 | Not Started
TestFlight beta testers (15) | Sprint 7 beta UAT | Mike | May 25 | Not Started

## Hours Summary
Sprint Hours Summary
Sprint | Dev Hours | QA Hours | Total Hours
Sprint 1: Auth + Onboarding (COMPLETE) | 42 | 0 | 42
Sprint 2: AI Navigator + RAG | 47 | 8 | 55
Sprint 3: Action Plans + Tracker | 33 | 6 | 39
Sprint 4: Calendar + Deadlines | 36 | 6 | 42
Sprint 5: Document Vault + Email | 32 | 6 | 38
Sprint 6: KB + i18n + Polish | 35 | 6 | 41
Sprint 7: App Store Prep + Submit | 31 | 18 | 49
TOTAL
Weekly capacity (solo dev, ~40 hrs/week): | 40
Total weeks required: