## Executive Summary
WAYPOINT GTM — GAP ANALYSIS & STATUS REPORT
As of March 15, 2026 ¦ Target: June 8, 2026 App Store Submission
SPRINT COMPLETION STATUS
Sprint | Status | Completion | Key Gaps
Sprint 1: Auth + Onboarding + Profile | Complete | 100% | None
Sprint 2: AI Navigator + RAG | Complete | 95% | Prompt caching not started, QA gate not run
Sprint 3: Action Plans + Tracker | Complete | 90% | Analytics UI partial, QA gate not run
Sprint 4: Calendar + Deadlines | Partial | 60% | Google Calendar API sync, push notifs, auto-calc deadlines
Sprint 5: Document Vault + Email | Partial | 50% | Email draft/send (Gmail API), expo-document-picker
Sprint 6: i18n + Polish + A11y | Complete | 85% | VoiceOver device audit pending, perf benchmarks
Sprint 7: App Store Prep | Complete | 75% | TestFlight build, Apple submission pending
OVERALL SOFTWARE PROGRESS
Metric | Value | Notes
Files created (Sprint 2-7) | 45+ | Screens, hooks, components, migrations, scripts
TypeScript errors | 0 | Strict mode, all sprints compile clean
Git commits (Sprint 1-7) | 9+ | Conventional commit style, all tracked
Languages supported | 3 | English, Spanish, Vietnamese
Supabase migrations | 4 | Schema, RLS, similarity search, actions
KB articles ready for ingestion | 26 | Enhanced JSON with embeddings schema
Edge Functions | 1 | ai-proxy (chat, classify, embed)

## Gap Analysis
GAP ANALYSIS — WHAT REMAINS TO SHIP
Grouped by criticality for June 8 App Store submission
# | Gap Item | Priority | Est Hours | Sprint | Resolution Path
P0 — MUST SHIP (App Store Blockers)
1 | Run Supabase migrations (002-004) on production | P0 | 1 | Infra | supabase db push or manual SQL execution
2 | Ingest 26 KB articles into pgvector (run ingest-kb.ts) | P0 | 1 | Infra | Set OPENAI_API_KEY + SUPABASE_SERVICE_ROLE_KEY, run script
3 | Deploy ai-proxy Edge Function + set secrets | P0 | 1 | Infra | supabase functions deploy ai-proxy; supabase secrets set
4 | Refactor client AI calls to use Edge Function (not direct API) | P0 | 4 | S2 | DONE — Client AI calls refactored to Edge Function proxy, API keys removed from client (Mar 15)
5 | Wire expo-document-picker for Document Vault uploads | P0 | 2 | S5 | DONE — vendor.d.ts types added, DocumentsScreen wired. npm install needed on device.
6 | Create EAS project + first TestFlight build | P0 | 3 | S7 | eas init → eas build --platform ios → TestFlight upload
7 | Generate App Store screenshots (6 screens × 2 sizes) | P0 | 3 | S7 | Run on simulator, capture 6.7" + 6.5"
8 | Submit to Apple App Store Review | P0 | 2 | S7 | Fill App Store Connect, upload build, submit
9 | Privacy Policy + Terms of Service pages (live URLs) | P0 | 3 | Legal | DONE — PrivacyPolicy.tsx + TermsOfService.tsx screens created in app (Mar 15)
10 | Set up Sentry or crash reporting | P0 | 2 | S7 | DONE — sentry.ts lib created, PII scrubbing, App.tsx integrated (Mar 15)
P1 — SHOULD SHIP (High Value but Not Blockers)
11 | Save-from-chat → Action Plan integration (UI button) | P1 | 3 | S2-S3 | DONE — 'Save as Action' button on NavigatorScreen message bubbles (Mar 15)
12 | Push notifications for deadlines (expo-notifications) | P1 | 4 | S4 | DONE — useNotifications.ts hook with deadline scheduling, AsyncStorage persistence (Mar 15)
13 | VoiceOver accessibility audit (all screens) | P1 | 4 | S6 | PARTIAL — accessibility.ts utilities + labels added to Home/Profile/Navigator. Device VoiceOver audit still needed.
14 | Performance benchmarks (<3s cold start, <50MB) | P1 | 2 | S6 | Measure with Expo build, optimize if needed
15 | Full QA regression (all features end-to-end) | P1 | 6 | S7 | Manual test plan across all screens, 3 languages
16 | Prompt caching for Claude API (cost optimization) | P1 | 2 | S2 | Add cache_control to system prompt blocks
P2 — NICE TO HAVE (Post-Launch)
17 | Google Calendar API integration (2-way sync) | P2 | 14 | S4 | OAuth token handling, conflict resolution — defer to v1.1
18 | Email draft generation + Gmail API send | P2 | 8 | S5 | Gmail API OAuth + draft builder — defer to v1.1
19 | Expense tracker | P2 | 6 | Post | New screen + hook — defer to v1.1
20 | Provider directory | P2 | 6 | Post | New screen + hook — defer to v1.1
21 | Benefits checker (diagnosis → eligibility) | P2 | 8 | Post | Complex logic from GAS MVP — defer to v1.1
22 | RC zip code lookup | P2 | 4 | Post | Port from GAS MVP, needs data source — defer to v1.1
23 | SMS integration (Twilio) | P2 | 4 | Post | Retention driver — defer to v1.1
24 | Landing page + waitlist website | P2 | 6 | Marketing | Vercel + Next.js site — separate workstream
VALIDATION — NOT STARTED (Separate from Software)
25 | Recruit 5 beta families (personal network) | P0 | 3 | Wk 1-2 | Friends, Embracing Autism, RCEB contacts
26 | Recruit 10 more beta families (Oakland networks) | P0 | 4 | Wk 3-4 | BIA, FB groups, Piedmont adaptive
27 | NPS survey from beta families (target >40) | P0 | 2 | Wk 4 | Tally form after 5+ sessions per family
28 | 3 documented outcome stories | P1 | 3 | Wk 4-6 | Family interviews: time saved, $ found, action taken
29 | Willingness-to-pay survey ($9.99/mo) | P1 | 2 | Wk 6 | Direct ask in interviews — target >40% yes
30 | 60-day validation report | P2 | 4 | Wk 8 | Compile all metrics for go/no-go decision

## Hours Remaining
HOURS REMAINING — BY PRIORITY
Category | P0 Hours | P1 Hours | P2 Hours | Total
Infrastructure / DevOps | 7 | 0 | 0 | 7
Software gaps (S2-S7) | 0 | 12 | 50 | 62
App Store / Legal | 5 | 0 | 0 | 5
Validation / User Testing | 9 | 5 | 4 | 18
Marketing / Content | 0 | 0 | 10 | 10
TOTAL | 21 | 17 | 64 | 102
KEY INSIGHT
P0 items total ~15 hours. At 20 hrs/week, that's <1 week to App Store submission readiness.
P0 + P1 total ~31 hours. At 20 hrs/week, that's ~1.5 weeks — well within the June 8 deadline.
P2 items (64 hours) are deferred to v1.1. They're high-value but not launch blockers.