## Project Plan
WAYPOINT AI ENGINE — IT PROJECT PLAN
Build Environment: Claude Cowork ¦ Owner: Mike ¦ Start: March 3, 2026 ¦ Target MVP: April 4, 2026
# | Task | Phase | Priority | Status | Owner | Est. Hours | Start | Due | Dependencies | Notes / Version History
WEEK 1: KNOWLEDGE BASE & DATA LAYER
1 | Set up Supabase project + enable pgvector extension | Week 1 | P0 - Critical | Not Started | Mike | 2 | 2026-03-03 | 2026-03-03 |  | Create project, enable extensions, configure RLS
2 | Create knowledge_chunks table + similarity search function | Week 1 | P0 - Critical | Not Started | Mike | 3 | 2026-03-03 | 2026-03-04 | Task 1 | Schema from Build Plan §5
3 | Create child_profiles table | Week 1 | P0 - Critical | Not Started | Mike | 2 | 2026-03-03 | 2026-03-04 | Task 1 | Include diagnosis[], regional_center, school_district
4 | Create ai_interactions logging table | Week 1 | P1 - High | Not Started | Mike | 1 | 2026-03-04 | 2026-03-04 | Task 1 | For analytics and prompt tuning
5 | Write KB docs: Regional Center (5 docs) | Week 1 | P0 - Critical | Not Started | Mike | 8 | 2026-03-03 | 2026-03-05 |  | Lanterman Act, intake, POS, IPP, fair hearing
6 | Write KB docs: IEP / School Services (5 docs) | Week 1 | P0 - Critical | Not Started | Mike | 8 | 2026-03-04 | 2026-03-06 |  | IDEA safeguards, CA Ed Code, SB 483, disputes
7 | Write KB docs: Benefits & Funding (5 docs) | Week 1 | P1 - High | Not Started | Mike | 6 | 2026-03-05 | 2026-03-07 |  | SSI, IHSS, Medi-Cal, funding waterfall, ABLE
8 | Build Python ingestion script (chunk + embed + store) | Week 1 | P0 - Critical | Not Started | Mike | 4 | 2026-03-05 | 2026-03-06 | Tasks 2, 5 | OpenAI text-embedding-3-small, 800-token chunks
9 | Run initial ingestion for RC + IEP knowledge bases | Week 1 | P0 - Critical | Not Started | Mike | 2 | 2026-03-06 | 2026-03-06 | Tasks 5, 6, 8 | Verify vector search returns relevant results
10 | Test similarity search with 10 sample questions | Week 1 | P1 - High | Not Started | Mike | 2 | 2026-03-06 | 2026-03-07 | Task 9 | Document precision/recall for each category
WEEK 2: CLASSIFICATION & RAG PIPELINE
11 | Build classification prompt (Claude Haiku) | Week 2 | P0 - Critical | Not Started | Mike | 3 | 2026-03-08 | 2026-03-08 |  | 7 categories + urgency + emotional state detection
12 | Test classification against 30+ real parent questions | Week 2 | P0 - Critical | Not Started | Mike | 4 | 2026-03-08 | 2026-03-09 | Task 11 | Target >90% accuracy; document misclassifications
13 | Write category-specific system prompts (7 categories) | Week 2 | P0 - Critical | Not Started | Mike | 8 | 2026-03-08 | 2026-03-10 |  | RC, IEP, Benefits, Insurance, Rights, Nav, Transitions
14 | Build ai-navigator Edge Function (full pipeline) | Week 2 | P0 - Critical | Not Started | Mike | 6 | 2026-03-09 | 2026-03-11 | Tasks 2, 11, 13 | Classify → Embed → Retrieve → Generate → Log
15 | Add child profile context injection to prompts | Week 2 | P1 - High | Not Started | Mike | 3 | 2026-03-10 | 2026-03-11 | Tasks 3, 14 | Personalize with RC, district, diagnosis, benefits
16 | Build structured JSON response parser | Week 2 | P1 - High | Not Started | Mike | 2 | 2026-03-10 | 2026-03-11 | Task 14 | Validate empathy, answer, action_steps, rights fields
17 | End-to-end test: 20 questions through full pipeline | Week 2 | P0 - Critical | Not Started | Mike | 4 | 2026-03-11 | 2026-03-12 | Task 14 | Test all 7 categories, verify context retrieval
18 | Tune prompts based on test results | Week 2 | P1 - High | Not Started | Mike | 3 | 2026-03-12 | 2026-03-12 | Task 17 | Iterate on misclassifications and weak responses
WEEK 3: FRONTEND INTEGRATION
19 | Build useAINavigator React hook | Week 3 | P0 - Critical | Not Started | Mike | 3 | 2026-03-13 | 2026-03-13 | Task 14 | Loading state, error handling, response typing
20 | Build EmpathyBanner component | Week 3 | P2 - Medium | Not Started | Mike | 1 | 2026-03-13 | 2026-03-13 |  | Teal card, warm tone, brief validation text
21 | Build ActionStepCard component | Week 3 | P0 - Critical | Not Started | Mike | 4 | 2026-03-13 | 2026-03-14 |  | Numbered steps, who/when/script, expandable
22 | Build RightsCallout component | Week 3 | P1 - High | Not Started | Mike | 2 | 2026-03-14 | 2026-03-14 |  | Highlighted sidebar with legal citation
23 | Build WarningBadge component | Week 3 | P2 - Medium | Not Started | Mike | 1 | 2026-03-14 | 2026-03-14 |  | Orange alert for common pitfalls
24 | Build DraftButton component (CTA for agent actions) | Week 3 | P0 - Critical | Not Started | Mike | 2 | 2026-03-14 | 2026-03-15 |  | 'Draft Appeal Letter', 'Draft Email' etc.
25 | Integrate Navigator chat screen with Edge Function | Week 3 | P0 - Critical | Not Started | Mike | 4 | 2026-03-15 | 2026-03-16 | Tasks 19-24 | Full chat flow: question → loading → response cards
26 | Add feedback buttons (thumbs up/down) + logging | Week 3 | P1 - High | Not Started | Mike | 2 | 2026-03-15 | 2026-03-16 | Task 25 | Write to ai_interactions.feedback column
27 | Build conversation history (multi-turn) | Week 3 | P1 - High | Not Started | Mike | 3 | 2026-03-16 | 2026-03-17 | Task 25 | Maintain context across follow-up questions
28 | UI polish + loading states + error handling | Week 3 | P2 - Medium | Not Started | Mike | 3 | 2026-03-16 | 2026-03-17 | Task 25 | Skeleton loaders, retry logic, offline handling
WEEK 4: AI AGENT LAYER (DRAFT & EXECUTE)
29 | Build ai-draft Edge Function | Week 4 | P0 - Critical | Not Started | Mike | 5 | 2026-03-18 | 2026-03-19 | Task 14 | Generic draft generator with type-specific prompts
30 | Write draft prompt: appeal_letter | Week 4 | P0 - Critical | Not Started | Mike | 3 | 2026-03-18 | 2026-03-19 |  | Insurance denial → appeal with medical necessity
31 | Write draft prompt: iep_email | Week 4 | P0 - Critical | Not Started | Mike | 3 | 2026-03-19 | 2026-03-20 |  | Email to school district re: evaluation/meeting
32 | Write draft prompt: rc_reimbursement | Week 4 | P1 - High | Not Started | Mike | 3 | 2026-03-19 | 2026-03-20 |  | RCEB reimbursement request with receipts
33 | Write draft prompt: iep_prep | Week 4 | P1 - High | Not Started | Mike | 3 | 2026-03-20 | 2026-03-20 |  | Meeting agenda, questions, rights, goals
34 | Write draft prompt: fair_hearing | Week 4 | P2 - Medium | Not Started | Mike | 2 | 2026-03-20 | 2026-03-21 |  | Request letter with legal citations
35 | Write draft prompt: medical_necessity | Week 4 | P2 - Medium | Not Started | Mike | 2 | 2026-03-20 | 2026-03-21 |  | Template for therapist to complete
36 | Build ReviewDraft screen (edit + approve flow) | Week 4 | P0 - Critical | Not Started | Mike | 5 | 2026-03-19 | 2026-03-21 | Task 29 | Editable text, Send/Download PDF buttons
37 | Integrate 'Open in Mail' for email drafts | Week 4 | P1 - High | Not Started | Mike | 2 | 2026-03-21 | 2026-03-21 | Task 36 | Pre-fill to/subject/body in native mail client
38 | Build document vault save for non-email drafts | Week 4 | P1 - High | Not Started | Mike | 3 | 2026-03-21 | 2026-03-22 | Task 36 | Save appeal letters, IEP prep docs to vault
WEEK 5: POLISH, EXPAND & LAUNCH PREP
39 | Write KB docs: Insurance (3 docs) | Week 5 | P1 - High | Not Started | Mike | 4 | 2026-03-23 | 2026-03-24 |  | Appeal process, medical necessity, EOB analysis
40 | Write KB docs: Rights & Advocacy (3 docs) | Week 5 | P1 - High | Not Started | Mike | 4 | 2026-03-23 | 2026-03-24 |  | Fair hearings, complaints, SB 483
41 | Write KB docs: Navigation + Transitions (4 docs) | Week 5 | P2 - Medium | Not Started | Mike | 4 | 2026-03-24 | 2026-03-25 |  | Provider finding, waitlists, age 3 transition, aging out
42 | Run ingestion for all new KB docs | Week 5 | P1 - High | Not Started | Mike | 2 | 2026-03-25 | 2026-03-25 | Tasks 39-41 | Re-run ingest script, verify search quality
43 | Prompt tuning: refine all 7 category prompts | Week 5 | P1 - High | Not Started | Mike | 4 | 2026-03-25 | 2026-03-26 | Task 17 | Based on feedback logs and test results
44 | Build basic analytics dashboard (interactions log) | Week 5 | P2 - Medium | Not Started | Mike | 3 | 2026-03-25 | 2026-03-26 | Task 4 | Category distribution, feedback rates, top questions
45 | Security review: RLS policies on all tables | Week 5 | P1 - High | Not Started | Mike | 3 | 2026-03-26 | 2026-03-26 |  | Users can only access own profiles and interactions
46 | Performance optimization: edge function cold starts | Week 5 | P2 - Medium | Not Started | Mike | 2 | 2026-03-26 | 2026-03-27 |  | Warm-up, caching, response time targets <3s
47 | End-to-end QA: 50 questions across all categories | Week 5 | P0 - Critical | Not Started | Mike | 5 | 2026-03-26 | 2026-03-27 | All | Full regression, all categories, all draft types
48 | Write README + internal documentation | Week 5 | P2 - Medium | Not Started | Mike | 3 | 2026-03-27 | 2026-03-27 |  | Setup guide, architecture docs, prompt library
TOTAL ESTIMATED HOURS | [5 empty] | 161

## Sprint Dashboard
SPRINT DASHBOARD — WEEKLY PROGRESS
Week | Sprint Theme | Tasks | Hours | P0 Tasks | Status | Completion %
Week 1 | Knowledge Base & Data Layer | 10 | 38 | Tasks 1-10 | Not Started | 0%
Week 2 | Classification & RAG Pipeline | 8 | 33 | Tasks 11-18 | Not Started | 0%
Week 3 | Frontend Integration | 10 | 25 | Tasks 19-28 | Not Started | 0%
Week 4 | AI Agent Layer (Draft & Execute) | 10 | 31 | Tasks 29-38 | Not Started | 0%
Week 5 | Polish, Expand & Launch Prep | 10 | 34 | Tasks 39-48 | Not Started | 0%
TOTAL |  | 48 | 161
KEY METRICS
Metric | Target / Current | Notes
Classification Accuracy Target | >90% | Test with 30+ real questions per sprint
Response Quality Score | TBD | Human review of AI responses (1-5 scale)
Avg. Response Time | <3 seconds | Edge function classify → generate → return
Knowledge Base Coverage | 0 / 7 categories | Track docs written per category
Draft Generation Success Rate | TBD | % of drafts approved without major edits
User Feedback (Thumbs Up Rate) | TBD | From in-app feedback buttons

## Version Control
VERSION CONTROL LOG
Track all changes to code, prompts, knowledge base, and configuration. One entry per meaningful change.
Version | Date | Component | Change Type | Description | Changed By | Tested | Notes
0.1.0 | 03/03/26 | Database | Initial | Create Supabase project, pgvector, base schema | Mike | No | knowledge_chunks, child_profiles, ai_interactions
0.1.1 | 03/03/26 | Knowledge Base | Initial | Regional Center KB docs v1 (5 docs) | Mike | No | Lanterman, intake, POS, IPP, fair hearing
0.1.2 | 03/04/26 | Knowledge Base | Initial | IEP KB docs v1 (5 docs) | Mike | No | IDEA, CA Ed Code, SB 483, meetings, disputes
0.1.3 | 03/05/26 | Ingestion | Initial | Python ingestion script + initial data load | Mike | No | chunk_document + embed_and_store
0.2.0 | 03/10/26 | AI Engine | Initial | Classification prompt v1 (Haiku) | Mike | No | 7 categories + urgency + emotional state
0.2.1 | 03/10/26 | AI Engine | Initial | Category system prompts v1 (7 prompts) | Mike | No | RC, IEP, Benefits, Insurance, Rights, Nav, Trans
0.2.2 | 03/11/26 | Edge Function | Initial | ai-navigator Edge Function v1 | Mike | No | Full classify → retrieve → generate pipeline
0.3.0 | 03/17/26 | Frontend | Initial | useAINavigator hook + Action Card components | Mike | No | Hook + 5 card components
0.3.1 | 03/19/26 | Frontend | Initial | Navigator chat screen integration | Mike | No | Full chat flow wired to Edge Function
0.4.0 | 03/24/26 | AI Engine | Initial | ai-draft Edge Function + 6 draft prompts | Mike | No | appeal, iep_email, rc_reimburse, iep_prep, hearing, med
0.4.1 | 03/25/26 | Frontend | Initial | ReviewDraft screen + Open in Mail | Mike | No | Edit, approve, send/download flow
0.5.0 | 03/31/26 | Knowledge Base | Expand | Insurance, Rights, Navigation KB docs (10 docs) | Mike | No | Complete all 7 category knowledge bases
1.0.0 | 04/04/26 | Release | MVP | AI Navigator MVP — all features complete | Mike | Yes | Full QA, 50-question regression, all draft types

## Risk Register
RISK REGISTER
# | Risk | Category | Likelihood | Impact | Mitigation | Owner | Status
1 | Classification accuracy below 90% | AI Quality | Medium | High | Iterative prompt tuning; add fallback 'general' category; human review loop for edge cases | Mike | Open
2 | Knowledge base gaps cause incorrect guidance | Content | High | High | Start with RC + IEP (deepest expertise); flag low-confidence responses; cite sources in every response | Mike | Open
3 | Hallucinated legal citations | AI Safety | Medium | Critical | RAG-only responses (never generate citations from training data); validate against KB; add disclaimer | Mike | Open
4 | Edge Function cold start latency >5s | Performance | Medium | Medium | Warm-up scheduled invocations; optimize prompt length; cache embeddings; consider Haiku for simple questions | Mike | Open
5 | OpenAI embedding API rate limits | Infrastructure | Low | Medium | Batch ingestion during off-peak; cache embeddings; pre-compute for common questions | Mike | Open
6 | Supabase pgvector performance at scale | Infrastructure | Low | Medium | IVFFlat index with 100 lists; partition by category; monitor query times; consider Pinecone if needed | Mike | Open
7 | Parents rely on AI for legal decisions | Liability | Medium | High | Every response includes 'consult an advocate' disclaimer; offer to connect to human navigators; log all interactions | Mike | Open
8 | Scope creep delays MVP launch | Project | High | Medium | Strict P0-only for Weeks 1-3; defer P2/P3 to post-MVP; weekly sprint review against timeline | Mike | Open
9 | Anthropic API cost exceeds budget | Financial | Low | Medium | Use Haiku for classification (cheap); monitor per-query cost; set usage alerts; consider caching frequent responses | Mike | Open
10 | OCR quality for IEP documents | Technical | Medium | Medium | Google Cloud Vision as primary; fallback to manual text input; structured upload form for key fields | Mike | Open

## Prompt Library
PROMPT LIBRARY — VERSION TRACKING
Track every prompt version. Never overwrite — always create a new version entry.
Prompt ID | Category | Version | Status | Last Updated | Change Summary
CLASSIFY-001 | Classification | v1.0 | Draft | 03/10/26 | Initial 7-category classifier with urgency + emotional state
SYS-RC-001 | Regional Center | v1.0 | Draft | 03/10/26 | Lanterman Act, intake, IPP, POS, fair hearing focus
SYS-IEP-001 | IEP / School | v1.0 | Draft | 03/10/26 | IDEA, FAPE, PWN, SB 483, dispute resolution focus
SYS-BEN-001 | Benefits | v1.0 | Draft | 03/10/26 | Funding waterfall, SSI, IHSS, Medi-Cal, ABLE
SYS-INS-001 | Insurance | v1.0 | Draft | 03/10/26 | Denials, appeals, medical necessity, EOB analysis
SYS-RGT-001 | Rights | v1.0 | Draft | 03/10/26 | Fair hearings, complaints, OCR, timelines
SYS-NAV-001 | Navigation | v1.0 | Draft | 03/10/26 | Provider finding, waitlists, general guidance
SYS-TRN-001 | Transitions | v1.0 | Draft | 03/10/26 | Early Start→IEP, school→adult, aging out
DFT-APL-001 | Draft: Appeal | v1.0 | Draft | 03/24/26 | Insurance appeal letter with medical necessity argument
DFT-IEP-001 | Draft: IEP Email | v1.0 | Draft | 03/24/26 | Email to school district requesting eval/meeting
DFT-RMB-001 | Draft: Reimbursement | v1.0 | Draft | 03/24/26 | RC reimbursement request with receipts/auth
DFT-PRP-001 | Draft: IEP Prep | v1.0 | Draft | 03/24/26 | Meeting agenda, questions, rights, goals
DFT-FHR-001 | Draft: Fair Hearing | v1.0 | Draft | 03/24/26 | Fair hearing request letter
DFT-MED-001 | Draft: Med Necessity | v1.0 | Draft | 03/24/26 | Therapist medical necessity template

## Cost Tracker
MONTHLY COST TRACKER
Service | Provider | Monthly Est. | Actual (Month 1) | Actual (Month 2) | Notes
Supabase Pro (Postgres + pgvector) | Supabase | 25 |  |  | Includes auth, edge functions, storage
Anthropic API — Classification (Haiku) | Anthropic | 15 |  |  | ~$0.001 per classification call
Anthropic API — Generation (Sonnet) | Anthropic | 75 |  |  | ~$0.01-0.03 per full response
Anthropic API — Draft Generation (Sonnet) | Anthropic | 35 |  |  | ~$0.02-0.05 per draft
OpenAI Embeddings API | OpenAI | 10 |  |  | text-embedding-3-small, ingestion + queries
Google Cloud Vision (OCR) | Google | 20 |  |  | IEP / document processing
Expo / React Native (EAS Build) | Expo | 0 |  |  | Free tier for development
Domain + DNS | Cloudflare | 0 |  |  | waypoint.app or similar
MONTHLY TOTAL |  | 180