## Sprint Board
Issue ID | Phase | Sprint | Sprint Name | Status | Workstream | Type | Severity | Title | Story Pts | Dependencies | Est Hours | Owner | CoWork Notes
ENT-001 | Phase 1 | Sprint 1 | Security Foundation | To Do | Security | Bug | Critical | Implement RLS policies on all 12 Supabase tables | 8 | None | 16 | Security Team
ENT-002 | Phase 1 | Sprint 1 | Security Foundation | To Do | Infrastructure | Improvement | Critical | API rate limiting with Upstash | 5 | None | 8 | Infrastructure Team
ENT-003 | Phase 1 | Sprint 1 | Security Foundation | To Do | Security | Improvement | High | Supabase Vault for secret management | 3 | None | 4 | Security Team
ENT-004 | Phase 1 | Sprint 1 | Security Foundation | To Do | Compliance | Feature | High | Audit logging for data access events | 5 | None | 10 | Compliance Officer
ENT-005 | Phase 1 | Sprint 1 | Security Foundation | To Do | Security | Improvement | Medium | Service account setup for Edge Functions | 2 | None | 3 | DevOps Team
ENT-006 | Phase 1 | Sprint 2 | CI/CD & Testing Foundation | Not Started | DevOps | Feature | Critical | GitHub Actions CI/CD pipeline (lint → test → build → deploy) | 8 | None | 16 | DevOps Team
ENT-007 | Phase 1 | Sprint 2 | CI/CD & Testing Foundation | Not Started | DevOps | Improvement | High | Supabase CLI migration workflow | 3 | None | 6 | DevOps Team
ENT-008 | Phase 1 | Sprint 2 | CI/CD & Testing Foundation | Not Started | QA | Feature | High | Jest unit test framework for React Native | 5 | None | 10 | QA Team
ENT-009 | Phase 1 | Sprint 2 | CI/CD & Testing Foundation | Not Started | QA | Feature | High | Vitest for Supabase Edge Functions | 3 | None | 6 | QA Team
ENT-010 | Phase 1 | Sprint 2 | CI/CD & Testing Foundation | Not Started | DevOps | Feature | High | EAS Build configuration for iOS | 5 | None | 8 | DevOps Team
ENT-011 | Phase 1 | Sprint 3 | Caching & Monitoring | Not Started | AI Ops | Feature | Critical | Upstash Redis integration for AI response caching | 8 | ENT-005 | 16 | AI Team
ENT-012 | Phase 1 | Sprint 3 | Caching & Monitoring | Not Started | Observability | Feature | High | Sentry error monitoring (React Native + Edge Functions) | 3 | None | 6 | DevOps Team
ENT-013 | Phase 1 | Sprint 3 | Caching & Monitoring | Not Started | Observability | Feature | Medium | PostHog analytics integration | 3 | None | 6 | Analytics Team
ENT-014 | Phase 1 | Sprint 3 | Caching & Monitoring | Not Started | Observability | Feature | Medium | Uptime monitoring with alerting | 2 | None | 3 | DevOps Team
ENT-015 | Phase 1 | Sprint 3 | Caching & Monitoring | Not Started | Compliance | Bug | Critical | Account deletion flow (Apple requirement) | 5 | None | 10 | Compliance Officer
ENT-016 | Phase 2 | Sprint 4 | Compliance Infrastructure | Not Started | Compliance | Feature | Critical | HIPAA BAA execution (Supabase Enterprise) | 3 | None | 8 | Compliance Officer
ENT-017 | Phase 2 | Sprint 4 | Compliance Infrastructure | Not Started | Compliance | Feature | Critical | Anthropic DPA / BAA verification | 2 | None | 4 | Legal Team
ENT-018 | Phase 2 | Sprint 4 | Compliance Infrastructure | Not Started | Compliance | Feature | High | Data retention automation (auto-purge expired data) | 5 | ENT-007 | 10 | DevOps Team
ENT-019 | Phase 2 | Sprint 4 | Compliance Infrastructure | Not Started | Compliance | Feature | High | COPPA compliance validation and documentation | 3 | None | 6 | Compliance Officer
ENT-020 | Phase 2 | Sprint 4 | Compliance Infrastructure | Not Started | Compliance | Feature | High | Privacy impact assessment | 3 | None | 8 | Security Team
ENT-021 | Phase 2 | Sprint 5 | AI Quality & Full Test Suite | Not Started | AI Ops | Feature | Critical | AI quality monitoring dashboard | 8 | ENT-012 | 16 | AI Team
ENT-022 | Phase 2 | Sprint 5 | AI Quality & Full Test Suite | Not Started | AI Ops | Feature | High | Prompt versioning system (git-tracked with metadata) | 5 | None | 8 | AI Team
ENT-023 | Phase 2 | Sprint 5 | AI Quality & Full Test Suite | Not Started | QA | Feature | High | AI test suite (100+ curated questions across 7 categories) | 8 | None | 20 | QA Team
ENT-024 | Phase 2 | Sprint 5 | AI Quality & Full Test Suite | Not Started | QA | Feature | High | Integration tests for Supabase + Edge Functions | 5 | ENT-009 | 10 | QA Team
ENT-025 | Phase 2 | Sprint 5 | AI Quality & Full Test Suite | Not Started | QA | Feature | High | Detox E2E testing for React Native (iOS) | 5 | ENT-010 | 12 | QA Team
ENT-026 | Phase 2 | Sprint 5 | AI Quality & Full Test Suite | Not Started | AI Ops | Feature | Medium | Cost alerting (75/90/100% budget thresholds) | 3 | None | 4 | Finance Team
ENT-027 | Phase 2 | Sprint 5 | AI Quality & Full Test Suite | Not Started | AI Ops | Feature | High | AI fallback strategy (cached responses when API down) | 5 | ENT-011 | 8 | AI Team
ENT-028 | Phase 2 | Sprint 6 | i18n & Core Features | Not Started | i18n | Feature | Critical | react-i18next framework implementation | 8 | None | 16 | Frontend Team
ENT-029 | Phase 2 | Sprint 6 | i18n & Core Features | Not Started | i18n | Feature | Critical | Complete Spanish translation (all screens) | 8 | ENT-028 | 20 | Localization Team
ENT-030 | Phase 2 | Sprint 6 | i18n & Core Features | Not Started | Features | Feature | High | Push notifications (Expo Push) for deadlines | 5 | None | 10 | Frontend Team
ENT-031 | Phase 2 | Sprint 6 | i18n & Core Features | Not Started | Features | Feature | High | Multi-child profile support | 8 | None | 16 | Backend Team
ENT-032 | Phase 2 | Sprint 6 | i18n & Core Features | Not Started | Features | Feature | High | Document upload + vault (Supabase Storage) | 5 | None | 10 | Backend Team
ENT-033 | Phase 2 | Sprint 6 | i18n & Core Features | Not Started | Subscriptions | Feature | Critical | RevenueCat subscription infrastructure | 8 | None | 16 | Backend Team
ENT-034 | Phase 2 | Sprint 6 | i18n & Core Features | Not Started | DevOps | Feature | High | Staging environment (separate Supabase project) | 3 | ENT-007 | 6 | DevOps Team
ENT-035 | Phase 3 | Sprint 7 | Multi-Tenancy Foundation | Not Started | Multi-Tenancy | Feature | Critical | Organization accounts (org_id, org settings, org-level RLS) | 8 | ENT-001 | 20 | Backend Team
ENT-036 | Phase 3 | Sprint 7 | Multi-Tenancy Foundation | Not Started | Multi-Tenancy | Feature | Critical | Role-based access control (Admin/Manager/Support/User) | 8 | ENT-035 | 16 | Backend Team
ENT-037 | Phase 3 | Sprint 7 | Multi-Tenancy Foundation | Not Started | Multi-Tenancy | Feature | High | Admin dashboard (org usage, user management) | 8 | ENT-036 | 20 | Frontend Team
ENT-038 | Phase 3 | Sprint 7 | Multi-Tenancy Foundation | Not Started | Multi-Tenancy | Feature | Medium | White-labeling framework (colors, logos, KB per org) | 5 | ENT-035 | 12 | Frontend Team
ENT-039 | Phase 3 | Sprint 7 | Multi-Tenancy Foundation | Not Started | Multi-Tenancy | Feature | Medium | B2B deployment documentation and onboarding flow | 3 | ENT-036 | 8 | Product Team
ENT-040 | Phase 3 | Sprint 8 | Languages & KB Expansion | Not Started | i18n | Feature | High | Vietnamese translation (all screens + AI responses) | 8 | ENT-028 | 20 | Localization Team
ENT-041 | Phase 3 | Sprint 8 | Languages & KB Expansion | Not Started | i18n | Feature | High | Tagalog translation | 8 | ENT-028 | 20 | Localization Team
ENT-042 | Phase 3 | Sprint 8 | Languages & KB Expansion | Not Started | i18n | Feature | High | Mandarin translation | 8 | ENT-028 | 20 | Localization Team
ENT-043 | Phase 3 | Sprint 8 | Languages & KB Expansion | Not Started | KB | Feature | High | RC-specific content for 21 Regional Centers | 8 | None | 40 | Content Team
ENT-044 | Phase 3 | Sprint 8 | Languages & KB Expansion | Not Started | KB | Feature | High | Scale KB from 25 to 100+ articles | 5 | None | 30 | Content Team
ENT-045 | Phase 3 | Sprint 8 | Languages & KB Expansion | Not Started | KB | Feature | Medium | Content versioning with effective dates | 3 | None | 8 | Backend Team
ENT-046 | Phase 3 | Sprint 9 | Testing & Compliance | Not Started | Accessibility | Feature | Critical | WCAG AA accessibility audit + fixes | 8 | None | 20 | QA Team
ENT-047 | Phase 3 | Sprint 9 | Testing & Compliance | Not Started | Accessibility | Feature | High | VoiceOver + TalkBack testing and fixes | 5 | ENT-046 | 12 | QA Team
ENT-048 | Phase 3 | Sprint 9 | Testing & Compliance | Not Started | QA | Feature | High | Performance load testing (k6 — 1,000 concurrent) | 5 | None | 10 | QA Team
ENT-049 | Phase 3 | Sprint 9 | Testing & Compliance | Not Started | Security | Feature | High | OWASP Mobile Top 10 security audit | 5 | None | 12 | Security Team
ENT-050 | Phase 3 | Sprint 9 | Testing & Compliance | Not Started | Compliance | Feature | High | SOC 2 readiness assessment | 5 | None | 16 | Compliance Officer
ENT-051 | Phase 3 | Sprint 9 | Testing & Compliance | Not Started | AI Ops | Feature | Medium | Prompt A/B testing framework | 5 | ENT-022 | 10 | AI Team
ENT-052 | Phase 4 | Sprint 10 | Advanced AI & Cross-Region | Not Started | Infrastructure | Feature | High | Cross-region database replication plan | 5 | None | 12 | Infrastructure Team
ENT-053 | Phase 4 | Sprint 10 | Advanced AI & Cross-Region | Not Started | AI Ops | Feature | Medium | Document intelligence (IEP redline / analysis) | 8 | None | 24 | AI Team
ENT-054 | Phase 4 | Sprint 10 | Advanced AI & Cross-Region | Not Started | AI Ops | Feature | Medium | Insurance policy analysis (EOB parsing) | 5 | None | 16 | AI Team
ENT-055 | Phase 4 | Sprint 10 | Advanced AI & Cross-Region | Not Started | AI Ops | Feature | Medium | AI provider abstraction layer (multi-model readiness) | 5 | ENT-022 | 10 | AI Team
ENT-056 | Phase 4 | Sprint 11 | Multi-State & Community | Not Started | KB | Feature | High | Multi-state architecture (federal baseline + state overlays) | 8 | ENT-044 | 20 | Backend Team
ENT-057 | Phase 4 | Sprint 11 | Multi-State & Community | Not Started | KB | Feature | High | Scale KB to 200+ articles | 5 | ENT-044 | 30 | Content Team
ENT-058 | Phase 4 | Sprint 11 | Multi-State & Community | Not Started | Features | Feature | Medium | Provider ratings / community layer | 5 | None | 16 | Frontend Team
ENT-059 | Phase 4 | Sprint 11 | Multi-State & Community | Not Started | Multi-Tenancy | Feature | High | Outcome tracking and ROI reporting | 8 | ENT-037 | 16 | Analytics Team
ENT-060 | Phase 4 | Sprint 12 | Enterprise Sales & Growth | Not Started | Multi-Tenancy | Feature | Medium | Enterprise sales toolkit and pricing engine | 5 | None | 12 | Product Team

## User Stories
Issue ID | Phase | Sprint | Title | User Story | Acceptance Criteria
ENT-001 | Phase 1 | Sprint 1 | Implement RLS policies on all 12 Supabase tables | As a Waypoint user, I want my family's data to only be accessible by me so that sensitive disability and financial information is protected. | 1. RLS policy on families table restricts SELECT/INSERT/UPDATE/DELETE to auth.uid() = user_id. 2. RLS on children/diagnoses/services cascade through family_id. 3. Verified: User A cannot see User B's data via Supabase client. 4. Edge Functions use service role for admin operations only.
ENT-002 | Phase 1 | Sprint 1 | API rate limiting with Upstash | As a system administrator, I want API requests to be rate-limited so that malicious actors cannot overwhelm the system. | 1. Upstash Redis configured with token bucket algorithm. 2. Rate limit: 100 requests/minute per IP, 1000/minute per authenticated user. 3. Returns 429 status with Retry-After header when exceeded. 4. Metrics logged to Sentry for monitoring.
ENT-003 | Phase 1 | Sprint 1 | Supabase Vault for secret management | As a DevOps engineer, I want secrets stored securely in Supabase Vault so that API keys and credentials are not exposed in code. | 1. Supabase Vault created with at least 5 secret entries (Anthropic API key, Upstash token, etc.). 2. Secrets rotated automatically every 90 days. 3. Access logs recorded for all secret retrieval. 4. Zero secrets in .env files or version control.
ENT-004 | Phase 1 | Sprint 1 | Audit logging for data access events | As a compliance officer, I want all data access events logged so that we can audit who accessed sensitive information and when. | 1. Audit log table captures user_id, table_name, operation (SELECT/INSERT/UPDATE/DELETE), timestamp, ip_address. 2. All data access via Supabase client logged automatically via RLS audit triggers. 3. Audit logs retained for 2 years. 4. Real-time alerts triggered for suspicious patterns (>10 failed auth attempts).
ENT-005 | Phase 1 | Sprint 1 | Service account setup for Edge Functions | As a backend developer, I want Edge Functions to have dedicated service accounts so they can perform admin operations safely. | 1. Service account created with restricted permissions (supabase_admin role). 2. Service account credentials stored in Supabase Vault. 3. Edge Functions authenticated via service role JWT. 4. All service account actions logged separately for auditing.
ENT-006 | Phase 1 | Sprint 2 | GitHub Actions CI/CD pipeline (lint → test → build → deploy) | As a developer, I want automated testing and deployment so code changes are validated before reaching production. | 1. GitHub Actions workflow: lint (ESLint) → test (Jest/Vitest) → build → deploy staging/prod. 2. All PRs require passing CI checks before merge. 3. Deployment to staging on PR merge, production via manual trigger. 4. Rollback available within 5 minutes of failed deployment.
ENT-007 | Phase 1 | Sprint 2 | Supabase CLI migration workflow | As a database administrator, I want a CLI-based migration workflow so schema changes are version-controlled and reproducible. | 1. supabase db push/pull commands integrated into CI/CD. 2. Migrations stored in migrations/ directory with timestamps. 3. Migration rollback tested in staging environment. 4. CI pipeline validates migration syntax before applying.
ENT-008 | Phase 1 | Sprint 2 | Jest unit test framework for React Native | As a QA engineer, I want comprehensive unit tests for React Native components so regressions are caught early. | 1. Jest configured with React Native preset. 2. At least 100 unit tests covering components, hooks, and utilities. 3. Code coverage minimum 80%. 4. Tests run in CI/CD pipeline and block merge if coverage drops.
ENT-009 | Phase 1 | Sprint 2 | Vitest for Supabase Edge Functions | As a backend developer, I want unit tests for Edge Functions so business logic is validated before deployment. | 1. Vitest configured for Edge Functions testing. 2. At least 50 tests covering all critical function paths. 3. Tests mock Supabase client and external API calls. 4. Coverage report generated and tracked in CI.
ENT-010 | Phase 1 | Sprint 2 | EAS Build configuration for iOS | As a mobile developer, I want automated iOS builds via EAS so releases are consistent and reproducible. | 1. EAS Build configured with ios build profile. 2. Staging and production build configurations defined. 3. Build artifacts stored for 30 days. 4. iOS app signed with production certificate and ready for App Store submission.
ENT-011 | Phase 1 | Sprint 3 | Upstash Redis integration for AI response caching | As a parent asking common questions, I want fast responses so I don't wait 5-8 seconds every time. | 1. Redis cache stores AI responses keyed by normalized question + category. 2. Cache TTL: 24 hours for factual content, 1 hour for personalized responses. 3. Cache hit returns in <500ms vs 3-8s for API call. 4. Cache bypass available for questions containing child-specific details.
ENT-012 | Phase 1 | Sprint 3 | Sentry error monitoring (React Native + Edge Functions) | As a DevOps engineer, I want real-time error alerts so production issues are caught immediately. | 1. Sentry SDK integrated into React Native app and Edge Functions. 2. Error events include stack trace, context, breadcrumbs, and user info. 3. Critical errors trigger Slack alerts within 1 minute. 4. Error trends dashboard shows top errors and affected users.
ENT-013 | Phase 1 | Sprint 3 | PostHog analytics integration | As a product manager, I want user behavior analytics so we understand how features are used. | 1. PostHog SDK integrated into React Native app. 2. Custom events tracked for key user actions (login, question asked, answer viewed, etc.). 3. Cohort analysis available (e.g., retention by signup date). 4. Privacy: All analytics respect user opt-out preference.
ENT-014 | Phase 1 | Sprint 3 | Uptime monitoring with alerting | As a system administrator, I want uptime monitoring so I know if the service is down. | 1. Uptime monitoring checks API endpoint every 60 seconds. 2. Slack alert sent if service is down for >5 minutes. 3. Dashboard shows uptime percentage (target: 99.9%). 4. Incident response playbook documented and accessible.
ENT-015 | Phase 1 | Sprint 3 | Account deletion flow (Apple requirement) | As a user, I want to be able to delete my account so my data is removed from the system. | 1. User can initiate account deletion from Settings > Account. 2. 30-day grace period before actual deletion (allows undo). 3. All user data (families, children, messages, documents) deleted. 4. Deletion request logged and compliant with Apple App Store guidelines.
ENT-016 | Phase 2 | Sprint 4 | HIPAA BAA execution (Supabase Enterprise) | As a healthcare provider, I want HIPAA compliance so we can securely handle patient health information. | 1. Supabase Enterprise plan with HIPAA BAA signed and executed. 2. Data encrypted at rest (AES-256) and in transit (TLS 1.2+). 3. Audit trails maintained for all PHI access. 4. Business Associate Agreement governs data handling and liability.
ENT-017 | Phase 2 | Sprint 4 | Anthropic DPA / BAA verification | As a legal officer, I want data processing agreements with Anthropic so we're compliant with data protection laws. | 1. Anthropic DPA signed covering GDPR/CCPA/HIPAA requirements. 2. API calls logged with data processing classification. 3. Data residency requirements documented and enforced. 4. Audit rights confirmed in DPA.
ENT-018 | Phase 2 | Sprint 4 | Data retention automation (auto-purge expired data) | As a compliance officer, I want data automatically deleted per retention policies so we don't over-retain information. | 1. Retention policy: deleted account data purged after 30 days, archived content after 7 years. 2. Automated nightly job purges expired records. 3. Purge operations logged and auditable. 4. Compliance report generated monthly showing retained vs. purged records.
ENT-019 | Phase 2 | Sprint 4 | COPPA compliance validation and documentation | As a product manager, I want COPPA compliance documented so we can serve families with children under 13. | 1. Parent consent flow implemented and documented. 2. No targeted advertising or tracking of children. 3. Privacy policy includes age-specific language. 4. COPPA compliance checklist completed and signed by legal.
ENT-020 | Phase 2 | Sprint 4 | Privacy impact assessment | As a privacy officer, I want a formal PIA so we understand privacy risks of new features. | 1. Privacy Impact Assessment completed covering all data flows. 2. Risk matrix created (likelihood vs. impact). 3. Mitigation strategies documented for medium/high risks. 4. Reviewed and approved by privacy and legal teams.
ENT-021 | Phase 2 | Sprint 5 | AI quality monitoring dashboard | As an AI team lead, I want a dashboard monitoring response quality so we can catch degradation immediately. | 1. Dashboard shows AI response metrics: accuracy, latency, error rate, cost per query. 2. Historical trends tracked over time. 3. Alerts triggered if accuracy drops >5% or errors exceed 1%. 4. Drill-down view shows individual poor responses with detailed feedback.
ENT-022 | Phase 2 | Sprint 5 | Prompt versioning system (git-tracked with metadata) | As an AI engineer, I want prompt versions tracked in git so changes are auditable and rollbackable. | 1. Prompts stored in prompts/ directory with version numbers. 2. Git commit message includes version metadata (date, author, change summary). 3. System can load any historical prompt version. 4. Prompt effectiveness metrics tied to version for A/B comparison.
ENT-023 | Phase 2 | Sprint 5 | AI test suite (100+ curated questions across 7 categories) | As a QA engineer, I want a comprehensive test suite so AI quality is validated before releases. | 1. Test suite contains 100+ curated questions across 7 categories. 2. Each question has expected answer and max acceptable latency. 3. Test suite run before each production deployment. 4. Regression report shows which categories degraded.
ENT-024 | Phase 2 | Sprint 5 | Integration tests for Supabase + Edge Functions | As a backend developer, I want integration tests validating database + function interaction. | 1. Test suite covers: data read/write, RLS enforcement, error handling, edge cases. 2. Tests run against staging Supabase project. 3. Tests verify response format, latency (<1s), and error messages. 4. Coverage includes both happy path and failure scenarios.
ENT-025 | Phase 2 | Sprint 5 | Detox E2E testing for React Native (iOS) | As a QA engineer, I want end-to-end tests so critical user workflows are validated. | 1. Detox E2E tests cover: login → navigate screens → ask question → view answer. 2. Tests run on physical iOS device and simulator. 3. Tests validate UI elements, text content, and user interactions. 4. E2E tests run nightly and block release if failed.
ENT-026 | Phase 2 | Sprint 5 | Cost alerting (75/90/100% budget thresholds) | As a finance manager, I want alerts when AI costs approach budget limits so we can manage spending. | 1. System tracks daily API costs vs. monthly budget. 2. Alerts: 75% threshold (email), 90% (Slack urgent), 100% (disable new queries). 3. Cost breakdown by API (Anthropic, Upstash, etc.) visible. 4. Forecast calculates if current burn rate will exceed budget.
ENT-027 | Phase 2 | Sprint 5 | AI fallback strategy (cached responses when API down) | As a parent, I want responses even when APIs are temporarily unavailable so the app is resilient. | 1. When Anthropic API is unavailable, system returns cached response from similar recent query. 2. Cached response marked as cached in UI ("Previously answered: ..." notice). 3. System retries API call in background. 4. Fallback available for >95% of common questions based on cache.
ENT-028 | Phase 2 | Sprint 6 | react-i18next framework implementation | As a developer, I want i18n framework integrated so we can easily add languages. | 1. react-i18next configured with namespace splits (common, home, settings, etc.). 2. Translation keys all converted to i18n calls. 3. Language switcher in Settings. 4. All hardcoded strings removed from codebase.
ENT-029 | Phase 2 | Sprint 6 | Complete Spanish translation (all screens) | As a Spanish-speaking parent, I want the entire app in Spanish so I can use it comfortably. | 1. All user-facing text translated to Spanish (Latin American variant). 2. AI prompts and responses in Spanish. 3. Professional translator review completed. 4. RTL text handling not applicable but verified for future Arabic.
ENT-030 | Phase 2 | Sprint 6 | Push notifications (Expo Push) for deadlines | As a parent, I want deadline reminders so I don't miss important dates. | 1. Expo Push Notifications configured. 2. Notification triggered 1 day before deadline, then at 6am on deadline day. 3. User can customize notification frequency in Settings. 4. Notification contains deadline title, child name, days remaining.
ENT-031 | Phase 2 | Sprint 6 | Multi-child profile support | As a parent with multiple children, I want separate profiles for each child so I can manage different needs. | 1. Users can create up to 10 child profiles. 2. Each child has own settings, documents, services, and progress tracking. 3. Quick switcher to jump between children. 4. Dashboard shows aggregate view across all children.
ENT-032 | Phase 2 | Sprint 6 | Document upload + vault (Supabase Storage) | As a parent, I want to store important documents so they're organized and accessible. | 1. Document upload to Supabase Storage with progress bar. 2. Support: PDF, DOC, JPG, PNG, max 50MB per file, unlimited total. 3. Documents organized by category (Medical, IEP, Insurance, etc.). 4. Full-text search on document names and metadata.
ENT-033 | Phase 2 | Sprint 6 | RevenueCat subscription infrastructure | As a product team, I want subscription handling abstracted so we can launch premium tiers. | 1. RevenueCat SDK configured for iOS and Android. 2. Subscription products: Basic (free), Pro ($9.99/mo), Enterprise (custom). 3. Entitlements visible in app based on subscription level. 4. Graceful downgrade handling when subscription expires.
ENT-034 | Phase 2 | Sprint 6 | Staging environment (separate Supabase project) | As a developer, I want a staging environment so I can test changes before production. | 1. Separate Supabase staging project with identical schema. 2. EAS Build creates staging APK/IPA. 3. Staging environment accessible via settings toggle. 4. Nightly data sync from production (anonymized) for realistic testing.
ENT-035 | Phase 3 | Sprint 7 | Organization accounts (org_id, org settings, org-level RLS) | As a Family Resource Center director, I want to deploy Waypoint for our 200 client families with our branding so they trust the tool. | 1. org_id column on families, organizations table created with org_settings (name, colors, logo_url). 2. RLS policies scope data to org. 3. Org admin can invite users via email with role assignment. 4. Org dashboard shows aggregate usage, user list, and settings.
ENT-036 | Phase 3 | Sprint 7 | Role-based access control (Admin/Manager/Support/User) | As an organization admin, I want to assign roles so I can delegate management tasks. | 1. Four roles defined: Admin (full access), Manager (user management), Support (user support only), User (read-only for own family). 2. Role assignments in admin dashboard. 3. Permissions enforced via RLS policies and application logic. 4. Audit log tracks role changes.
ENT-037 | Phase 3 | Sprint 7 | Admin dashboard (org usage, user management) | As an admin, I want a dashboard to manage users and monitor usage. | 1. Dashboard shows: active users, sign-ups trend, questions asked, cost breakdown. 2. User management table: add/remove/disable users, change roles. 3. Usage export to CSV for reporting. 4. Compliance report showing audit log summary.
ENT-038 | Phase 3 | Sprint 7 | White-labeling framework (colors, logos, KB per org) | As an organization, I want to white-label the app with our branding. | 1. Org can upload logo, set primary/secondary colors. 2. App theme updated dynamically from org_settings. 3. Org-specific knowledge base articles pinned to top. 4. App name can be customized ("Child Support - ABC Org" vs "Waypoint").
ENT-039 | Phase 3 | Sprint 7 | B2B deployment documentation and onboarding flow | As a B2B customer, I want clear onboarding so I can quickly deploy to my organization. | 1. Deployment guide covers: org signup, user invites, SSO setup, white-label config. 2. Onboarding checklist in admin dashboard. 3. Email templates for user invites and training materials. 4. Success criteria: 100% of invited users active within 2 weeks.
ENT-040 | Phase 3 | Sprint 8 | Vietnamese translation (all screens + AI responses) | As a Vietnamese-speaking parent, I want the entire app in Vietnamese. | 1. All user-facing text translated to Vietnamese. 2. AI prompts and responses optimized for Vietnamese language. 3. Professional translator review completed. 4. Verified with Vietnamese-speaking beta users.
ENT-041 | Phase 3 | Sprint 8 | Tagalog translation | As a Tagalog-speaking parent, I want the entire app in Tagalog. | 1. All user-facing text translated to Tagalog (Philippine variant). 2. AI prompts optimized for Tagalog context. 3. Professional translator review completed. 4. Tested with Tagalog-speaking users.
ENT-042 | Phase 3 | Sprint 8 | Mandarin translation | As a Mandarin-speaking parent, I want the entire app in Mandarin Chinese. | 1. All user-facing text translated to Mandarin (Simplified). 2. Character count estimated (typically 30% shorter than English). 3. Professional translator review completed. 4. Tested with Mandarin-speaking users.
ENT-043 | Phase 3 | Sprint 8 | RC-specific content for 21 Regional Centers | As a Regional Center, I want content specific to our center so families get relevant information. | 1. Content management system allows org-specific article creation. 2. 21 Regional Centers each have 5-10 custom articles. 3. Articles appear in context (e.g., "Services near you" shows RC contact info). 4. Content approval workflow (org admin → editorial review).
ENT-044 | Phase 3 | Sprint 8 | Scale KB from 25 to 100+ articles | As a content team, I want a comprehensive knowledge base so users find answers quickly. | 1. KB scaled from 25 to 100+ articles across 8 categories. 2. Article structure: title, body, related articles, FAQ. 3. Search indexes all articles and supports filters. 4. Content rated by users (helpful/not helpful) to guide improvements.
ENT-045 | Phase 3 | Sprint 8 | Content versioning with effective dates | As a content manager, I want to schedule content updates so changes go live at specific dates. | 1. Articles can have multiple versions with effective_from/effective_to dates. 2. Scheduler publishes versions automatically at effective_from date. 3. Version history accessible for audit. 4. Editor warns if publishing over active content.
ENT-046 | Phase 3 | Sprint 9 | WCAG AA accessibility audit + fixes | As a user with disabilities, I want the app to be fully accessible so I can use it independently. | 1. WCAG 2.1 AA audit completed by third-party auditor. 2. Issues categorized: critical (blocking), major (difficult), minor (inconvenient). 3. All critical and major issues fixed. 4. Accessible color contrasts (4.5:1), font sizes (14pt min), interactive element sizes (44px min).
ENT-047 | Phase 3 | Sprint 9 | VoiceOver + TalkBack testing and fixes | As a blind user, I want the app fully navigable with screen readers. | 1. All interactive elements have descriptive labels. 2. Tested with VoiceOver (iOS) and TalkBack (Android). 3. Navigation order logical and intuitive. 4. Images have alt text, form fields have labels.
ENT-048 | Phase 3 | Sprint 9 | Performance load testing (k6 — 1,000 concurrent) | As a system architect, I want to validate system capacity so we can confidently scale. | 1. Load test: 1,000 concurrent users, each making 10 API requests over 10 minutes. 2. P95 latency target: <2s, P99: <5s. 3. No errors during load test. 4. System automatically scales to handle 2x peak load (2,000 concurrent).
ENT-049 | Phase 3 | Sprint 9 | OWASP Mobile Top 10 security audit | As a security officer, I want independent validation so we meet industry security standards. | 1. Third-party security audit completed against OWASP Mobile Top 10. 2. All critical and high-risk findings remediated. 3. Penetration test of API endpoints completed. 4. Security report published (sanitized version) in security.txt.
ENT-050 | Phase 3 | Sprint 9 | SOC 2 readiness assessment | As a B2B customer, I want SOC 2 certification so I can confidently use us for regulated data. | 1. SOC 2 Type II audit scoped and scheduled. 2. Control framework: Access, Processing Integrity, Availability, Confidentiality, Privacy. 3. Evidence collected: policies, procedures, logs, test results. 4. Expected certification: 12 months of audit period completed by Q3.
ENT-051 | Phase 3 | Sprint 9 | Prompt A/B testing framework | As an AI team, I want to A/B test prompts so we can optimize response quality. | 1. Framework allows assigning users to prompt variants (A, B, C). 2. User feedback (thumbs up/down) collected separately by variant. 3. Analytics dashboard shows variant performance (accuracy, sentiment). 4. Statistical significance test recommends winning variant.
ENT-052 | Phase 4 | Sprint 10 | Cross-region database replication plan | As a company, I want geographic redundancy so we can survive regional outages. | 1. Replication strategy documented: primary (US-East), replicas (EU, Asia-Pacific). 2. RTO target: 15 minutes, RPO: <1 minute. 3. Failover procedures tested quarterly. 4. Read traffic routed to nearest replica for latency optimization.
ENT-053 | Phase 4 | Sprint 10 | Document intelligence (IEP redline / analysis) | As an IEP specialist, I want AI analysis of IEP documents so I can spot key goals and progress. | 1. User uploads IEP PDF. 2. AI extracts: annual goals, related services, accommodations, least restrictive environment. 3. Comparison with previous year highlights changes. 4. AI generates summary of progress toward each goal based on notes.
ENT-054 | Phase 4 | Sprint 10 | Insurance policy analysis (EOB parsing) | As a parent, I want AI analysis of insurance documents so I understand coverage and benefits. | 1. User uploads EOB or insurance policy. 2. AI extracts: covered services, copay amounts, deductible, out-of-pocket max. 3. Flags important information (e.g., pre-authorization required). 4. Cross-references with Waypoint KB articles on insurance topics.
ENT-055 | Phase 4 | Sprint 10 | AI provider abstraction layer (multi-model readiness) | As a platform architect, I want to support multiple AI providers so we're not locked into one. | 1. Provider interface defined (abstract class with query() method). 2. Implementations: Anthropic (primary), OpenAI (fallback), Llama (self-hosted option). 3. Switch providers in config without code changes. 4. Cost tracking per provider shows comparative economics.
ENT-056 | Phase 4 | Sprint 11 | Multi-state architecture (federal baseline + state overlays) | As a multi-state organization, I want to serve customers in different states with state-specific content. | 1. Content split: federal baseline articles + state overlay articles. 2. Query parameter or user profile determines state context. 3. Example: IEP content shows federal requirements + CA-specific requirements. 4. State selector in app settings and admin dashboard.
ENT-057 | Phase 4 | Sprint 11 | Scale KB to 200+ articles | As a content team, I want a comprehensive knowledge base covering all disability topics. | 1. KB scaled to 200+ articles across 15 categories. 2. Content calendar establishes publication schedule. 3. Community contributions reviewed and integrated. 4. Analytics show article usage (views, time spent, search queries landing on article).
ENT-058 | Phase 4 | Sprint 11 | Provider ratings / community layer | As a parent, I want ratings of service providers so I can find quality resources. | 1. Users can rate providers they've used (1-5 stars with comment). 2. Aggregated ratings displayed in provider listings. 3. Moderation system flags inappropriate reviews. 4. Anonymized rating data shared with providers for improvement.
ENT-059 | Phase 4 | Sprint 11 | Outcome tracking and ROI reporting | As a Family Resource Center, I want outcome metrics so I can demonstrate program impact. | 1. Org collects outcomes: health improvements, service access increases, family satisfaction. 2. Dashboard shows outcome trends over time. 3. ROI calculation: (cost saved + outcomes) / (implementation cost). 4. Report generation for funders and stakeholders.
ENT-060 | Phase 4 | Sprint 12 | Enterprise sales toolkit and pricing engine | As a sales team, I want a toolkit to sell enterprise plans efficiently. | 1. Pricing engine calculates quotes: per-user, per-organization, volume discounts. 2. Sales deck templates (PowerPoint), case studies, ROI calculator. 3. License key generation and tracking. 4. Integration with Salesforce for deal pipeline.

## Sprint Summary
Phase | Sprint | Sprint Name | Weeks | Issue Count | Total Pts | Total Hours | Issues | Key Deliverables | Dependencies | Risk Level
Phase 1 | Sprint 1 | Security Foundation | 1-2 | 5 | 23 | 47 | ENT-001,ENT-002,ENT-003,ENT-004,ENT-005 | RLS policies, API rate limiting, Vault setup, Audit logging, Service accounts | None | Low
Phase 1 | Sprint 2 | CI/CD & Testing Foundation | 3-4 | 5 | 24 | 46 | ENT-006,ENT-007,ENT-008,ENT-009,ENT-010 | GitHub Actions pipeline, Supabase CLI, Jest framework, Vitest setup, EAS Build config | None | Low
Phase 1 | Sprint 3 | Caching & Monitoring | 5-8 | 5 | 21 | 45 | ENT-011,ENT-012,ENT-013,ENT-014,ENT-015 | Redis caching, Sentry integration, PostHog analytics, Uptime monitoring, Account deletion | ENT-005 | Medium
Phase 2 | Sprint 4 | Compliance Infrastructure | 9-12 | 5 | 16 | 36 | ENT-016,ENT-017,ENT-018,ENT-019,ENT-020 | HIPAA BAA, DPA verification, Data retention automation, COPPA validation, Privacy assessment | ENT-007 | High
Phase 2 | Sprint 5 | AI Quality & Full Test Suite | 13-16 | 7 | 37 | 82 | ENT-021,ENT-022,ENT-023,ENT-024,ENT-025,ENT-026,ENT-027 | AI quality dashboard, Prompt versioning, AI test suite, Integration tests, E2E tests, Cost alerting, Fallback strategy | ENT-009, ENT-010, ENT-011, ENT-012 | High
Phase 2 | Sprint 6 | i18n & Core Features | 17-20 | 8 | 48 | 108 | ENT-028,ENT-029,ENT-030,ENT-031,ENT-032,ENT-033,ENT-034 | i18n framework, Spanish translation, Push notifications, Multi-child profiles, Document vault, Subscriptions, Staging env | ENT-007, ENT-028 | Medium
Phase 3 | Sprint 7 | Multi-Tenancy Foundation | 21-26 | 5 | 32 | 76 | ENT-035,ENT-036,ENT-037,ENT-038,ENT-039 | Org accounts, RBAC, Admin dashboard, White-labeling, B2B onboarding | ENT-001, ENT-035, ENT-036 | High
Phase 3 | Sprint 8 | Languages & KB Expansion | 27-32 | 6 | 36 | 118 | ENT-040,ENT-041,ENT-042,ENT-043,ENT-044,ENT-045 | Vietnamese, Tagalog, Mandarin translations, RC-specific content, KB scaling, Content versioning | ENT-028 | Medium
Phase 3 | Sprint 9 | Testing & Compliance | 33-36 | 6 | 33 | 90 | ENT-046,ENT-047,ENT-048,ENT-049,ENT-050,ENT-051 | WCAG AA audit, Accessibility fixes, Performance testing, OWASP audit, SOC 2 readiness, A/B testing | ENT-022 | High
Phase 4 | Sprint 10 | Advanced AI & Cross-Region | 37-40 | 4 | 23 | 62 | ENT-052,ENT-053,ENT-054,ENT-055 | Cross-region replication, Document intelligence, Insurance analysis, AI provider abstraction | ENT-022 | Medium
Phase 4 | Sprint 11 | Multi-State & Community | 41-44 | 4 | 26 | 82 | ENT-056,ENT-057,ENT-058,ENT-059 | Multi-state architecture, KB scaling to 200+, Provider ratings, Outcome tracking & ROI | ENT-044, ENT-037 | Medium
Phase 4 | Sprint 12 | Enterprise Sales & Growth | 45-48 | 1 | 5 | 12 | ENT-060 | Sales toolkit, Pricing engine, Salesforce integration | None | Low

## Phase Summary
Phase | Phase Name | Duration (Weeks) | Sprint Count | Total Issues | Total Story Points | Total Hours | Est. Cost Range | Key Outcomes | Critical Dependencies | Success Criteria
Phase 1 | Harden & Secure | 8 | 3 | 15 | 89 | 183 | $50K-$75K | Security foundation: RLS policies, API rate limiting, audit logging, CI/CD pipeline established, monitoring & alerting, account deletion compliance | None | All RLS policies deployed and tested; CI/CD pipeline passing all checks; monitoring alerts configured; no critical security findings
Phase 2 | Scale & Comply | 12 | 3 | 20 | 101 | 226 | $100K-$150K | Compliance & AI quality: HIPAA/DPA execution, data retention automation, AI quality monitoring, comprehensive test coverage, internationalization (Spanish), subscriptions, staging environment | Phase 1 security foundation; ENT-007, ENT-009, ENT-010, ENT-012, ENT-028 | Compliance audits passed; AI accuracy >95%; test coverage >80%; Spanish language fully supported; staging matches production schema
Phase 3 | Enterprise Features | 16 | 3 | 17 | 101 | 284 | $150K-$225K | Multi-tenancy & localization: Organization accounts, RBAC, admin dashboards, white-labeling, Vietnamese/Tagalog/Mandarin translations, 100+ KB articles, RC-specific content, accessibility (WCAG AA), performance testing, security audit, SOC 2 readiness | Phase 2 scaled infrastructure; ENT-028, ENT-022, ENT-035, ENT-036, ENT-037, ENT-046 | Multi-tenancy fully functional for 21 RCs; all translations verified by native speakers; WCAG AA audit passed; SOC 2 in audit; <2s P95 latency under load
Phase 4 | Scale & Optimize | 12 | 3 | 8 | 54 | 156 | $100K-$150K | Enterprise AI & advanced features: Cross-region replication, document intelligence, insurance analysis, AI provider abstraction, multi-state content, KB scaling to 200+, community layer (provider ratings), outcome tracking & ROI, enterprise sales toolkit | Phase 3 enterprise foundation; ENT-022, ENT-037, ENT-044 | Cross-region failover tested; Document intelligence accuracy >90%; 200+ KB articles published; Multi-state deployment live in 3+ states; ROI tracking producing meaningful metrics