## Task Tracker
WAYPOINT LITE — GOOGLE SHEETS MVP PROJECT PLAN
Build in: Claude Cowork ¦ Owner: Mike ¦ Stack: Google Sheets + Apps Script + Claude API ¦ Target: 10 working days
⚡ COWORK INSTRUCTIONS: Reference this sheet at the start of each session. Update Status and Cowork Session columns as you complete tasks. Add notes in the Session Notes column.
# | Task | Day | Pri | Status | Hours | Actual | Cowork Session | Files Created | Dependencies | Acceptance Criteria | Session Notes | Date Done
⚡ DAY 1: SHEET SETUP + APPS SCRIPT FOUNDATION
1 | Create Google Sheet with 6 tabs (KnowledgeBase, ChildProfiles, InteractionLog, Prompts, DraftLog, Config) | Day 1 | P0 | Not Started | 0.5 |  |  | Waypoint AI Engine.gsheet |  | All 6 tabs exist with correct column headers per Lite MVP doc §2
2 | Set up Apps Script project + store ANTHROPIC_API_KEY in Script Properties | Day 1 | P0 | Not Started | 0.5 |  |  | Code.gs |  | API key stored securely; never in source code
3 | Write Config.gs — CONFIG object + getSheet() + callClaude() helper | Day 1 | P0 | Not Started | 1.5 |  |  | Config.gs | Task 2 | callClaude() returns text from Anthropic API; test with simple prompt
4 | Write KnowledgeRetrieval.gs — keyword-based KB search | Day 1 | P0 | Not Started | 1.5 |  |  | KnowledgeRetrieval.gs | Task 3 | getRelevantKnowledge(question, category) returns top 5 matched chunks
5 | Test callClaude() with a simple question via Apps Script console | Day 1 | P0 | Not Started | 0.5 |  |  |  | Task 3 | Successful API response logged in console; no errors
⚡ DAY 2: CORE AI PIPELINE
6 | Write AIPipeline.gs — askWaypoint() main function (classify → retrieve → generate) | Day 2 | P0 | Not Started | 3 |  |  | AIPipeline.gs | Tasks 3, 4 | askWaypoint(question, profileId) returns structured JSON with empathy, answer, action_steps
7 | Write Profiles.gs — getChildProfile() from ChildProfiles tab | Day 2 | P0 | Not Started | 1 |  |  | Profiles.gs | Task 1 | Returns profile object with all fields; handles missing profileId gracefully
8 | Write Prompts.gs — getCategoryPrompt() with profile variable injection | Day 2 | P0 | Not Started | 1 |  |  | Prompts.gs | Task 1 | Returns active prompt for category; injects child_name, regional_center, school_district, diagnosis
9 | Write Logger.gs — logInteraction() appends to InteractionLog tab | Day 2 | P0 | Not Started | 0.5 |  |  | Logger.gs | Task 1 | Row appended with timestamp, profileId, question, category, urgency, response_json, empty feedback
10 | Test full pipeline via console: askWaypoint('My child was just diagnosed with autism', 'test-001') | Day 2 | P0 | Not Started | 1 |  |  |  | Tasks 6-9 | Returns valid JSON; correct category (regional-center or diagnosis); logged in InteractionLog
⚡ DAY 3: KNOWLEDGE BASE CONTENT — REGIONAL CENTER
11 | Write RC KB: Lanterman Act key sections + rights | Day 3 | P0 | Not Started | 1.5 |  |  | KnowledgeBase tab rows |  | 200-500 words; covers §4502, §4512, §4646, §4648; payer of last resort
12 | Write RC KB: Intake process + 120-day timeline | Day 3 | P0 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | Step-by-step intake; referral → assessment → eligibility → IPP; timeline requirements
13 | Write RC KB: IPP rights and process | Day 3 | P0 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | What IPP is; parent rights; how to prepare; how to dispute
14 | Write RC KB: Purchase of Service (POS) standards | Day 3 | P0 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | What POS covers; how to reference your RC’s standards; common services
15 | Write RC KB: Fair hearing procedures | Day 3 | P1 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | When to file; timeline; what to bring; how to prepare; mediation vs hearing
16 | Test: Ask 5 RC questions through pipeline; verify KB retrieval quality | Day 3 | P0 | Not Started | 1 |  |  |  | Tasks 6, 11-15 | All 5 questions retrieve relevant KB content; responses cite Lanterman Act correctly
⚡ DAY 4: KNOWLEDGE BASE CONTENT — IEP + SYSTEM PROMPTS
17 | Write IEP KB: IDEA procedural safeguards + FAPE | Day 4 | P0 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | Core IDEA rights; FAPE definition; parent participation; PWN requirements
18 | Write IEP KB: California Education Code + SB 483 | Day 4 | P0 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | CA-specific requirements; SB 483 provisions; how they exceed federal IDEA
19 | Write IEP KB: IEP meeting process + parent preparation | Day 4 | P0 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | Before/during/after meeting; what to bring; questions to ask; red flags
20 | Write IEP KB: Dispute resolution options | Day 4 | P1 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | Mediation, due process, compliance complaint, OCR; when to use each
21 | Write IEP KB: Independent Educational Evaluations (IEE) | Day 4 | P1 | Not Started | 0.5 |  |  | KnowledgeBase tab rows |  | Right to IEE at public expense; how to request; what to do if denied
22 | Write system prompts for RC + IEP in Prompts tab | Day 4 | P0 | Not Started | 2 |  |  | Prompts tab rows |  | Full prompts from Build Plan §7; {variables} for profile injection; active=TRUE
23 | Create test child profile in ChildProfiles tab (Teddy-based) | Day 4 | P0 | Not Started | 0.5 |  |  | ChildProfiles tab row |  | Realistic profile: name, age, diagnosis, RCEB, school district, current benefits
24 | Test: 10 questions across RC + IEP; verify classification + quality | Day 4 | P0 | Not Started | 1.5 |  |  |  | Tasks 6, 16-23 | Classification >85% accurate; responses include action_steps; rights cited correctly
⚡ DAY 5: WEB APP FRONTEND
25 | Write WebApp.gs — doGet() serves ChatUI.html | Day 5 | P0 | Not Started | 0.5 |  |  | WebApp.gs |  | doGet() returns HtmlService output; deploys without error
26 | Build ChatUI.html — chat input + profile selector | Day 5 | P0 | Not Started | 2 |  |  | ChatUI.html | Task 25 | Text input, profile dropdown, Ask button; calls google.script.run.askWaypoint()
27 | Build ChatUI.html — Action Card response rendering | Day 5 | P0 | Not Started | 2 |  |  | ChatUI.html | Task 26 | Renders: empathy banner, answer, numbered action_steps, rights_reminder, watch_out
28 | Deploy web app + test end-to-end from browser | Day 5 | P0 | Not Started | 1 |  |  |  | Tasks 25-27 | Deployed URL works; type question → see loading → see formatted response
29 | Add loading spinner + error handling to ChatUI | Day 5 | P1 | Not Started | 0.5 |  |  | ChatUI.html | Task 28 | Spinner during API call; error message if call fails; retry button
⚡ DAY 6: END-TO-END TESTING + PROMPT TUNING
30 | Test 20 questions across RC + IEP through web UI | Day 6 | P0 | Not Started | 2 |  |  |  | Task 28 | 20 questions tested; classification, retrieval, and response quality rated per question
31 | Review InteractionLog — identify misclassifications | Day 6 | P0 | Not Started | 1 |  |  |  | Task 30 | List of misclassified questions documented; patterns identified
32 | Tune classification prompt based on misclassifications | Day 6 | P1 | Not Started | 1.5 |  |  | Prompts tab update | Task 31 | Updated classifier re-tested on failed questions; accuracy improves
33 | Tune RC + IEP system prompts based on weak responses | Day 6 | P1 | Not Started | 1.5 |  |  | Prompts tab update | Task 30 | Weak responses identified and improved; re-tested
34 | Add KB content for any gaps identified during testing | Day 6 | P1 | Not Started | 1 |  |  | KnowledgeBase tab rows | Task 30 | New KB rows added for topics where retrieval returned no/poor results
⚡ DAY 7: DRAFT GENERATION (AGENT LAYER)
35 | Write Drafts.gs — generateDraft() function with 4 draft types | Day 7 | P1 | Not Started | 2.5 |  |  | Drafts.gs | Task 6 | generateDraft(type, profileId, question, response) returns formatted draft text
36 | Write draft prompt: appeal_letter (insurance denial appeal) | Day 7 | P1 | Not Started | 1 |  |  | Drafts.gs |  | Generates formal appeal with: date, policy ref, denial reason, med necessity argument, legal cite
37 | Write draft prompt: iep_email (email to school district) | Day 7 | P1 | Not Started | 1 |  |  | Drafts.gs |  | Professional email citing IDEA/CA Ed Code; specific requests with deadlines
38 | Write draft prompt: rc_reimbursement (RC reimbursement request) | Day 7 | P1 | Not Started | 1 |  |  | Drafts.gs |  | References service auth and POS standards; itemized expenses
39 | Add draft buttons + draft display to ChatUI.html | Day 7 | P1 | Not Started | 1.5 |  |  | ChatUI.html update | Tasks 35, 28 | When offer_to_draft present, button appears; clicking shows draft with copy button
40 | Test: Generate 3 drafts (appeal, IEP email, reimbursement) | Day 7 | P1 | Not Started | 1 |  |  |  | Tasks 35-39 | All 3 draft types generate; content is realistic and usable
⚡ DAY 8: EXPAND KNOWLEDGE BASE
41 | Write Benefits KB: SSI eligibility + IHSS hours + funding waterfall (5 rows) | Day 8 | P1 | Not Started | 2.5 |  |  | KnowledgeBase tab rows |  | SSI thresholds, IHSS parent-as-provider, insurance→Medi-Cal→CCS→RC waterfall
42 | Write Insurance KB: Appeal process + medical necessity + denials (3 rows) | Day 8 | P1 | Not Started | 1.5 |  |  | KnowledgeBase tab rows |  | Internal/external appeal, timelines, med necessity documentation, EOB basics
43 | Write system prompts for Benefits + Insurance in Prompts tab | Day 8 | P1 | Not Started | 1.5 |  |  | Prompts tab rows |  | Full prompts with profile injection; active=TRUE; covers key facts from Build Plan
44 | Test: 10 questions across Benefits + Insurance categories | Day 8 | P1 | Not Started | 1.5 |  |  |  | Tasks 41-43 | Classification correct; funding waterfall explained accurately; appeal steps actionable
⚡ DAY 9: REMAINING CATEGORIES + FEEDBACK
45 | Write Rights KB: Fair hearings, compliance complaints, OCR (3 rows) | Day 9 | P2 | Not Started | 1.5 |  |  | KnowledgeBase tab rows |  | When/how to file each; timelines; what to prepare
46 | Write Navigation KB: Provider finding, waitlists, coordination (3 rows) | Day 9 | P2 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | How to find therapists; managing waitlists; coordinating RC + school + insurance
47 | Write Transitions KB: Early Start→IEP, school→adult (2 rows) | Day 9 | P2 | Not Started | 1 |  |  | KnowledgeBase tab rows |  | Age 3 transition timeline; age 18/22 planning; key deadlines
48 | Write system prompts for Rights, Navigation, Transitions | Day 9 | P2 | Not Started | 1.5 |  |  | Prompts tab rows |  | All 7 category prompts now active in Prompts tab
49 | Add feedback buttons (thumbs up/down) to ChatUI + Logger update | Day 9 | P2 | Not Started | 1.5 |  |  | ChatUI.html + Logger.gs update | Task 28 | Buttons appear after response; click writes to feedback column in InteractionLog
50 | Add conversation history display (show previous Q&A in session) | Day 9 | P2 | Not Started | 1 |  |  | ChatUI.html update | Task 28 | Previous questions + responses visible in chat thread above input
⚡ DAY 10: FULL QA + DOCUMENTATION
51 | Full QA: 30 questions across all 7 categories | Day 10 | P0 | Not Started | 3 |  |  |  | All | 30 questions tested; results logged; classification accuracy >85%; response quality 4+/5
52 | Generate analytics from InteractionLog (category distribution, accuracy) | Day 10 | P1 | Not Started | 1.5 |  |  |  | Task 51 | Summary stats: questions per category, avg feedback score, misclassification rate
53 | Document learnings: what worked, what needs fixing for full MVP | Day 10 | P1 | Not Started | 1.5 |  |  | LEARNINGS.md or Sheet tab | Tasks 51-52 | Written summary of: prompt strengths/weaknesses, KB gaps, category accuracy, draft quality
54 | Create README with setup instructions for anyone else to test | Day 10 | P2 | Not Started | 1 |  |  | README tab in Sheet |  | Step-by-step: how to copy sheet, set API key, deploy web app, test
55 | Snapshot: Export InteractionLog for use as test suite in full MVP | Day 10 | P1 | Not Started | 0.5 |  |  | CSV export | Task 51 | CSV of all interactions; becomes regression test data for Supabase migration
TOTALS |  |  |  |  | 69 | 0

## Cowork Sessions
CLAUDE COWORK SESSION LOG
Start each Cowork session by telling Claude: "I'm working on Waypoint Lite. Reference the Task Tracker tab. I'm starting [Task #X]." End each session by updating this log.
Session # | Date | Duration | Tasks Worked | Tasks Completed | Files Created/Modified | Blockers / Issues | Key Decisions / Notes
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15

## Version Control
VERSION CONTROL LOG
One row per meaningful change. Never overwrite — always add a new version entry. Update this after each Cowork session.
Version | Date | Component | Change Type | Description | Files Changed | Cowork Session | Tested?
0.1.0 |  | Infrastructure | Setup | Google Sheet + 6 tabs + Apps Script project | Sheet, Code.gs | Session 1
0.1.1 |  | Backend | New | Config.gs + callClaude() + KnowledgeRetrieval.gs | Config.gs, KnowledgeRetrieval.gs | Session 1
0.2.0 |  | Backend | New | Full AI pipeline: AIPipeline.gs + Profiles + Prompts + Logger | 4 .gs files | Session 2
0.3.0 |  | Content | New | Regional Center knowledge base (5 docs) | KnowledgeBase tab | Session 3
0.3.1 |  | Content | New | IEP knowledge base (5 docs) + system prompts | KnowledgeBase + Prompts tabs | Session 4
0.4.0 |  | Frontend | New | ChatUI.html + WebApp.gs + web app deployment | ChatUI.html, WebApp.gs | Session 5
0.4.1 |  | AI Engine | Tune | Classification + system prompt tuning (post-testing) | Prompts tab | Session 6
0.5.0 |  | Backend | New | Drafts.gs + 3 draft prompts + draft UI | Drafts.gs, ChatUI.html | Session 7
0.6.0 |  | Content | Expand | Benefits + Insurance KB + system prompts | KnowledgeBase + Prompts tabs | Session 8
0.7.0 |  | Content | Expand | Rights + Navigation + Transitions KB + prompts | KnowledgeBase + Prompts tabs | Session 9
0.7.1 |  | Frontend | New | Feedback buttons + conversation history | ChatUI.html, Logger.gs | Session 9
1.0.0 |  | Release | MVP | Full QA complete — Waypoint Lite MVP | All files | Session 10

## Prompt Library
PROMPT LIBRARY — TRACK ALL PROMPT VERSIONS
This is your prompt index. The actual prompts live in the Prompts tab of the Waypoint AI Engine sheet. Update version here when you change a prompt.
Prompt ID | Category | Type | Version | Status | Last Changed | Change Summary
CLASSIFY-001 | Classification | System | v1.0 | Draft |  | 7-category classifier: RC, IEP, benefits, insurance, rights, navigation, transitions
SYS-RC-001 | Regional Center | System | v1.0 | Draft |  | Lanterman Act, intake, IPP, POS, fair hearing; {regional_center} injection
SYS-IEP-001 | IEP / School | System | v1.0 | Draft |  | IDEA, FAPE, PWN, SB 483, IEE, disputes; {school_district} injection
SYS-BEN-001 | Benefits | System | v1.0 | Draft |  | Funding waterfall, SSI, IHSS, Medi-Cal, ABLE; {benefits} injection
SYS-INS-001 | Insurance | System | v1.0 | Draft |  | Denials, appeals, medical necessity, EOB analysis
SYS-RGT-001 | Rights | System | v1.0 | Draft |  | Fair hearings, compliance complaints, OCR, timelines
SYS-NAV-001 | Navigation | System | v1.0 | Draft |  | Provider finding, waitlists, general guidance, coordination
SYS-TRN-001 | Transitions | System | v1.0 | Draft |  | Early Start→IEP (age 3), school→adult (18/22), aging out
DFT-APL-001 | Draft: Appeal | Draft | v1.0 | Draft |  | Insurance appeal letter with medical necessity + legal citations
DFT-IEP-001 | Draft: IEP Email | Draft | v1.0 | Draft |  | Email to school district requesting eval/meeting/disputing decision
DFT-RMB-001 | Draft: Reimburse | Draft | v1.0 | Draft |  | RC reimbursement request with receipts + service auth reference
DFT-PRP-001 | Draft: IEP Prep | Draft | v1.0 | Draft |  | Meeting agenda, questions, rights, suggested goals

## QA Test Log
QA TEST LOG — TRACK EVERY TEST QUESTION
Log every test question here. This becomes your regression test suite when you migrate to the full Supabase MVP.
# | Date | Question | Expected Category | Actual Category | Correct? | Response Quality (1-5) | KB Relevant? | Action Steps Usable? | Notes / Issues
1 |  | My 3-year-old was just diagnosed with autism. What do I do? | regional-center
2 |  | The school says my child doesn't qualify for an IEP. What are my options? | iep
3 |  | Our insurance denied OT after 20 sessions. How do I appeal? | insurance
4 |  | What is IHSS and how do I apply for my child? | benefits
5 |  | I think the Regional Center is underserving my child. Can I request a fair hearing? | rights
6 |  | How do I find a good ABA therapist in the East Bay? | navigation
7 |  | My child turns 3 next month. What happens to Early Start services? | transitions
8 |  | Can I get reimbursed by Regional Center for therapy I paid out of pocket? | regional-center
9 |  | The school wants to reduce my child's speech hours. What should I do before the IEP meeting? | iep
10 |  | Does my child qualify for SSI? We make about $80K/year. | benefits
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Cowork Cheat Sheet
CLAUDE COWORK CHEAT SHEET
Copy-paste these prompts to start each Cowork session. They give Claude the context it needs to pick up where you left off.
Session Kickoff Prompt | I'm building Waypoint Lite, a Google Sheets + Apps Script MVP for an AI-powered navigator that helps parents of children with disabilities. I have a detailed build plan doc and project tracker. Today I'm working on [TASK #X]: [paste task name]. Here's the acceptance criteria: [paste from col K]. Let's build it.
Continue Previous Work | I'm continuing work on Waypoint Lite. Last session I completed [TASKS]. Today I'm picking up with [TASK #X]. Here's where I left off: [describe state]. The acceptance criteria for today's task: [paste from col K].
Debug / Fix Session | I'm working on Waypoint Lite and hitting an issue with [COMPONENT]. Here's what's happening: [describe bug]. Here's the relevant code: [paste code]. The expected behavior is: [describe]. Help me fix it.
Knowledge Base Writing | I'm writing knowledge base content for Waypoint Lite's [CATEGORY] category. This will be pasted into the KnowledgeBase tab of my Google Sheet. Each entry needs: a clear title, 200-500 words of content, and the category tag. The content should include: key facts, step-by-step procedures, common pitfalls, scripts (what to say), and source citations. Write me the entry for: [TOPIC].
Prompt Tuning Session | I'm tuning the [CATEGORY] system prompt for Waypoint Lite. Here's the current prompt: [paste]. Here are 3 questions where the response was weak: [paste questions + responses]. Help me improve the prompt to handle these cases better while maintaining quality on the cases that already work.
Testing Session | I'm running QA on Waypoint Lite. I'm going to send you 10 questions as if I were a parent. For each, tell me: (1) what category you'd classify it as, (2) what the ideal action steps would be, (3) what KB content should have been retrieved. I'll compare your answers against what the actual system produced.
Draft Generation Testing | I'm testing draft generation in Waypoint Lite. Generate a [TYPE: appeal_letter / iep_email / rc_reimbursement] for this scenario: Child: [name], Age: [age], Diagnosis: [diagnosis], RC: [regional center], Situation: [describe]. The draft should be ready to send with minimal edits.
End of Session Summary | Summarize what we accomplished this session. List: (1) tasks completed with their numbers, (2) files created or modified, (3) any blockers or decisions made, (4) what I should work on next session. Format it so I can paste it into my Cowork Sessions log.
QUICK REFERENCE
Apps Script Files | Config.gs, KnowledgeRetrieval.gs, AIPipeline.gs, Profiles.gs, Prompts.gs, Logger.gs, Drafts.gs, WebApp.gs, ChatUI.html
Sheet Tabs | KnowledgeBase, ChildProfiles, InteractionLog, Prompts, DraftLog, Config
AI Model | claude-sonnet-4-5-20250929 (via Anthropic API)
7 Categories | regional-center, iep, benefits, insurance, rights, navigation, transitions
Response JSON Fields | empathy, answer, action_steps[], rights_reminder, watch_out, offer_to_draft
Draft Types | appeal_letter, iep_email, rc_reimbursement, iep_prep
Key Doc Reference | Waypoint-Lite-Sheets-MVP.docx (full build guide with all code)