## Sprint Plan
WAYPOINT — Sprint Plan & GitHub Issue Map
Solo dev workflow: 1-week sprints ¦ Branch per issue ¦ Cowork sessions ¦ Commit on green
Sprint | # | Issue Title | Priority | Label | Est Hrs | Status | Branch | Done When | Cowork Prompt | Commit Msg
Sprint 1 — Week 1: Project Foundation (Mar 2–6)
Goal: Set up everything from scratch. By Friday you have an Expo app with auth that writes to Supabase.
Sprint 1 | #1 | Project scaffold: Expo + TypeScript | P0 | setup | 2 |  | feat/scaffold | Expo app runs on iOS simulator | Create new Expo TypeScript project with folder structure: src/screens, src/components, src/lib, src/hooks, src/types | feat: initialize expo project with typescript
Sprint 1 | #2 | Supabase project setup + pgvector | P0 | setup | 1 |  | feat/supabase-init | Supabase dashboard accessible, pgvector enabled | Set up Supabase project, enable pgvector extension, configure env vars in app | feat: configure supabase project with pgvector
Sprint 1 | #3 | Auth: email + Apple + Google OAuth | P0 | auth | 3 |  | feat/auth | User can sign up/in via all 3 methods | Build auth flow with Supabase Auth — email/password, Apple Sign-In, Google OAuth. Create AuthContext provider | feat: implement auth with email, apple, google
Sprint 1 | #4 | Database schema v1 | P0 | backend | 4 |  | feat/schema-v1 | Migration runs, all tables created with proper relationships | Design and write SQL migration: families, children, diagnoses, services, documents, expenses, appointments, providers tables | feat: create database schema v1 migration
Sprint 1 | #5 | Row Level Security policies | P0 | backend | 2 |  | feat/rls | User A cannot read User B's data | Write RLS policies for all tables — family_id based isolation | feat: add row level security policies
Sprint 1 | #6 | Onboarding flow (6 screens) | P0 | frontend | 6 |  | feat/onboarding-ui | Complete flow from welcome → diagnosis → state → RC → insurance → done | Build 6-screen onboarding: Welcome, AddChild, Diagnosis (multi-select), StateAndRC, Insurance, Complete. Use React Navigation stack | feat: build onboarding flow ui
Sprint 1 | #7 | Onboarding → Supabase write | P0 | frontend | 4 |  | feat/onboarding-db | Family + child profile persists after onboarding | Connect onboarding form data to Supabase inserts — create family row, child row, link diagnosis codes | feat: persist onboarding data to supabase
Sprint 2 — Week 2: AI Navigator Core (Mar 9–13)
Goal: Get Claude talking to parents. By Friday the AI knows who the family is and can answer questions.
Sprint 2 | #8 | Tab navigation (5 tabs) | P0 | frontend | 4 |  | feat/tab-nav | All 5 tabs navigable with placeholder screens | Build bottom tab navigator: Home, Navigator, Tracker, Documents, Profile. Placeholder screens for each | feat: add 5-tab bottom navigation
Sprint 2 | #9 | Claude API edge function | P0 | ai | 3 |  | feat/claude-api | Edge function calls Claude and returns streamed response | Create Supabase edge function that proxies to Anthropic Claude API. Handle streaming. Store API key in Supabase secrets | feat: create claude api edge function
Sprint 2 | #10 | AI Navigator chat UI | P0 | ai | 6 |  | feat/chat-ui | Messages display with streaming, scroll, input works | Build chat interface: message list (user/assistant bubbles), text input with send button, streaming response display, auto-scroll | feat: build ai navigator chat interface
Sprint 2 | #11 | System prompt + family context injection | P0 | ai | 4 |  | feat/system-prompt | AI references child's diagnosis, age, RC, insurance in responses | Build system prompt that pulls family profile from Supabase and injects as context. Include role, tone, and disclaimer instructions | feat: inject family context into ai system prompt
Sprint 2 | #12 | Chat conversation persistence | P1 | ai | 3 |  | feat/chat-persist | Conversations survive app close/reopen | Store messages in Supabase conversations + messages tables. Load history on mount. New conversation button | feat: persist chat conversations to supabase
Sprint 2 | #13 | Knowledge base infrastructure | P0 | ai | 4 |  | feat/kb-infra | KB table + ingestion script working | Create kb_articles table (id, title, content, source, category, embedding vector). Write Node script to ingest markdown → table | feat: create knowledge base table and ingestion
Sprint 2 | #14 | Lanterman Act KB content | P0 | content | 5 |  | content/lanterman | 20+ articles ingested and retrievable | Research and write KB articles for key Lanterman Act provisions: §4512, §4646, §4648, §4659, §4731. Ingest via script | content: add lanterman act knowledge base
Sprint 3 — Week 3: RAG & Eligibility Engine (Mar 16–20)
Goal: Make the AI actually smart. RAG grounds answers in law. Eligibility checker tells families what they qualify for.
Sprint 3 | #15 | IDEA KB content | P0 | content | 5 |  | content/idea | 30+ articles covering Part B, Part C, Section 504 | Write and ingest IDEA articles: IEP process, IFSP, transition, procedural safeguards, Section 504 accommodations | content: add idea knowledge base articles
Sprint 3 | #16 | SSI/SSDI KB content | P0 | content | 3 |  | content/ssi | 15+ articles on eligibility, application, childhood disability evaluation | Write and ingest SSI/SSDI articles: childhood disability evaluation, income/asset limits, application steps, appeals | content: add ssi ssdi knowledge base
Sprint 3 | #17 | Embeddings pipeline (OpenAI → pgvector) | P0 | ai | 4 |  | feat/embeddings | All KB articles have embeddings stored in pgvector | Build script: for each KB article → call OpenAI text-embedding-3-small → store vector in pgvector column. Run on all existing articles | feat: build openai embeddings pipeline
Sprint 3 | #18 | RAG retrieval system | P0 | ai | 5 |  | feat/rag | User question → top 5 relevant KB articles → injected into Claude context | On chat message: embed question → cosine similarity search in pgvector → take top 5 → prepend to Claude system prompt as context | feat: implement rag retrieval for ai navigator
Sprint 3 | #19 | Source citations in AI responses | P1 | ai | 3 |  | feat/citations | AI responses show law/regulation references | Update system prompt to require citations. Parse citations from response. Display as tappable references below answer | feat: add source citations to ai responses
Sprint 3 | #20 | Benefits eligibility checker | P0 | feature | 6 |  | feat/eligibility | 8-question flow → personalized program list | Build guided flow: diagnosis, age, state, RC, insurance, income bracket, current services, goals → generate ranked list of eligible programs | feat: build benefits eligibility checker
Sprint 3 | #21 | Regional Center directory | P1 | content | 3 |  | content/rc-directory | All 21 CA RCs with contact info, counties, intake process | Create rc_centers table. Populate with all 21 CA Regional Centers: name, phone, email, website, counties served, intake steps | content: populate regional center directory
Sprint 3 | #22 | RC-specific guidance | P1 | ai | 5 |  | feat/rc-guidance | AI tailors answers to user's specific Regional Center | When family has RC set, include that RC's POS standards in context. Start with RCEB + GGRC as first two | feat: add rc-specific ai guidance
Sprint 4 — Week 4: Documents, Providers & Appointments (Mar 23–27)
Goal: Build the case management tools. By Friday the MVP is feature-complete for beta.
Sprint 4 | #23 | Medi-Cal / CCS / IHSS KB | P0 | content | 4 |  | content/medi-cal | 25+ articles on CA health/support programs | Write and ingest articles: Medi-Cal eligibility, CCS criteria, IHSS application, hours calculation, waiver programs | content: add medi-cal ccs ihss knowledge base
Sprint 4 | #24 | Financial planning KB (ABLE, taxes) | P1 | content | 3 |  | content/financial | 15+ articles on ABLE accounts, tax deductions, credits | Write articles: ABLE rules, medical expense deduction threshold, EITC for disabled dependents, Dependent Care Credit | content: add financial planning knowledge base
Sprint 4 | #25 | Document vault (upload + categorize) | P0 | feature | 6 |  | feat/doc-vault | Upload files, assign category, persist in Supabase Storage | Build upload screen: pick file/photo → select category (IEP, eval, insurance, medical, other) → upload to Supabase Storage → save metadata | feat: build document vault with upload
Sprint 4 | #26 | Document list view | P1 | feature | 3 |  | feat/doc-list | Sort by date, filter by category, tap to preview | Build document library: FlatList sorted by date, category filter chips, tap to open preview. Show file type icon | feat: add document list view with filters
Sprint 4 | #27 | Provider directory (personal contacts) | P1 | feature | 4 |  | feat/providers | Add/edit/delete provider contacts with role and specialty | Build provider contact book: add (name, role, phone, email, specialty, notes), list view grouped by role, edit/delete. Seed roles: therapist, RC coordinator, SPED, pediatrician, insurance | feat: build provider contact directory
Sprint 4 | #28 | Appointment tracker | P1 | feature | 5 |  | feat/appointments | Add appointments, calendar list view, basic reminders | Build: add appointment (date, time, provider, type, notes), upcoming list sorted by date, past appointments section | feat: build appointment tracker
Sprint 4 | #29 | Push notifications (Expo) | P0 | infra | 3 |  | feat/push-notifs | Appointment reminders fire 1 day + 1 hour before | Register for Expo push token on onboarding. Schedule local notifications for each appointment. Handle permission request | feat: implement push notifications
Sprint 4 | #30 | QA Sprint 1 | P0 | qa | 4 |  | fix/qa-sprint-1 | All Phase 1 features stable end-to-end | Test full flow: signup → onboard → chat → upload doc → add appointment → verify push notification. Fix all blockers | fix: resolve qa sprint 1 issues
Sprint 5 — Week 5: Beta Launch (Mar 30–Apr 3)
Goal: Get the app into real parents' hands. TestFlight to 10 families. Start learning what works.
Sprint 5 | #31 | TestFlight build + distribution | P0 | infra | 4 |  | feat/testflight | Build available for external testers | Create App Store Connect app entry, configure code signing, create TestFlight build, add first 10 external testers | chore: configure testflight distribution
Sprint 5 | #32 | In-app feedback system | P1 | feature | 2 |  | feat/feedback | Bug reports write to Supabase + email notification | Add 'Report Issue' button in profile tab → text input + screenshot option → write to feedback table → trigger email to mike@ | feat: add in-app feedback system
Sprint 5 | #33 | Mixpanel analytics | P0 | infra | 3 |  | feat/analytics | Key events tracked: onboarding_complete, ai_question, doc_upload, appointment_add, subscription_start | Install Mixpanel RN SDK. Track core events with properties. Set up user identification on auth. Create dashboard | feat: integrate mixpanel analytics
Sprint 5 | #34 | AI quality review (first 50 questions) | P0 | ai | 4 |  | fix/ai-quality-1 | 10+ improvement areas documented, top 5 fixed | Review all user questions in Supabase. Categorize: accurate, partially accurate, wrong, hallucinated. Fix system prompt and KB gaps | fix: improve ai quality from beta feedback
Sprint 5 | #35 | Beta fixes sprint 1 | P0 | bug | 5 |  | fix/beta-sprint-1 | Top 5 user-reported issues resolved | Triage all feedback submissions. Fix top 5 by severity. Deploy updated TestFlight build | fix: resolve top beta user issues
Sprint 6 — Week 6: IEP Prep & Appeal Letters (Apr 6–10)
Goal: Ship the two highest-value features: meeting prep and appeal generation. Expand beta to 25.
Sprint 6 | #36 | IEP/IPP preparation assistant | P0 | feature | 6 |  | feat/iep-prep | Select meeting type → get agenda + preparation checklist + talking points | Build flow: select meeting type (IEP annual, IEP triennial, IPP, 504) → AI generates parent agenda, prep checklist, suggested questions, rights reminder | feat: build iep ipp preparation assistant
Sprint 6 | #37 | Deadline engine v1 | P0 | feature | 3 |  | feat/deadlines | Auto-calculated deadlines from document dates | When user uploads IEP with date, calculate: annual review (365 days), triennial (3 years). Track insurance appeal windows (60/180 days). Show in notification list | feat: implement deadline calculation engine
Sprint 6 | #38 | Funding waterfall visualization | P1 | feature | 5 |  | feat/funding-waterfall | Visual funding order per service type | Build interactive display: for each service type (OT, ABA, speech, PT, equipment), show which funder pays first → last. Insurance → Medi-Cal → CCS → RC. Color-coded steps | feat: add funding waterfall visualization
Sprint 6 | #39 | Insurance denial patterns KB (top 5 CA insurers) | P0 | content | 5 |  | content/insurance | Denial patterns + appeal strategies for Kaiser, Blue Shield, Anthem, United, Aetna | Research and write KB articles: common OT/ABA/speech denial reasons per insurer, successful appeal language, medical necessity templates, external review process | content: add insurance denial patterns kb
Sprint 6 | #40 | Appeal letter generator | P0 | feature | 6 |  | feat/appeal-gen | AI generates customizable appeal letter with legal citations | Build flow: select service denied + insurer + denial reason → AI generates appeal letter citing relevant law (Parity Act, Lanterman, IDEA) → preview → export as PDF | feat: build insurance appeal letter generator
Sprint 7 — Week 7: Financial Tracking Module (Apr 13–17)
Goal: Build the money tools. Track every dollar. Surface what families are missing.
Sprint 7 | #41 | Expense tracker v1 | P0 | feature | 5 |  | feat/expenses | Add expense with amount, date, provider, category, funding source | Build: add expense form (amount, date, provider select, category select, funding source: insurance/OOP/RC/school/Medi-Cal, receipt photo optional), list view | feat: build expense tracker
Sprint 7 | #42 | Expense categories | P1 | feature | 2 |  | feat/expense-cats | Predefined categories + custom option | Seed categories: therapy, evaluation, medical equipment, adaptive tech, transportation, co-pay, medication, respite, other. Allow custom add | feat: add expense category management
Sprint 7 | #43 | Insurance claim tracker | P0 | feature | 5 |  | feat/claims | Log claims with status tracking (submitted/approved/denied/appealed) | Build: add claim (service, date, amount, insurer, status), status update flow, claims list with filter by status, running totals per status | feat: build insurance claim tracker
Sprint 7 | #44 | Expense summary dashboard | P1 | feature | 5 |  | feat/expense-dashboard | Totals by category, month, funding source, OOP running total | Build dashboard tab in Tracker: total by category (bar chart), monthly trend (line), by funding source (pie), YTD out-of-pocket total | feat: add expense summary dashboard
Sprint 7 | #45 | Profile settings | P1 | feature | 4 |  | feat/profile-settings | Edit child info, insurance, notifications, add/remove children | Build profile screen: edit family info, edit child details, update insurance, notification preferences toggle, add second child option | feat: build profile settings screen
Sprint 7 | #46 | QA Sprint 2 | P0 | qa | 4 |  | fix/qa-sprint-2 | All Sprint 5-7 features stable | Full regression: IEP prep, appeal gen, expenses, claims, dashboard, profile settings. Fix all P0 bugs | fix: resolve qa sprint 2 issues
Sprint 8 — Week 8: Monetization & App Store Submission (Apr 20–24)
Goal: Wire up payments. Submit to Apple. This is the gate to going public.
Sprint 8 | #47 | RevenueCat subscription setup | P0 | infra | 4 |  | feat/revenuecat | Plus ($9.99) and Pro ($19.99) tiers configured in RevenueCat + App Store Connect | Create RevenueCat project, configure products in App Store Connect, install RevenueCat RN SDK, test sandbox purchases | feat: configure revenuecat subscriptions
Sprint 8 | #48 | Paywall UI | P0 | frontend | 4 |  | feat/paywall | Feature comparison table + subscription selection + purchase flow | Build paywall screen: feature matrix (Free vs Plus vs Pro), select tier, purchase button → RevenueCat purchase flow → success screen | feat: build paywall with tier comparison
Sprint 8 | #49 | Feature entitlements (Free/Plus/Pro) | P0 | frontend | 4 |  | feat/entitlements | Pro features gated: appeal gen, multi-child, priority AI | Create EntitlementContext: check RevenueCat subscription status. Gate components: appeal letter behind Pro, expense dashboard behind Plus, show upgrade prompts | feat: implement feature entitlements gating
Sprint 8 | #50 | Stripe B2B billing | P1 | infra | 3 |  | feat/stripe-b2b | B2B invoicing and customer portal working | Set up Stripe account, create B2B product ($99-299/mo tiers), build simple admin page to create provider subscriptions | feat: add stripe b2b billing
Sprint 8 | #51 | App Store assets + submission prep | P0 | infra | 5 |  | chore/app-store-prep | Screenshots (6.7" + 6.5"), app description, keywords, privacy labels ready | Capture 6 screenshots per device size, write App Store description + keywords, fill out privacy nutrition labels, set up app categories | chore: prepare app store submission assets
Sprint 8 | #52 | App Store submission | P0 | infra | 2 |  | chore/app-store-submit | Build submitted to Apple review | Create release build, upload via Xcode, submit for review. Expect 3-5 day review window | chore: submit app to app store review
Sprint 9 — Week 9: Public Launch (Apr 27–May 1)
Goal: Go live. Fix fast. Ship tax optimization. Start the feedback flywheel.
Sprint 9 | #53 | Tax optimization report | P1 | feature | 5 |  | feat/tax-report | YTD deductible expenses + 7.5% AGI threshold tracker + ABLE tracker | Build report generation: pull all expenses marked tax-deductible, group by IRS category, calculate vs 7.5% AGI threshold, show ABLE contributions. Export as PDF | feat: build tax optimization report
Sprint 9 | #54 | Launch hotfixes | P0 | bug | 5 |  | fix/launch-hotfixes | All critical launch bugs resolved within 24 hours | Monitor App Store reviews + feedback system + crash reports. Fix and ship same-day TestFlight → expedited review if needed | fix: resolve critical launch issues
Sprint 9 | #55 | AI feedback loop (upvote/flag) | P1 | ai | 4 |  | feat/ai-feedback | Users can rate AI answer quality with thumbs up/down + optional comment | Add thumbs up/down below each AI response. On thumbs down, prompt for reason (wrong info, not specific enough, didn't understand question). Log to ai_feedback table | feat: add ai response feedback system
Sprint 10 — Week 10: B2B Directory & RC Depth (May 4–8)
Goal: Second revenue stream goes live. Complete California knowledge base.
Sprint 10 | #56 | B2B provider directory (in-app) | P0 | feature | 6 |  | feat/b2b-directory | Featured listings with practice info, specialties, insurance accepted | Build public provider directory: search by specialty/location, featured listings (paid) at top, practice details screen with contact + insurance + reviews placeholder | feat: build b2b provider directory
Sprint 10 | #57 | Multi-child support (Pro) | P1 | feature | 5 |  | feat/multi-child | Switch between child profiles, separate service records | Add child picker to home screen. Scope all data queries (appointments, documents, expenses) to selected child. Pro entitlement gate | feat: add multi-child profile support
Sprint 10 | #58 | Full RC KB (all 21 POS standards) | P0 | content | 6 |  | content/full-rc | Complete CA Regional Center coverage | Research and ingest remaining RC POS standards. Priority: NLACRC, SCLARC, FDLRC, SARC, VMRC + remaining 14. Structure: services available, hour limits, eligibility specifics | content: complete all 21 rc pos standards
Sprint 10 | #59 | RC reimbursement request helper | P1 | feature | 4 |  | feat/rc-reimburse | Generate letter requesting Waypoint be added to IPP/SDP | Build flow: select RC → AI generates IPP amendment request letter citing POS code 371/331 → preview → export PDF → instructions for submission | feat: build rc reimbursement request helper
Sprint 10 | #60 | Performance optimization sprint | P1 | infra | 4 |  | fix/performance | App loads in <2s, chat responds in <3s, images compressed | Profile app with React DevTools. Optimize: lazy load tabs, paginate chat history, compress document thumbnails, cache KB embeddings | fix: optimize app performance
Sprint 11 — Week 11: The Quarterback Engine (May 11–15)
Goal: THE differentiator. Waypoint stops being passive and starts driving the journey forward.
Sprint 11 | #61 | School district context for IEP | P1 | ai | 5 |  | feat/district-context | AI tailors IEP advice based on user's school district | When user sets school district, include district-specific context in IEP-related AI responses. Start with 5 largest East Bay districts: Oakland USD, WCCUSD, SRVUSD, MDUSD, Fremont USD | feat: add school district context to iep ai
Sprint 11 | #62 | Notification center | P0 | feature | 4 |  | feat/notif-center | Centralized view of all upcoming deadlines, appointments, and action items | Build notification center screen: grouped by urgency (overdue, this week, upcoming). Pull from deadlines, appointments, and Next Steps engine. Badge count on tab | feat: build centralized notification center
Sprint 11 | #63 | Next Steps engine (THE QUARTERBACK) | P0 | feature | 6 |  | feat/next-steps | Proactive recommendations based on family profile + completed actions | Build recommendation engine: analyze family profile (diagnosis, age, services, documents) → identify gaps → generate 'Your next waypoint' cards. Examples: 'Apply for IHSS', 'Your IEP review is in 30 days — start preparing', 'You may qualify for SSI', 'Upload your latest evaluation to track progress' | feat: build next steps quarterback engine
Sprint 11 | #64 | Weekly email digest | P1 | feature | 4 |  | feat/digest | SendGrid weekly summary: deadlines, insights, expense totals | Create SendGrid template. Build Supabase cron job (pg_cron) that runs weekly: pull upcoming deadlines, new AI insights, expense totals → send personalized email | feat: add weekly email digest via sendgrid
Sprint 11 | #65 | Share AI answers / checklists | P1 | feature | 3 |  | feat/share | Share via text/email from within app | Add share button to AI responses and checklists. Use RN Share API to open native share sheet with formatted text. Include 'Generated by Waypoint' footer | feat: add share functionality for ai content
Sprint 11 | #66 | QA Sprint 3 | P0 | qa | 4 |  | fix/qa-sprint-3 | Full regression test passes | Test everything: all 4 modules, subscriptions, B2B directory, Next Steps engine, notifications, sharing, email digest. Fix all P0s | fix: resolve qa sprint 3 issues
Sprint 12 — Week 12: Growth Systems & Multi-State Prep (May 18–22)
Goal: Build virality. Prepare the architecture for national expansion. Retro and plan Phase 4.
Sprint 12 | #67 | Onboarding v2 (streamlined) | P1 | frontend | 4 |  | feat/onboarding-v2 | Quick setup path for users who want to skip details initially | Add 'Quick Start' option that only asks: child name, primary diagnosis, state. Fill rest later from profile settings. Reduce time-to-first-AI-question | feat: streamline onboarding flow
Sprint 12 | #68 | Smart App Store rating prompt | P1 | frontend | 2 |  | feat/rating-prompt | Prompt appears after 5th AI question answered | Track ai_question_count in user profile. After 5th answer, show native StoreReview prompt. Don't show again if dismissed or submitted | feat: add smart rating prompt
Sprint 12 | #69 | Referral system | P0 | feature | 4 |  | feat/referrals | Invite link → both parties get 1 month free Plus | Build: generate unique referral link per user, track installs + signups via link, on referee signup → apply 1 month Plus to both accounts via RevenueCat promotional entitlement | feat: build referral reward system
Sprint 12 | #70 | Multi-state architecture | P0 | backend | 5 |  | feat/multi-state | State abstraction layer for KB and eligibility | Refactor KB to add state_code column. Refactor eligibility checker to accept state parameter. Create state_programs table mapping programs to states. Ensure CA data tagged correctly. Test with empty NY state | feat: add multi-state architecture layer
Sprint 12 | #71 | New York research + KB planning | P1 | content | 4 |  | content/ny-research | NY disability programs documented, KB structure planned | Research: OPWDD, CPSE, CSE, NY Medicaid waivers, CDPAP. Document in markdown. Plan KB article structure. Don't ingest yet — just research | content: research new york disability programs

## Git Workflow
Git Workflow — Solo Dev with Cowork
Branch Strategy
main — production code. Only merge when a sprint is complete and tested.
dev — working branch. Merge feature branches here throughout the sprint.
feat/*, content/*, fix/*, chore/* — one branch per GitHub issue (see Sprint Plan for names).
Flow: main ← dev ← feat/branch-name
At the end of each sprint: dev → main (squash merge with sprint summary).
Daily Workflow in Cowork
1. Open Cowork session. Name it: 'Sprint X — Issue #NN: [title]'
2. Start your Cowork prompt with the text from the 'Cowork Prompt' column in the Sprint Plan.
3. Code until the 'Done When' acceptance criteria is met.
4. Test on simulator (or device via Expo Go).
5. When it works:
git add -A
git commit -m '[commit msg from Sprint Plan]'
git push origin [branch-name]
6. Open GitHub → create PR from [branch] → dev. Self-review the diff. Merge.
7. Move to next issue.
Commit Message Convention
feat: — new feature (feat: build ai navigator chat interface)
fix: — bug fix (fix: resolve qa sprint 1 issues)
content: — knowledge base content (content: add lanterman act knowledge base)
chore: — infra/setup/config (chore: configure testflight distribution)
refactor: — code restructure without feature change
docs: — documentation only
Keep messages lowercase, imperative mood, under 72 characters.
Every commit message is pre-written in the Sprint Plan — just copy it.
Sprint Cadence
Monday AM: Review sprint backlog. Pick highest-priority issue. Create branch.
Mon–Thu: Work through issues in priority order (P0 first, then P1).
Friday: QA pass. Fix bugs. Merge dev → main if sprint is stable.
If you finish early: pull next sprint's P0 issues forward.
If you're behind: defer P1 issues to next sprint. Ship P0s.
End-of-sprint ritual:
1. git checkout dev && git merge main (sync)
2. Test the full app end-to-end
3. git checkout main && git merge --squash dev
4. git commit -m 'Sprint X complete: [summary]'
5. git push origin main
6. Tag: git tag -a vX.0 -m 'Sprint X release'
7. Update GitHub milestone: close Sprint X, review Sprint X+1
GitHub Setup (Do Once)
1. Create repo: waypoint-app/waypoint (private)
2. Create labels: setup, auth, frontend, backend, ai, content, feature, infra, bug, qa
3. Create milestones: Phase 1 (Sprints 1-4), Phase 2 (5-8), Phase 3 (9-12)
4. Create all 71 issues from the Sprint Plan (or batch-create with GitHub CLI):
gh issue create --title '[title]' --label '[label]' --milestone '[Phase N]'
5. Optionally create GitHub Project board with columns: Backlog, In Progress, Done
Batch create script (run from terminal):
# Copy the 'GitHub Issues' sheet from 12-Week Plan into issues.csv
# Then: while IFS=, read -r num title label milestone week priority criteria; do
# gh issue create -t "$title" -l "$label" -m "$milestone" -b "$criteria"
# done < issues.csv
Cowork Tips
— Name your Cowork session after the current issue for context continuity.
— Paste the 'Cowork Prompt' from the Sprint Plan as your opening message.
— Include the acceptance criteria so Cowork knows when the task is done.
— If the session gets long, start a new one with: 'Continuing Issue #NN. Here's where we left off: [summary]'
— Cowork doesn't persist files across sessions — always commit before ending.
— For content issues (KB articles), write markdown files locally, then use the ingestion script.
— For debugging: paste the error message into Cowork with 'I'm getting this error in [file]. Here's the relevant code: [paste]'
Version Milestones
v0.1.0 — Sprint 4 complete: MVP feature-complete (AI + docs + appointments)
v0.2.0 — Sprint 5 complete: TestFlight beta live
v0.3.0 — Sprint 6 complete: IEP prep + appeal letters
v0.4.0 — Sprint 7 complete: expense + claims tracking
v0.5.0 — Sprint 8 complete: subscriptions + App Store submitted
v1.0.0 — Sprint 9: PUBLIC LAUNCH on App Store
v1.1.0 — Sprint 10: B2B directory + multi-child
v1.2.0 — Sprint 11: Quarterback engine (Next Steps)
v1.3.0 — Sprint 12: Referrals + multi-state architecture

## Sprint Summary
Sprint Summary Dashboard
Sprint | Name | Dates | Issues | P0s | P1s | Total Hrs | Version | Key Ship
Sprint 1 | Project Foundation | Mar 2–6 | 7 | 6 | 1 | 22 | — | Expo + Auth + Onboarding → Supabase
Sprint 2 | AI Navigator Core | Mar 9–13 | 7 | 5 | 2 | 29 | — | Claude chat with family context
Sprint 3 | RAG & Eligibility | Mar 16–20 | 8 | 5 | 3 | 34 | — | RAG-powered AI + eligibility checker
Sprint 4 | Docs, Providers & Appts | Mar 23–27 | 8 | 4 | 4 | 32 | v0.1.0 | MVP feature-complete
Sprint 5 | Beta Launch | Mar 30–Apr 3 | 5 | 3 | 2 | 18 | v0.2.0 | TestFlight to 10 families
Sprint 6 | IEP Prep & Appeals | Apr 6–10 | 5 | 3 | 2 | 25 | v0.3.0 | IEP prep + appeal letter gen
Sprint 7 | Financial Tracking | Apr 13–17 | 6 | 3 | 3 | 25 | v0.4.0 | Expenses + claims dashboard
Sprint 8 | Monetization & App Store | Apr 20–24 | 6 | 4 | 2 | 22 | v0.5.0 | Subscriptions + App Store submit
Sprint 9 | Public Launch | Apr 27–May 1 | 3 | 1 | 2 | 14 | v1.0.0 | PUBLIC LAUNCH
Sprint 10 | B2B & RC Depth | May 4–8 | 5 | 2 | 3 | 25 | v1.1.0 | B2B directory + full RC KB
Sprint 11 | The Quarterback | May 11–15 | 6 | 3 | 3 | 26 | v1.2.0 | Next Steps engine
Sprint 12 | Growth & Multi-State | May 18–22 | 5 | 2 | 3 | 19 | v1.3.0 | Referrals + multi-state arch
TOTAL |  |  | 71 | 41 | 30 | 291