## All Tasks
ID | Source | Sprint | Task | Description | Priority | Effort | Owner | Files to Modify | Status | Persona(s) | Notes
G1 | GAS App | Sprint 1 | Add Spanish localization (i18n framework) | Install i18n library. Extract all user-facing strings. Create es-MX translations. Add language toggle. | HIGH | Medium | Product + i18n | Index.html | Not Started | P2 (Maria)
G2 | GAS App | Sprint 1 | Add POS data request action card | Create 'Request Your POS Data from RC' action card with pre-drafted email and DRC complaint link. | HIGH | Low | Content + Equity | Index.html | Not Started | P2 (Maria)
G3 | GAS App | Sprint 1 | Add softer AI Navigator entry prompts | Add beginner prompts: 'What should I do first?', 'How do I find my RC?', 'What is an IFSP?' | MEDIUM | Low | Content + AI | Index.html | Not Started | P1 (Sarah)
G4 | GAS App | Sprint 1 | Reduce email field prominence in onboarding | Move email after step 1 or reduce visual weight. Already labeled optional — make it feel optional. | MEDIUM | Low | Product + Growth | Index.html | Not Started | P1, P2
G5 | GAS App | Sprint 2 | Add 'YOU ARE HERE' badge to journey maps | Surface getJourneyPhaseForAge() visually. Highlight age-matched phase. | MEDIUM | Low | Product + Frontend | Index.html | Not Started | P1, P3
G6 | GAS App | Sprint 2 | Expand ZIP-to-RC lookup to 5-digit | Add full 5-digit mapping or county fallback. Add 'I don't know my zip' dropdown. | MEDIUM | Low | Engineering + Data | Index.html | Not Started | P2 (Maria)
G7 | GAS App | Sprint 2 | Add Claude API error handling | Graceful fallback UI if Claude API fails. Show cached/static guidance. | MEDIUM | Medium | Engineering | Code.gs + Index.html | Not Started | All
G8 | GAS App | Sprint 2 | Clarify privacy claim | Update 'stays on your device' claim or add local-only mode. Data goes to Google Sheets. | MEDIUM | Medium | Product + Legal | Index.html + Code.gs | Not Started | P3 (David)
G9 | GAS App | Sprint 3 | Add ARIA labels and keyboard navigation | ARIA roles on all interactives. Full keyboard nav. Semantic HTML. Screen reader testing. | MEDIUM | High | Frontend + QA | Index.html | Not Started | P2, P3
G10 | GAS App | Sprint 3 | Explain 'Conditional' RC for ADHD | Clarify ADHD+LD does NOT qualify for RC. Explain what co-occurring diagnosis means. | MEDIUM | Low | Content + Product | Index.html | Not Started | P3 (David)
L1 | Landing Page | Sprint 4 | Add SLD/LD to PROGRAMS data | Add 'Specific Learning Disability' with IEP, 504, insurance programs. Port from GAS App. | HIGH | Low | Content + Product | Landing-Page.jsx | Not Started | P2 (Maria)
L2 | Landing Page | Sprint 4 | Add SLD/LD journey map to JOURNEYS | Port SLD journey map from GAS App (2 phases). Match existing format. | HIGH | Low | Content + Product | Landing-Page.jsx | Not Started | P2 (Maria)
L3 | Landing Page | Sprint 4 | Add multi-select to eligibility tool | Allow multi-diagnosis selection. Show merged program list. Match GAS App capability. | HIGH | High | Engineering + Product | Landing-Page.jsx | Not Started | P3 (Jenny/David)
L4 | Landing Page | Sprint 4 | Remove/restructure email gate | Show all programs. Move email to waitlist or make optional after full reveal. | HIGH | Low | Growth + Product | Landing-Page.jsx | Not Started | All
L5 | Landing Page | Sprint 5 | Add responsive breakpoints | Media queries: 375px, 768px, 1024px. Stack grid, hamburger nav, vertical eligibility. | HIGH | Medium | Frontend | Landing-Page.jsx | Not Started | P2 (Maria)
L6 | Landing Page | Sprint 5 | Add Spanish localization | i18n for all user-facing strings. Language toggle in nav. Share translations with G1. | HIGH | Medium | Product + i18n | Landing-Page.jsx | Not Started | P2 (Maria)
L7 | Landing Page | Sprint 5 | Speed up typewriter animation | Reduce 35ms→20ms/char or instant on mobile. Detect viewport width. | LOW | Low | Frontend | Landing-Page.jsx | Not Started | P1 (Sarah)
L8 | Landing Page | Sprint 6 | Add diverse family imagery | Photos/illustrations of Latino, Asian, Black families. Testimonials. Cultural framing. | MEDIUM | Medium | Design + Content | Landing-Page.jsx | Not Started | P2, P3
L9 | Landing Page | Sprint 6 | Add age-personalized journey phases | Prompt for child's age. Highlight current phase. Session-only (no login needed). | MEDIUM | Low | Product + Frontend | Landing-Page.jsx | Not Started | P1, P3
L10 | Landing Page | Sprint 6 | Add ARIA labels and keyboard nav | ARIA roles, alt text, keyboard nav, skip-to-content link. Test with screen reader. | MEDIUM | High | Frontend + QA | Landing-Page.jsx | Not Started | P2, P3
L11 | Landing Page | Sprint 6 | Explain 'Conditional' RC for ADHD | Tooltip/inline note: ADHD alone doesn't qualify for RC. Explain Lanterman conditions. | MEDIUM | Low | Content + Product | Landing-Page.jsx | Not Started | P3 (David)

## GAS App Tasks
ID | Source | Sprint | Task | Description | Priority | Effort | Owner | Files to Modify | Status | Persona(s) | Notes
G1 | GAS App | Sprint 1 | Add Spanish localization (i18n framework) | Install i18n library. Extract all user-facing strings. Create es-MX translations. Add language toggle. | HIGH | Medium | Product + i18n | Index.html | Not Started | P2 (Maria)
G2 | GAS App | Sprint 1 | Add POS data request action card | Create 'Request Your POS Data from RC' action card with pre-drafted email and DRC complaint link. | HIGH | Low | Content + Equity | Index.html | Not Started | P2 (Maria)
G3 | GAS App | Sprint 1 | Add softer AI Navigator entry prompts | Add beginner prompts: 'What should I do first?', 'How do I find my RC?', 'What is an IFSP?' | MEDIUM | Low | Content + AI | Index.html | Not Started | P1 (Sarah)
G4 | GAS App | Sprint 1 | Reduce email field prominence in onboarding | Move email after step 1 or reduce visual weight. Already labeled optional — make it feel optional. | MEDIUM | Low | Product + Growth | Index.html | Not Started | P1, P2
G5 | GAS App | Sprint 2 | Add 'YOU ARE HERE' badge to journey maps | Surface getJourneyPhaseForAge() visually. Highlight age-matched phase. | MEDIUM | Low | Product + Frontend | Index.html | Not Started | P1, P3
G6 | GAS App | Sprint 2 | Expand ZIP-to-RC lookup to 5-digit | Add full 5-digit mapping or county fallback. Add 'I don't know my zip' dropdown. | MEDIUM | Low | Engineering + Data | Index.html | Not Started | P2 (Maria)
G7 | GAS App | Sprint 2 | Add Claude API error handling | Graceful fallback UI if Claude API fails. Show cached/static guidance. | MEDIUM | Medium | Engineering | Code.gs + Index.html | Not Started | All
G8 | GAS App | Sprint 2 | Clarify privacy claim | Update 'stays on your device' claim or add local-only mode. Data goes to Google Sheets. | MEDIUM | Medium | Product + Legal | Index.html + Code.gs | Not Started | P3 (David)
G9 | GAS App | Sprint 3 | Add ARIA labels and keyboard navigation | ARIA roles on all interactives. Full keyboard nav. Semantic HTML. Screen reader testing. | MEDIUM | High | Frontend + QA | Index.html | Not Started | P2, P3
G10 | GAS App | Sprint 3 | Explain 'Conditional' RC for ADHD | Clarify ADHD+LD does NOT qualify for RC. Explain what co-occurring diagnosis means. | MEDIUM | Low | Content + Product | Index.html | Not Started | P3 (David)

## Landing Page Tasks
ID | Source | Sprint | Task | Description | Priority | Effort | Owner | Files to Modify | Status | Persona(s) | Notes
L1 | Landing Page | Sprint 4 | Add SLD/LD to PROGRAMS data | Add 'Specific Learning Disability' with IEP, 504, insurance programs. Port from GAS App. | HIGH | Low | Content + Product | Landing-Page.jsx | Not Started | P2 (Maria)
L2 | Landing Page | Sprint 4 | Add SLD/LD journey map to JOURNEYS | Port SLD journey map from GAS App (2 phases). Match existing format. | HIGH | Low | Content + Product | Landing-Page.jsx | Not Started | P2 (Maria)
L3 | Landing Page | Sprint 4 | Add multi-select to eligibility tool | Allow multi-diagnosis selection. Show merged program list. Match GAS App capability. | HIGH | High | Engineering + Product | Landing-Page.jsx | Not Started | P3 (Jenny/David)
L4 | Landing Page | Sprint 4 | Remove/restructure email gate | Show all programs. Move email to waitlist or make optional after full reveal. | HIGH | Low | Growth + Product | Landing-Page.jsx | Not Started | All
L5 | Landing Page | Sprint 5 | Add responsive breakpoints | Media queries: 375px, 768px, 1024px. Stack grid, hamburger nav, vertical eligibility. | HIGH | Medium | Frontend | Landing-Page.jsx | Not Started | P2 (Maria)
L6 | Landing Page | Sprint 5 | Add Spanish localization | i18n for all user-facing strings. Language toggle in nav. Share translations with G1. | HIGH | Medium | Product + i18n | Landing-Page.jsx | Not Started | P2 (Maria)
L7 | Landing Page | Sprint 5 | Speed up typewriter animation | Reduce 35ms→20ms/char or instant on mobile. Detect viewport width. | LOW | Low | Frontend | Landing-Page.jsx | Not Started | P1 (Sarah)
L8 | Landing Page | Sprint 6 | Add diverse family imagery | Photos/illustrations of Latino, Asian, Black families. Testimonials. Cultural framing. | MEDIUM | Medium | Design + Content | Landing-Page.jsx | Not Started | P2, P3
L9 | Landing Page | Sprint 6 | Add age-personalized journey phases | Prompt for child's age. Highlight current phase. Session-only (no login needed). | MEDIUM | Low | Product + Frontend | Landing-Page.jsx | Not Started | P1, P3
L10 | Landing Page | Sprint 6 | Add ARIA labels and keyboard nav | ARIA roles, alt text, keyboard nav, skip-to-content link. Test with screen reader. | MEDIUM | High | Frontend + QA | Landing-Page.jsx | Not Started | P2, P3
L11 | Landing Page | Sprint 6 | Explain 'Conditional' RC for ADHD | Tooltip/inline note: ADHD alone doesn't qualify for RC. Explain Lanterman conditions. | MEDIUM | Low | Content + Product | Landing-Page.jsx | Not Started | P3 (David)

## Sprint Summary
Sprint | Phase | Tasks | HIGH | MED | LOW | Focus
Sprint 1 | GAS App | 4 | 2 | 2 | 0 | Language access (Spanish i18n) + equity (POS action card) + quick UX wins (AI prompts, email field)
Sprint 2 | GAS App | 4 | 0 | 4 | 0 | Infrastructure hardening: journey personalization, ZIP lookup, error handling, privacy claim
Sprint 3 | GAS App | 2 | 0 | 2 | 0 | Accessibility (ARIA, keyboard nav) + ADHD conditional RC explanation
Sprint 4 | Landing Page | 4 | 4 | 0 | 0 | Content parity with GAS App: SLD data, multi-select eligibility, email gate removal
Sprint 5 | Landing Page | 3 | 2 | 0 | 1 | Mobile responsiveness + Spanish localization + hero animation
Sprint 6 | Landing Page | 4 | 0 | 3 | 1 | Polish: diverse imagery, age personalization, accessibility, ADHD tooltip