## Backlog
Issue # | Sprint | Category | User Story / Title | Description | Acceptance Criteria | Cowork Prompt | Priority | Status | Est Hours | Git Branch | Commit Msg | Dependencies | Notes
SPRINT 0: FOUNDATION — Shared platform tasks tracked in VoltPlan plan
ℹ Phase 0 platform tasks (pipeline, Stripe, email, PDF, analytics) are in the VoltPlan project plan. Pipeline must be complete before Sprint 2.
SPRINT 2: IEPCLARITY LAUNCH (Week 3-5)
IEP-201 | Sprint 2 | Design | Design IEP form fields + upload flow | Map out form fields: child's grade, school district, document type (IEP/504/eval), specific concerns, upcoming meeting dates, file upload field for IEP document (PDF). | Field spec documented; file upload supports PDF up to 20MB; conditional logic mapped | Design the form fields for IEPClarity.ai intake. I need: child's grade level, school district name, document type (IEP/504 Plan/Evaluation Report/Other), specific parent concerns (text), upcoming meeting date, file upload for IEP document (PDF, up to 20MB). Add conditional fields where appropriate. | P0 | To Do | 1 | feat/iep-form-design | feat: IEP form field specification | —
IEP-202 | Sprint 2 | Feature | Build Tally form with file upload | Create Tally form with all IEP fields plus PDF upload. Configure webhook with file URL passthrough to Make.com. | Form live; file upload works for PDFs up to 20MB; webhook fires with form data + file URL | Build a Tally form for IEPClarity.ai with file upload capability. Fields: [paste IEP-201 spec]. The webhook must pass the uploaded file URL so Make.com can download and process it. Test with a sample IEP document. | P0 | To Do | 2 | feat/iep-tally | feat: IEPClarity Tally form with upload | IEP-201
IEP-203 | Sprint 2 | Feature | Write Claude prompt for IEP parsing | Engineer prompt chain: (1) Extract text from uploaded PDF (2) Identify document type and structure (3) Extract all goals with baselines/targets (4) Extract services, accommodations, modifications (5) Extract key dates (6) Generate structured JSON for tracker + summary. | Prompt correctly parses 5 test IEP documents from 3+ districts; extracts >90% of goals, services, and dates; handles different formats gracefully | I need a Claude prompt chain for IEPClarity.ai. The prompt receives extracted text from an IEP document and should: (1) identify document type (IEP/504/eval), (2) extract all goals with baselines and measurable targets, (3) extract related services (type, frequency, duration, provider), (4) extract accommodations and modifications, (5) extract all key dates (annual review, triennial, next meeting), (6) extract responsible parties. Output as structured JSON. | P0 | To Do | 4 | feat/iep-prompt | feat: IEP document parsing prompt chain | — | Highest leverage task
IEP-204 | Sprint 2 | Feature | Build XLSX tracker generation | Create script/template that takes parsed IEP JSON and generates a formatted Excel tracker with tabs: Goals, Services, Accommodations, Dates, Action Items. | Generated XLSX opens cleanly in Excel/Sheets; all data populated; formatting is professional and parent-friendly | Build an Excel tracker generator for IEPClarity.ai. Input: parsed IEP JSON. Output: formatted XLSX with tabs: Goals (goal text, baseline, target, measurement method, status), Services (type, frequency, duration, provider, start/end), Accommodations (description, setting, responsible), Key Dates (event, date, notes), Action Items (task, owner, deadline, status). Use clean formatting parents can understand. | P0 | To Do | 3 | feat/xlsx-tracker | feat: IEP tracker XLSX generation | —
IEP-205 | Sprint 2 | Design | Create PDF summary template | Design branded IEPClarity PDF summary: overview card, goal summary cards, service summary, accommodation checklist, deadline calendar view, meeting prep guide. | Template renders professional 4-6 page PDF; all sections populate from JSON; warm parent-friendly design | Design an HTML template for the IEPClarity.ai PDF summary report. Brand colors: #2E6B4F forest green, #D4834E terracotta, warm cream background. Sections: child overview card, goal summary cards (each with baseline/target/status), services grid, accommodations checklist, deadline calendar, meeting prep guide with suggested questions. Warm, parent-friendly tone. | P0 | To Do | 2 | feat/iep-pdf | feat: IEPClarity branded PDF template | —
IEP-206 | Sprint 2 | QA | Test with 5 IEP docs from 3+ districts | Run prompt chain against 5 real IEP documents from at least 3 different school districts. Evaluate parsing accuracy, completeness, and handling of different formats. | All 5 documents parsed without errors; >90% of goals/services/dates correctly extracted; format variations handled | Test my IEP parsing prompt with 5 real IEP documents from different districts. For each, evaluate: were all goals extracted? All services? All dates? Any hallucinated content? Any missed sections? Score accuracy as a percentage. | P0 | To Do | 3 | test/iep-parsing | test: validate parsing across districts | IEP-203
IEP-207 | Sprint 2 | Feature | Iterate parsing prompt for >90% accuracy | Based on IEP-206 results, refine prompt to handle format variations, improve extraction completeness, add error handling for corrupted/unusual documents. | Re-test all 5 documents; accuracy >90% for all; previously missed items now captured | Based on testing, my IEP prompt has these accuracy issues: [paste IEP-206 results]. Help me fix: (1) handling for non-standard goal formats, (2) better service frequency extraction, (3) date parsing for different date formats. Also add a confidence score to each extracted item. | P0 | To Do | 3 | fix/iep-prompt-v2 | fix: IEP parsing accuracy improvements | IEP-206
IEP-208 | Sprint 2 | Infra | Register iepclarity.ai domain | Register iepclarity.ai domain. Configure DNS for hosting + email. | Domain registered; DNS configured; SSL active |  | P0 | To Do | 0.5 | — | — | —
IEP-209 | Sprint 2 | Design | Build IEPClarity landing page | Deploy IEPClarity landing page with empathy-first messaging. Include "We Get It" section, how it works, what you get, pricing ($29 single / $69 annual / $9/mo sub), testimonials placeholder. | iepclarity.ai loads; mobile responsive; warm parent-friendly tone; form embedded; Lighthouse >90 | Deploy my IEPClarity.ai HTML landing page. Connect the iepclarity.ai domain. Ensure mobile responsiveness. Add PostHog analytics. The page should feel warm and empathetic — parents dealing with IEPs are often stressed and overwhelmed. | P0 | To Do | 3 | feat/iep-landing | feat: deploy IEPClarity landing page | IEP-208
IEP-210 | Sprint 2 | Feature | Embed form + Stripe on landing page | Embed Tally form on landing page. Configure Stripe checkout for $29 single parse tier. Wire to Make.com pipeline. | User fills form → uploads PDF → pays $29 → pipeline triggered → tracker + summary delivered |  | P0 | To Do | 1 | feat/iep-form-pay | feat: IEP form + payment integration | IEP-202, IEP-209
IEP-211 | Sprint 2 | Feature | Connect form → Make.com → IEP pipeline | Wire Tally form + file upload to Make.com scenario. Download uploaded PDF, extract text, run through Claude, generate XLSX + PDF, email both to customer. | Full pipeline works: upload → parse → tracker + summary → email delivered with both attachments | Connect my IEPClarity Tally form to the Make.com pipeline. The flow: (1) receive webhook with form data + file URL, (2) download the uploaded PDF, (3) extract text from PDF, (4) send to Claude for parsing, (5) generate XLSX tracker + PDF summary from Claude output, (6) email both files to customer. Help me build each Make.com module. | P0 | To Do | 2 | feat/iep-pipeline | feat: IEP form to pipeline integration | IEP-202, VP-008
IEP-212 | Sprint 2 | Marketing | Beta: Free parses for 10 FB parents | Post in 3-5 Facebook parent/special ed groups offering free IEP parses for first 10 respondents. Collect feedback and testimonials. | 10 parents receive free parses; 8+ provide feedback; testimonials collected with permission | Write a Facebook post for special education parent groups offering free IEP document parsing from IEPClarity.ai. Tone: empathetic, parent-to-parent. Mention that I'm a parent navigating IEPs too (for Teddy). Offer first 10 free, ask for honest feedback in return. | P0 | To Do | 3 | — | — | IEP-211
IEP-213 | Sprint 2 | Marketing | Collect testimonials from beta | Follow up with beta users. Request testimonials with permission to use on landing page. | 5+ testimonials collected with written permission; 3+ added to landing page |  | P1 | To Do | 1 | — | — | IEP-212
IEP-214 | Sprint 2 | Feature | Go live with $29 paid tier | Switch from free beta to paid $29 tier. Verify payment flow works. Update landing page with testimonials. | $29 payment processes correctly; first paid customer receives deliverables; testimonials visible on page |  | P0 | To Do | 1 | feat/iep-paid | feat: launch $29 paid tier | IEP-213
IEP-215 | Sprint 2 | Marketing | Post in FB groups with testimonials | Post in 3-5 Facebook parent groups with beta testimonials. Link to iepclarity.ai. | Posts published in 3+ groups; positive engagement; measurable traffic from Facebook |  | P0 | To Do | 2 | — | — | IEP-213
IEP-216 | Sprint 2 | Marketing | Post in Reddit special ed subs | Write helpful posts for r/specialeducation, r/IEP, r/Autism. Value-first, subtle mention. | Posts published; positive engagement; no removals |  | P1 | To Do | 1 | — | — | —
IEP-217 | Sprint 2 | Feature | Add Waypoint CTA to report + email | Add subtle Waypoint mention to PDF report footer and email template. Track click-through in PostHog. | CTA visible but not pushy; clicks tracked; conversion to Waypoint waitlist measurable |  | P1 | To Do | 1 | feat/waypoint-cta | feat: Waypoint CTA in IEP deliverables | IEP-205 | Keep light touch per Mike
IEP-218 | Sprint 2 | Marketing | Build email nurture sequence | Create 4-email nurture sequence: Day 1 (welcome + tips), Day 3 (IEP meeting prep guide), Day 7 (common parent rights), Day 14 (Waypoint intro). Set up in Make.com with delays. | All 4 emails designed and tested; delay triggers work correctly; unsubscribe option included | Create a 4-email nurture sequence for IEPClarity customers: Day 1: welcome + 3 tips for using your tracker. Day 3: IEP meeting prep guide (free value). Day 7: know your rights as a parent (IDEA overview). Day 14: gentle intro to Waypoint for ongoing support. Tone: warm, empathetic, parent-to-parent. | P1 | To Do | 3 | feat/nurture | feat: 4-email nurture sequence | —
IEP-219 | Sprint 2 | QA | Monitor first 5 paid orders | Manual QA review of first 5 paid customer deliverables. Check parsing accuracy, tracker usability, PDF quality. | All 5 reviewed; issues documented; accuracy >90%; no customer complaints |  | P0 | To Do | 2 | — | — | IEP-214
IEP-220 | Sprint 2 | Feature | Iterate prompt from customer feedback | Refine parsing prompt based on real customer document issues. | Updated prompt fixes flagged issues; re-test confirms improvements |  | P0 | To Do | 2 | fix/iep-prompt-v3 | fix: parsing refinements from customers | IEP-219
✓ GATE: 12+ paying customers. Parse accuracy >90%. 2+ Waypoint waitlist signups. FB referral traffic >40%.
SPRINT 3: OPTIMIZATION & B2B (Week 5-8)
IEP-301 | Sprint 3 | Feature | Build annual package ($69) — multi-doc | Support multiple document uploads per customer (IEP + evaluations + 504). Generate combined tracker with all documents. | Multi-doc upload works; combined tracker merges data from 2+ documents correctly | Extend IEPClarity to support an Annual package ($69) where parents can upload multiple documents (IEP + evaluations + previous IEPs). Generate a combined tracker that merges data from all documents into one comprehensive view. | P1 | To Do | 3 | feat/annual-tier | feat: annual multi-doc package | IEP-220
IEP-302 | Sprint 3 | Feature | Build subscription ($9/mo) with reminders | Create $9/mo Stripe subscription. Auto-send deadline reminders 2 weeks before IEP dates. Allow re-uploads for updated documents. | Subscription billing works; reminders fire on schedule; re-upload triggers re-parse |  | P1 | To Do | 3 | feat/subscription | feat: $9/mo subscription with reminders | IEP-301
IEP-303 | Sprint 3 | Marketing | Outreach: 20 special ed advocates | Compile list of 20 special ed advocates/attorneys. Send outreach offering bulk pricing for client intake. | 20 emails sent; 3+ replies; 1+ pilot started | Write a cold outreach email to special education advocates offering IEPClarity as an intake tool. Value prop: save hours per client on document review, offer clients a professional tracker, bulk pricing at $15-20/parse. Write 2 variants. | P1 | To Do | 2 | — | — | —
IEP-304 | Sprint 3 | Feature | District format detection | Build prompt logic that detects IEP document format/structure and adapts extraction strategy. Maintain district-specific templates for known formats. | System correctly identifies 3+ different district formats; extraction accuracy improves for previously problematic formats | My IEP parsing works well for standard formats but struggles with some districts. Help me build format detection logic: the prompt should first identify the document structure/format, then apply a district-specific extraction strategy. I want to maintain a library of known district formats. | P2 | To Do | 3 | feat/format-detect | feat: district format auto-detection | IEP-207
IEP-305 | Sprint 3 | Feature | Waypoint conversion tracking | Set up PostHog funnel: IEP customer → email nurture → Waypoint CTA click → waitlist signup. Dashboard showing conversion rate. | Funnel visible in PostHog; conversion rate measurable; > threshold triggers celebration |  | P1 | To Do | 1 | feat/waypoint-funnel | feat: Waypoint conversion funnel tracking | IEP-217
IEP-306 | Sprint 3 | Feature | Automated QA module (shared) | Same as VP-302 but adapted for IEP output validation. Check: all goals extracted, dates are valid, services have frequency data. | QA catches incomplete parses; flags for manual review; reduces error rate |  | P1 | To Do | 4 | feat/iep-auto-qa | feat: automated IEP output validation | —
IEP-307 | Sprint 3 | Feature | Post-delivery survey + feedback loop | Same survey framework as VP-305/306 adapted for IEP customers. Focus on parse accuracy and tracker usability. | Survey auto-sends; results in Airtable; weekly review process documented |  | P1 | To Do | 1 | feat/iep-survey | feat: IEP feedback survey | —
IEP-308 | Sprint 3 | Ops | 60-day review: Go / Pause / No-Go | Comprehensive review: revenue, customers, accuracy, Waypoint conversions, unit economics. | Decision documented; next phase plan defined |  | P0 | To Do | 2 | — | — | All | Major decision point
✓ GATE: >20% Waypoint conversion. Subscription tier active. 1+ advocate using as intake tool.

## Sprint Summary
Sprint | Timeline | Theme | Issues | Total Hours | Key Deliverables | Definition of Done
Sprint 0 | Week 1-2 | Foundation (Shared) | 14 | 22 | Shared automation pipeline — see VoltPlan project plan | Pipeline works end-to-end. Tracked in VoltPlan plan.
Sprint 2 | Week 3-5 | IEPClarity Launch | 20 | 35 | Live landing page at iepclarity.ai, Tally form with file upload, Claude IEP parsing prompt, XLSX tracker + PDF summary, beta testing with 10 parents, paid launch at $29 | 12+ paying customers. Parse accuracy >90%. 2+ Waypoint signups. FB referral >40%.
Sprint 3 | Week 5-8 | Optimization & B2B | 8 | 19 | Annual + subscription tiers, district format detection, advocate outreach, Waypoint funnel tracking, auto QA, 60-day review | >20% Waypoint conversion. Subscription active. 1+ advocate pilot. Go/No-Go decided.
TOTAL |  |  | 42 | 76

## Change Log
Date | Version | Changed By | Section | Change Description
2026-02-21 | 1.0 | Mike | All | Initial IEPClarity project plan created. Pricing: Single $29, Annual $69, Subscription $9/mo.
2026-02-21 | 1.1 | Mike | All | Local dev workflow (no GitHub). Added Cowork prompts, user stories, acceptance criteria to all tasks.