WAYPOINT

Project Plans Critical Review

Comprehensive Analysis of 49 Planning Documents

Gaps, Conflicts, and Recommendations

March 12, 2026

Prepared for Mike Beebe, Founder

CONFIDENTIAL

Table of Contents

# Executive Summary

This review synthesizes 49 planning documents across the WayPoint repository — business plans, GTM strategies, sprint plans, financial models, Apple App Store readiness plans, enterprise scale-up proposals, user research, and competitive analysis. The goal: identify gaps, conflicts, and missing pieces before go-to-market.

Bottom Line

WayPoint has exceptional domain knowledge, a working product (GAS MVP), deep user research, and a validated market thesis. However, the planning documents describe a product that does not yet exist (React Native/Supabase app) while the product that does exist (GAS MVP) has no GTM plan written for it. The financial projections conflict across documents, no plan has been updated to reflect actual progress, and critical path items (Apple App Store, RC vendorization) have not started.

# 1. The Core Conflict: Two Parallel Universes

The documents describe two different products on two different timelines that have never been reconciled:

## Universe A: GAS MVP (What Was Actually Built)

- Google Apps Script + Google Sheets + single HTML file

- 14+ sprints completed: 49 KB articles, 3 languages, draft generation, chat history, tone calibration

- Live and functional today

- Ceiling: ~50-100 DAU, no auth, no offline, no push notifications

## Universe B: React Native/Expo/Supabase App (What All Plans Describe)

- 12-week sprint plan (71 issues, 291 hours)

- Apple App Store readiness plan (6 sprints, 35 issues, 163 hours)

- Enterprise scale-up proposal (4 phases, 60+ issues, 36-48 weeks, $180K-$350K)

- Status: Auth scaffolding + Welcome screen only. Sprint 1 partially done. Everything else untouched.

The gap: Every GTM plan, every financial model, every investor document, and the Apple readiness plan assumes Universe B exists. It does not. The GAS MVP is production — but none of the plans account for it as the launch vehicle.

# 2. Financial Model Contradictions

Three versions of the financial model tell three different stories:

| Metric | v3 ($100/RC) | v3.2 ($12.49/RC) | Strategic Analysis | SWOT |
| --- | --- | --- | --- | --- |
| Year 1 Revenue | ~$29K | ~$14K | $130-180K | $318-500K |
| Year 1 Paid Users | 75 | ~50 | 1,100 | Not specified |
| 24-mo Net Income | -$30K | -$93K | 85% margin | Not modeled |
| Breakeven | Month 16 | Never (24 mo) | Month 10-12 | Not specified |

The gap: The Strategic Analysis and SWOT use the original optimistic projections that the V3 Addendum explicitly disavowed. These documents have not been updated to reflect the honest numbers. If these go to investors or partners, they will see conflicting figures across your own documents.

The single biggest variable: RC reimbursement rate. At $100/user/month, the model works. At $12.49, it does not break even in 2 years. There is no validated data point for what RCs will actually pay.

# 3. GTM Plan: V1 vs V3 — Which Is Active?

GTM Plan v1 (the .docx): 5 phases, 162 action items, 52 weeks, targets 15,000 active users and $18.6K MRR by Month 12.

GTM Plan v3 (Focus 90): 3 tracks, 8 weeks, targets 15 beta users and 5 IEPClarity customers.

The V3 Addendum explicitly states v1 was “a wish list, not an executable plan.” But:

- The Website Project Plan still references v1 Phase 0 targets (500 waitlist signups in 4 weeks)

- The 12-Week Plan still uses v1 timelines and user targets

- The GTM Actions spreadsheet still has all 162 v1 tasks

The gap: V1 artifacts were never archived, deprecated, or labeled as superseded. Someone reading the docs would see both versions with no clear signal about which is active.

# 4. Plan Tracking: Zero Plans Updated

Every single task tracker across all documents shows the same pattern:

| Document | Total Tasks | Marked Done | Actually Done |
| --- | --- | --- | --- |
| Sprint Plan (Expo) | 71 | 0 | ~7 (partial) |
| 12-Week Plan | 71+ | 0 | ~7 (partial) |
| Lite Project Plan | 55 | 0 | ~55 (all done!) |
| AI Engine Project Plan | 48 | 0 | 0 |
| Task Tracker | 21 | 0 | ~8 (via GAS sprints) |
| GAS MVP IT Plan | 40 | 4 sprints | 4 sprints (S1-S4) |
| Apple App Store Plan | 35 | 0 | 0 |
| Enterprise IT Plan | 60+ | 0 | 0 |
| Website Plan | 56 | 0 | 0 |

The gap: The Lite Project Plan describes exactly what was built — but shows 0% complete. The GAS MVP IT Plan is the only one reflecting any actual progress (S1-S4 done). There is no single source of truth for what has been done vs. what remains.

# 5. Apple App Store: Critical Path Not Started

The App Store Readiness Plan is thorough and well-researched, but:

- Requires React Native/Capacitor build — which does not exist yet (GAS MVP cannot be submitted to the App Store)

- April 2026 deadline: Apple requires iOS 26 SDK for all new submissions

- 12-week timeline (6 sprints) has not started

- Prerequisites not met: No Apple Developer enrollment, no DUNS number, no Privacy Policy page, no RevenueCat integration, no Supabase auth in production

- AI Consent Modal (Apple Rule 5.1.2(i), Nov 2025): Must explicitly name Anthropic and list every data type sent. Not designed yet.

The gap: There is no bridge plan from the GAS MVP to an App Store-submittable product. The Sprint Plan assumes starting from the waypoint-app scaffolding, but the GAS MVP has 14 sprints of features that would need to be re-implemented.

# 6. User Research: Rich Data, Weak Integration

The persona work is excellent — 10 detailed personas, 43 findings, impact matrix, priority roadmap. But:

- The Priority Roadmap Phase 1 items (Spanish i18n, RC eligibility fix, data persistence, Vietnamese) are partially addressed in GAS MVP but the tracker shows them all as “Not Started”

- 60% of personas face significant barriers — the app currently serves affluent, English-speaking, tech-literate families best

- Top user request (Document Vault) appears in 5 different plans but zero implementations

- Benefits Eligibility Calculator — mentioned in GAS IT Plan (S14), GTM Actions, Persona Matrix. Not built.

The gap: No traceability between persona findings and actual sprint work. Findings were documented but the path from “finding” to “shipped feature” is not tracked.

# 7. Documents That Do Not Exist But Should

Critical planning artifacts missing from the repository:

1. Migration Plan (GAS → Native App)

How do you get from the working GAS MVP to a submittable iOS app? Which features port, which get rebuilt, what is the timeline? This is the single most important missing document.

2. Single Source of Truth / Master Roadmap

One document that reconciles all plans into a unified, current-state view. Right now someone needs to read 10+ documents to understand what is happening.

3. RC Vendorization Playbook

The entire B2B revenue model depends on RC reimbursement, but there is no dedicated document for the vendorization process — just scattered references. The new DDS Provider Directory (mandatory March 2026) is mentioned once in Growth Assumptions but not in any project plan.

4. IEPClarity Product Plan

The V3 Addendum and Focus 90 plan make IEPClarity a P0 revenue validation track ($29-69 one-time product). But there is no product spec, no landing page plan, no build plan. It is a revenue line item with no implementation artifact.

5. Legal/Compliance Review

Multiple documents mention HIPAA, FERPA, COPPA, and “information vs. legal advice” risk. No legal review has been conducted. The App Store Readiness Plan flags this as a submission risk.

6. Analytics & Measurement Plan

No document describes what is being measured, how, or what tools are being used. The Product Review mentions “no analytics” as a gap.

7. Content/KB Maintenance Plan

The V3 Addendum budgets $2,500/month for KB maintenance. No process document exists for how articles get reviewed, updated, or added when laws change.

8. Data Privacy Policy & Terms of Service

The App Store plan requires hosted Privacy Policy and ToS pages. These do not exist yet.

# 8. Recommended Priorities

Based on the synthesis of all 49 documents:

## Decide First (Strategic)

- Is the GAS MVP the GTM vehicle, or must you build the native app first? Every downstream decision depends on this. The GAS MVP is live and functional but cannot go on the App Store. The native app would take 8-12 weeks minimum.

- What is the RC reimbursement rate assumption? $100 vs $12.49 is the difference between a viable and non-viable business model within 24 months.

## Fix Immediately (Document Hygiene)

- Reconcile financial projections across Business Plan, Strategic Analysis, and SWOT to use v3.2 numbers (or explicitly label which scenario each uses)

- Archive or label v1 GTM artifacts as superseded by Focus 90

- Create a single master roadmap that reflects what has actually been built and what is next

## Build Next (If GAS MVP Is the GTM Vehicle)

- GAS IT Plan Sprints 5-17 contain the features your personas need most

- RC vendorization research and outreach (the March 2026 Provider Directory deadline is NOW)

- IEPClarity product spec + landing page (your earliest revenue validation)

# Appendix: Documents Reviewed

The following 49 documents were analyzed for this review:

Business & GTM Plans (7)

- Waypoint-Business-Plan.docx

- Waypoint-Business-Plan-V3-Addendum.docx

- Waypoint-GTM-Plan.docx

- Waypoint-GTM-Plan-v3.xlsx

- Waypoint-GTM-Actions.xlsx

- Waypoint-Enterprise-ScaleUp-Proposal.docx

- Waypoint-Growth-Assumptions-Research.docx

Project & Sprint Plans (13)

- Waypoint-Project-Plan.docx

- Waypoint-Sprint-Plan.xlsx

- Waypoint-12-Week-Plan.xlsx

- Waypoint-Lite-Project-Plan.xlsx

- Waypoint-AI-Engine-Project-Plan.xlsx

- Waypoint-AI-Engine-Build-Plan.docx

- Waypoint-Task-Tracker.xlsx

- Waypoint-Website-Project-Plan.xlsx

- Waypoint-Enterprise-IT-Project-Plan.xlsx

- Waypoint_IT_Project_Plan.xlsx

- Waypoint-Apple-AppStore-Project-Plan-v2.xlsx

- Waypoint-Port-Sprint-Plan.xlsx

Financial Models (3)

- Waypoint-Financial-Model-v3.xlsx

- Waypoint-Financial-Model-v3.1.xlsx

- Waypoint-Financial-Model-v3_2.xlsx

Strategic Analysis & Competitive (4)

- Waypoint-Competitor-Analysis.docx

- Waypoint-SWOT-Analysis.docx

- Waypoint-SWOT-Matrix.docx

- Waypoint-Strategic-Analysis-Mar2026.docx

Apple App Store Readiness (2)

- Waypoint-Apple-AppStore-Readiness-Plan-v2.docx

- Waypoint-Apple-AppStore-Project-Plan-v2.xlsx

User Research & Testing (6)

- Waypoint-User-Testing-Memo.docx

- Waypoint_Parent_Personas.xlsx

- Waypoint_Parent_Personas_California.docx

- Waypoint_Persona_Feedback_Matrix.xlsx

- Waypoint_Persona_Testing_Report.docx

- Waypoint-Product-Review-Feb2026.docx

Investor Materials (2)

- Waypoint-Investor-Pitch.pptx

- Waypoint-Investor-Pitch-v3.pptx

Other (12+)

- Executive_Summary_Memo_CA_Parents_Disabilities.docx

- Waypoint-Lite-Sheets-MVP.docx

- Waypoint-Lite-KB-Articles (multiple versions)

- Waypoint MVP Data.xlsx

- Waypoint-Entity-Navigation-Matrix-v9_4.xlsx