## Findings by Need Bucket
ID | Memo Bucket | Finding Type | Severity | Title | Description | Effort | GAS Feasible? | GAS Notes | Priority Rank | Affected Personas | Persona Count
BUG-01 | 1. Rights & Process Information | Critical Bug | Critical | Spanish i18n Only Covers Landing Page | Entire app after onboarding is English-only. Spanish-dominant users (30% of CA) cannot use dashboard, chat, articles, or action plans. | Medium | Yes | GAS HtmlService supports dynamic string replacement. Store translations in Sheets. Swap strings based on user lang preference. | 1 | 1, 5 | 2
BUG-05 | 1. Rights & Process Information | Critical Bug | Critical | Diagnosis-to-Eligibility Mapping Errors | ADHD-only users incorrectly directed to Regional Center. Autism users with normal IQ not told they qualify under 5th category. SLD users get minimal content. | Medium | Yes | Fix generateRichPlan() logic to filter actions by diagnosis eligibility matrix. Pure code change. | 2 | 2, 3, 4 | 3
IMP-01 | 1. Rights & Process Information | Improvement | High | Add Vietnamese Language Support | Vietnamese is CA's 4th most spoken language. Tran family (grandparent caregivers) at suspension crisis with zero language support. | Medium | Yes | Same i18n architecture as Spanish. Add VI strings to STRINGS object and translation sheets. | 5 | 9 | 1
IMP-02 | 1. Rights & Process Information | Improvement | High | Add Tagalog, Mandarin, Cantonese Support | These 3 languages + Vietnamese + Spanish cover ~65% of CA non-English speakers. | Large | Yes | Same approach as Vietnamese. Larger translation effort but same architecture. | 12 | Extended CA population | 0
IMP-03 | 1. Rights & Process Information | Improvement | High | Expand Onboarding to Capture Key Demographics | Missing: immigration concerns, military status, kinship/guardianship, rural location, language beyond EN/ES, parent disability, single parent status. | Medium | Yes | Add onboarding screens/steps. Store in user profile Sheets. Use to customize plan generation. | 6 | 5, 6, 7, 9 | 4
IMP-10 | 1. Rights & Process Information | Improvement | Medium | Learn More Articles Should Link External Resources | Articles don't link to DRC, SERR manual, CDE resources, TRICARE, RC websites, Medi-Cal lookup. | Small | Yes | Add href links to LEARN_MORE data objects. Simple content update. | 15 | All | 10
IMP-15 | 1. Rights & Process Information | Improvement | Medium | Surface Tone Escalation System in Chat UI | Tone levels (collaborative→assertive→adversarial) exist but users don't know. No toggle or explanation in chat. | Small | Yes | Add UI toggle button in chat screen. Pass tone parameter to askWaypoint(). Already supported backend. | 16 | 3, 8, 10 | 3
IMP-16 | 1. Rights & Process Information | Improvement | Medium | RC Reimbursable List Should Explain Process | Shows what's reimbursable but not HOW: forms, timelines, documentation needed, dispute process. | Small | Yes | Expand RC_REIMBURSABLE data structure with process fields. Render in expanded view. | 20 | 1, 5, 7, 9 | 4
IMP-20 | 1. Rights & Process Information | Improvement | Medium | Regulatory/Procedural Quick-Reference Cards | Timelines scattered across articles. Need: IEP timeline card, RC referral card, appeal deadlines card, suspension rules card. | Small | Yes | Create new data structure for quick-ref cards. Render as modal or dashboard widget. | 18 | All | 10
IMP-21 | 1. Rights & Process Information | Improvement | Medium | Personalized Resource Recommendations | All users see same 40+ articles. Should filter by diagnosis, phase, urgency, language. | Medium | Yes | Tag articles with metadata. Score relevance against user profile. Sort/filter in renderLearnMore(). | 19 | All | 10
FEAT-08 | 1. Rights & Process Information | Large Feature | Medium | Benefit Eligibility Calculator | Interactive questionnaire → shows all programs family may qualify for (SSI, IHSS, Medi-Cal, CCS, CalWORKs, CalABLE). | Large | Yes | Decision-tree logic in Code.gs. Store eligibility rules in Sheets. Render results in HTML. | 22 | 1, 5, 7, 9 | 4
FEAT-09 | 1. Rights & Process Information | Large Feature | Medium | Military Family Module | EFMP integration, PCS transition checklists, TRICARE navigation, dual system coordination for military families. | Large | Yes | Content + onboarding flag. New KB entries for military. Conditional action plan generation. | 28 | 6 | 1
BUG-02 | 2. Advocacy & Conflict Resolution | Critical Bug | Critical | Fragile Client-Side Email Analysis Regex | Hardcoded patterns ("unfortunately", "at this time") produce false positives. AI analysis requires API key setup most users won't complete. | Small | Yes | Improve regex patterns. Add confidence scoring. Make AI analysis default (API key already in Code.gs). | 4 | All | 10
BUG-08 | 2. Advocacy & Conflict Resolution | Critical Bug | Medium | Check-in Frustration Flow Actions Not Integrated into Dashboard | Frustration flows generate escalation actions (4731 complaints, IEE requests) but they appear in modal and disappear. Not tracked in action list. | Medium | Yes | Save frustration-generated actions to user's action plan in Sheets. Tag with "escalation" priority. | 8 | 1, 3, 5, 7, 9 | 5
IMP-13 | 2. Advocacy & Conflict Resolution | Improvement | High | Expand Draft Generation Templates | Missing: PWN request, assessment request, records request, CDE/OCR complaints, IHSS appeal, 4731 complaint, manifestation determination challenge, AAC eval request. | Medium | Yes | Add new draft types to generateDraft() in Code.gs. Each type needs system prompt + user context injection. | 9 | 3, 8, 9, 10 | 4
IMP-19 | 2. Advocacy & Conflict Resolution | Improvement | High | Emergency/Crisis Quick-Access | No fast path for "my child was just expelled" or "I got a denial letter today." Users must navigate normal app flow during crisis. | Small | Yes | Add crisis button to home screen. Map to 5 scenario templates. Generate same-day/next-day priority actions. | 10 | 3, 8, 9 | 3
FEAT-07 | 2. Advocacy & Conflict Resolution | Large Feature | Medium | Advocate and Attorney Directory | Searchable database: region, specialization, cost model, languages, credentials, user reviews. | Large | Partial | Can store directory in Sheets and render in HTML. User reviews need auth system GAS doesn't natively support well. Consider read-only directory first. | 23 | 2, 3, 8, 10 | 4
BUG-03 | 3. Service Access & Accountability | Critical Bug | Critical | localStorage-Based Action State with No Persistence | All progress stored in browser localStorage only. Device switch, browser clear, incognito = total progress loss with no recovery. | Large | Yes | Sync action state to Google Sheets (ActionLog). Read from Sheets on load, write on change. GAS server calls handle this. | 3 | All | 10
BUG-06 | 3. Service Access & Accountability | Critical Bug | High | Profile Save Destructively Regenerates Action Plan | Editing profile calls generateRichPlan() which creates new plan, destroying all started/completed/dismissed states and follow-ups. | Medium | Yes | Implement action plan versioning. Compare old vs new plan. Preserve completion states by matching action IDs. | 7 | All | 10
BUG-07 | 3. Service Access & Accountability | Critical Bug | Medium | No Session Timeout Handling | GAS session expires mid-use → cryptic error, no recovery. No warning, no re-authentication, no state caching. | Small | Yes | Add client-side timeout detection. Catch google.script.run failures. Show re-auth prompt. Cache last state in localStorage. | 11 | All | 10
IMP-05 | 3. Service Access & Accountability | Improvement | Medium | Contextual Quick Actions Grid | Home screen quick actions are static. Should adapt based on action plan progress, deadlines, and user situation. | Small | Yes | Score actions by status/urgency in renderHome(). Display top 4-6 dynamic buttons. | 17 | All | 10
IMP-08 | 3. Service Access & Accountability | Improvement | High | Add Proactive Notification/Reminder System | No reminders. Users must remember to return. Deadlines, follow-ups, authorization expirations go untracked. | Medium | Partial | GAS time-based triggers can send emails. Browser push notifications need service worker (not native GAS). Email reminders are fully feasible. | 13 | All | 10
IMP-09 | 3. Service Access & Accountability | Improvement | Medium | Agency Directory Should Filter by User Location | Static/hardcoded agency list. Should detect user county from profile and surface local agencies with contact info, languages, hours. | Small | Yes | Add county field to profile. Filter AGENCIES data by county. Already have ZIP_TO_RC mapping as foundation. | 21 | 1, 8, 9 | 3
IMP-11 | 3. Service Access & Accountability | Improvement | Medium | Expand Follow-Up Outcome Tracking | Outcomes limited to "Voicemail/Spoke/Denied." Need nuanced outcomes per agency type and free-text notes. | Small | Yes | Expand FOLLOWUPS object with richer outcome options. Store in Sheets. Simple UI addition. | 24 | All | 10
IMP-14 | 3. Service Access & Accountability | Improvement | Medium | Add Progress History and Timeline | No way to see what was accomplished and when. Need timestamped completion log and progress visualization. | Small | Yes | Log timestamps to ActionLog sheet on status change. New "History" screen rendering from Sheets data. | 25 | All | 10
IMP-18 | 3. Service Access & Accountability | Improvement | Medium | Action Cards Should Show Dependencies | Some actions must precede others (e.g., call RC before requesting eval). No dependency display or sequencing. | Small | Yes | Add dependency field to action plan data model. Render "Blocked by" and "Enables" on cards. Gray out blocked items. | 27 | All | 10
FEAT-01 | 3. Service Access & Accountability | Large Feature | High | Document Vault | Upload, store, organize IEPs, evaluations, denial letters. Tagged by date/agency/type. Full-text search. Share with advocates. | Very Large | Partial | Can use Google Drive API for storage (GAS has DriveApp). File upload via HTML form. Tagging via Sheets metadata. Full-text search limited in GAS. | 26 | 3, 8, 10 | 3
FEAT-02 | 3. Service Access & Accountability | Large Feature | High | Appointment Tracker with Prep Checklists | Unified calendar across RC, school, medical, therapy. Smart reminders. Prep checklists per appointment type. Post-appointment logging. | Large | Yes | Store appointments in Sheets. Render calendar view in HTML/JS. Google Calendar API for sync. Prep checklists as KB content. | 14 | 7, 8, 9 | 3
FEAT-04 | 3. Service Access & Accountability | Large Feature | High | Service Coordination Dashboard | Visual map of all active services, providers, authorization dates, renewal deadlines, costs. | Large | Yes | New Sheets tab for services data. Render dashboard with HTML/JS visualization. Deadline tracking via GAS triggers. | 29 | 1, 5, 7, 8, 9 | 5
FEAT-10 | 3. Service Access & Accountability | Large Feature | Medium | Interactive Journey Timeline Visualization | Horizontal timeline showing milestones, current status, projected future. Export as image/PDF. | Medium | Yes | Build with HTML5 Canvas or SVG in Index.html. Data from ActionLog + user profile. Export via html2canvas. | 30 | 4, 8 | 2
IMP-04 | 4. Emotional & Community Support | Improvement | High | Multi-Child Support | Most families have siblings. App assumes single child. Parents must run separate instances or conflate children. | Large | Yes | Add child selector to profile. Separate action plans per child in Sheets. Unified dashboard view. | 8 | 1, 2, 3, 4, 5, 6, 8 | 7
IMP-07 | 4. Emotional & Community Support | Improvement | Medium | SMS Reminders Should Be Actual Reminders | Current "Text Myself" sends one-time copy. Should set up recurring reminders (7 days, 24 hours before deadline). | Medium | Partial | GAS can't send SMS natively. Options: Twilio API via UrlFetchApp, or email-to-SMS gateways. Email reminders fully feasible. | 26 | 7, 8, 9 | 3
IMP-17 | 4. Emotional & Community Support | Improvement | Medium | Action Plan Sharing with Co-Parents/Advocates | No way to share plans. Need invite collaborator, shareable read-only link, comments. | Medium | Partial | Can generate shareable link (GAS doGet with token parameter). Full collaboration needs real-time sync GAS doesn't support well. Read-only sharing feasible. | 31 | 2, 4, 6 | 3
IMP-22 | 4. Emotional & Community Support | Improvement | Medium | Mobile Responsiveness and Accessibility Audit | App targets 480px but needs WCAG AA color contrast, keyboard nav, screen reader, 200% zoom testing. | Medium | Yes | Pure HTML/CSS/JS improvements. No GAS limitations. Fix contrast, add ARIA labels, test focus indicators. | 32 | All | 10
FEAT-05 | 4. Emotional & Community Support | Large Feature | Medium | Peer Connection Network | Anonymized matching by RC, school district, diagnosis, situation. Moderated forums. Direct messaging. | Very Large | No | Real-time messaging, user moderation, and forum functionality exceed GAS capabilities. Would need separate platform (Firebase, Supabase) with GAS as data bridge. | 35 | 1, 5, 7, 9 | 4
FEAT-06 | 4. Emotional & Community Support | Large Feature | Medium | Persistent Chat History | Chat sessions don't persist. Users can't return to prior conversations or search past AI guidance. | Medium | Yes | Already have ChatSessions sheet. Store full conversation history. Add chat list screen. Search via Apps Script string matching. | 33 | 2, 3, 8 | 3
FEAT-12 | 4. Emotional & Community Support | Large Feature | Medium | Family Delegation and Account Sharing | Role-based access: co-parent (edit), advocate (view), grandmother (configurable). Permission matrix. Audit log. | Large | Partial | GAS lacks native user auth/roles. Can implement via shared access tokens + Sheets-based permission table. Limited but workable for basic delegation. | 34 | 2, 5, 6, 7, 9 | 5
BUG-04 | 5. Transition & Life Pathway | Critical Bug | High | No Offline Capability | GAS web app requires live internet. Rural users (Redding) and traveling parents (8-12 appointments) lose work mid-session. | Very Large | No | GAS cannot serve offline. PWA service workers not supported in GAS HtmlService. Would require migration to standalone web app. | 36 | 7, 8 | 2
IMP-06 | 5. Transition & Life Pathway | Improvement | Medium | Expand Calendar Integration | Only Google Calendar supported. Need Apple Calendar (.ics), Outlook, generic .ics download. | Small | Yes | Generate .ics files server-side with GAS. Serve as downloadable blob. Works for all calendar apps. | 23 | All | 10
IMP-12 | 5. Transition & Life Pathway | Improvement | High | Document Upload and Storage | No in-app storage for IEPs, evaluations, denial letters. Need upload, tag, search, share, attach to actions. | Medium | Yes | GAS DriveApp creates folders per user. HTML file upload form. Store metadata in Sheets. Link files to actions. | 14 | 3, 8, 10 | 3
FEAT-03 | 5. Transition & Life Pathway | Large Feature | High | Multi-Child Support Dashboard | Separate action plans per child. Unified view. Cross-child insights. Color-coded calendar. | Very Large | Yes | Multiple child profiles in Sheets. Child selector in UI. Separate action plan generation per child. Dashboard aggregation. | 15 | 1, 2, 3, 4, 5, 6, 8 | 7
FEAT-11 | 5. Transition & Life Pathway | Large Feature | High | PWA / Offline Mode | Progressive Web App for offline access to plans, articles, drafts. Background sync. | Very Large | No | GAS HtmlService does not support service workers or PWA manifest. Would need to migrate frontend to standalone hosting. | 37 | 7, 8 | 2
FEAT-13 | 5. Transition & Life Pathway | Large Feature | Medium | Integration with External Systems | Connect to school IEP portals, RC case management, IHSS timesheets, Medi-Cal portal. | Very Large | No | External system APIs (school districts, RC) largely don't exist. Where APIs exist, GAS UrlFetchApp could connect. Mostly blocked by lack of partner APIs. | 38 | All | 10

## Bucket Summary
Bucket # | Need Category (from Memo) | Total Findings | Critical Bugs | Improvements | Large Features | GAS: Yes | GAS: Partial | GAS: No | Top Priority Items
1 | 1. Rights & Process Information | 12 | 2 | 8 | 2 | 12 | 0 | 0 | BUG-01, BUG-05, IMP-01
2 | 2. Advocacy & Conflict Resolution | 5 | 2 | 2 | 1 | 4 | 1 | 0 | BUG-02, BUG-08, IMP-13
3 | 3. Service Access & Accountability | 13 | 3 | 6 | 4 | 11 | 2 | 0 | BUG-03, BUG-06, BUG-07
4 | 4. Emotional & Community Support | 7 | 0 | 4 | 3 | 3 | 3 | 1 | IMP-04, IMP-07, IMP-17
5 | 5. Transition & Life Pathway | 6 | 1 | 2 | 3 | 3 | 0 | 3 | IMP-12, FEAT-03, IMP-06
TOTAL |  | 43 | 8 | 22 | 13 | 33 | 6 | 4

## Persona Impact Matrix
ID | Bucket | Title | P1:Maria | P2:David | P3:Tamika | P4:Robert | P5:Guadalupe | P6:Keoni | P7:Destiny | P8:James | P9:Anh | P10:Alexis | Count
BUG-01 | Rights & Process Information | Spanish i18n Only Covers Landing Page | X |  |  |  | X | [5 empty] | 2
BUG-05 | Rights & Process Information | Diagnosis-to-Eligibility Mapping Errors |  | X | X | X | [6 empty] | 3
IMP-01 | Rights & Process Information | Add Vietnamese Language Support | [8 empty] | X |  | 1
IMP-02 | Rights & Process Information | Add Tagalog, Mandarin, Cantonese Support | [10 empty] | 0
IMP-03 | Rights & Process Information | Expand Onboarding to Capture Key Demographics |  |  |  |  | X | X | X |  | X |  | 4
IMP-10 | Rights & Process Information | Learn More Articles Should Link External Resources | X | X | X | X | X | X | X | X | X | X | 10
IMP-15 | Rights & Process Information | Surface Tone Escalation System in Chat UI |  |  | X |  |  |  |  | X |  | X | 3
IMP-16 | Rights & Process Information | RC Reimbursable List Should Explain Process | X |  |  |  | X |  | X |  | X |  | 4
IMP-20 | Rights & Process Information | Regulatory/Procedural Quick-Reference Cards | X | X | X | X | X | X | X | X | X | X | 10
IMP-21 | Rights & Process Information | Personalized Resource Recommendations | X | X | X | X | X | X | X | X | X | X | 10
FEAT-08 | Rights & Process Information | Benefit Eligibility Calculator | X |  |  |  | X |  | X |  | X |  | 4
FEAT-09 | Rights & Process Information | Military Family Module | [5 empty] | X |  |  |  |  | 1
BUG-02 | Advocacy & Conflict Resolution | Fragile Client-Side Email Analysis Regex | X | X | X | X | X | X | X | X | X | X | 10
BUG-08 | Advocacy & Conflict Resolution | Check-in Frustration Flow Actions Not Integrated into Dashboard | X |  | X |  | X |  | X |  | X |  | 5
IMP-13 | Advocacy & Conflict Resolution | Expand Draft Generation Templates |  |  | X |  |  |  |  | X | X | X | 4
IMP-19 | Advocacy & Conflict Resolution | Emergency/Crisis Quick-Access |  |  | X |  |  |  |  | X | X |  | 3
FEAT-07 | Advocacy & Conflict Resolution | Advocate and Attorney Directory |  | X | X |  |  |  |  | X |  | X | 4
BUG-03 | Service Access & Accountability | localStorage-Based Action State with No Persistence | X | X | X | X | X | X | X | X | X | X | 10
BUG-06 | Service Access & Accountability | Profile Save Destructively Regenerates Action Plan | X | X | X | X | X | X | X | X | X | X | 10
BUG-07 | Service Access & Accountability | No Session Timeout Handling | X | X | X | X | X | X | X | X | X | X | 10
IMP-05 | Service Access & Accountability | Contextual Quick Actions Grid | X | X | X | X | X | X | X | X | X | X | 10
IMP-08 | Service Access & Accountability | Add Proactive Notification/Reminder System | X | X | X | X | X | X | X | X | X | X | 10
IMP-09 | Service Access & Accountability | Agency Directory Should Filter by User Location | X | [6 empty] | X | X |  | 3
IMP-11 | Service Access & Accountability | Expand Follow-Up Outcome Tracking | X | X | X | X | X | X | X | X | X | X | 10
IMP-14 | Service Access & Accountability | Add Progress History and Timeline | X | X | X | X | X | X | X | X | X | X | 10
IMP-18 | Service Access & Accountability | Action Cards Should Show Dependencies | X | X | X | X | X | X | X | X | X | X | 10
FEAT-01 | Service Access & Accountability | Document Vault |  |  | X |  |  |  |  | X |  | X | 3
FEAT-02 | Service Access & Accountability | Appointment Tracker with Prep Checklists | [6 empty] | X | X | X |  | 3
FEAT-04 | Service Access & Accountability | Service Coordination Dashboard | X |  |  |  | X |  | X | X | X |  | 5
FEAT-10 | Service Access & Accountability | Interactive Journey Timeline Visualization |  |  |  | X |  |  |  | X |  |  | 2
IMP-04 | Emotional & Community Support | Multi-Child Support | X | X | X | X | X | X |  | X |  |  | 7
IMP-07 | Emotional & Community Support | SMS Reminders Should Be Actual Reminders | [6 empty] | X | X | X |  | 3
IMP-17 | Emotional & Community Support | Action Plan Sharing with Co-Parents/Advocates |  | X |  | X |  | X |  |  |  |  | 3
IMP-22 | Emotional & Community Support | Mobile Responsiveness and Accessibility Audit | X | X | X | X | X | X | X | X | X | X | 10
FEAT-05 | Emotional & Community Support | Peer Connection Network | X |  |  |  | X |  | X |  | X |  | 4
FEAT-06 | Emotional & Community Support | Persistent Chat History |  | X | X |  |  |  |  | X |  |  | 3
FEAT-12 | Emotional & Community Support | Family Delegation and Account Sharing |  | X |  |  | X | X | X |  | X |  | 5
BUG-04 | Transition & Life Pathway | No Offline Capability | [6 empty] | X | X |  |  | 2
IMP-06 | Transition & Life Pathway | Expand Calendar Integration | X | X | X | X | X | X | X | X | X | X | 10
IMP-12 | Transition & Life Pathway | Document Upload and Storage |  |  | X |  |  |  |  | X |  | X | 3
FEAT-03 | Transition & Life Pathway | Multi-Child Support Dashboard | X | X | X | X | X | X |  | X |  |  | 7
FEAT-11 | Transition & Life Pathway | PWA / Offline Mode | [6 empty] | X | X |  |  | 2
FEAT-13 | Transition & Life Pathway | Integration with External Systems | X | X | X | X | X | X | X | X | X | X | 10
TOTAL |  | Findings affecting each persona | 24 | 22 | 26 | 20 | 25 | 21 | 26 | 31 | 28 | 20

## GAS Feasibility
ID | Title | GAS Feasible? | GAS Implementation Notes | Effort | Alternative if Not GAS | CoWork Actionable?
BUG-01 | Spanish i18n Only Covers Landing Page | Yes | GAS HtmlService supports dynamic string replacement. Store translations in Sheets. Swap strings based on user lang preference. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
BUG-05 | Diagnosis-to-Eligibility Mapping Errors | Yes | Fix generateRichPlan() logic to filter actions by diagnosis eligibility matrix. Pure code change. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-01 | Add Vietnamese Language Support | Yes | Same i18n architecture as Spanish. Add VI strings to STRINGS object and translation sheets. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-02 | Add Tagalog, Mandarin, Cantonese Support | Yes | Same approach as Vietnamese. Larger translation effort but same architecture. | Large | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-03 | Expand Onboarding to Capture Key Demographics | Yes | Add onboarding screens/steps. Store in user profile Sheets. Use to customize plan generation. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-10 | Learn More Articles Should Link External Resources | Yes | Add href links to LEARN_MORE data objects. Simple content update. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-15 | Surface Tone Escalation System in Chat UI | Yes | Add UI toggle button in chat screen. Pass tone parameter to askWaypoint(). Already supported backend. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-16 | RC Reimbursable List Should Explain Process | Yes | Expand RC_REIMBURSABLE data structure with process fields. Render in expanded view. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-20 | Regulatory/Procedural Quick-Reference Cards | Yes | Create new data structure for quick-ref cards. Render as modal or dashboard widget. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-21 | Personalized Resource Recommendations | Yes | Tag articles with metadata. Score relevance against user profile. Sort/filter in renderLearnMore(). | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-08 | Benefit Eligibility Calculator | Yes | Decision-tree logic in Code.gs. Store eligibility rules in Sheets. Render results in HTML. | Large | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-09 | Military Family Module | Yes | Content + onboarding flag. New KB entries for military. Conditional action plan generation. | Large | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
BUG-02 | Fragile Client-Side Email Analysis Regex | Yes | Improve regex patterns. Add confidence scoring. Make AI analysis default (API key already in Code.gs). | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
BUG-08 | Check-in Frustration Flow Actions Not Integrated into Dashboard | Yes | Save frustration-generated actions to user's action plan in Sheets. Tag with "escalation" priority. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-13 | Expand Draft Generation Templates | Yes | Add new draft types to generateDraft() in Code.gs. Each type needs system prompt + user context injection. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-19 | Emergency/Crisis Quick-Access | Yes | Add crisis button to home screen. Map to 5 scenario templates. Generate same-day/next-day priority actions. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-07 | Advocate and Attorney Directory | Partial | Can store directory in Sheets and render in HTML. User reviews need auth system GAS doesn't natively support well. Consider read-only directory first. | Large | Read-only directory in GAS. Full review system needs external auth. | Yes - CoWork can write/edit Code.gs and Index.html directly
BUG-03 | localStorage-Based Action State with No Persistence | Yes | Sync action state to Google Sheets (ActionLog). Read from Sheets on load, write on change. GAS server calls handle this. | Large | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
BUG-06 | Profile Save Destructively Regenerates Action Plan | Yes | Implement action plan versioning. Compare old vs new plan. Preserve completion states by matching action IDs. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
BUG-07 | No Session Timeout Handling | Yes | Add client-side timeout detection. Catch google.script.run failures. Show re-auth prompt. Cache last state in localStorage. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-05 | Contextual Quick Actions Grid | Yes | Score actions by status/urgency in renderHome(). Display top 4-6 dynamic buttons. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-08 | Add Proactive Notification/Reminder System | Partial | GAS time-based triggers can send emails. Browser push notifications need service worker (not native GAS). Email reminders are fully feasible. | Medium | Email via GAS MailApp. Push notifications need service worker (not GAS). | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-09 | Agency Directory Should Filter by User Location | Yes | Add county field to profile. Filter AGENCIES data by county. Already have ZIP_TO_RC mapping as foundation. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-11 | Expand Follow-Up Outcome Tracking | Yes | Expand FOLLOWUPS object with richer outcome options. Store in Sheets. Simple UI addition. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-14 | Add Progress History and Timeline | Yes | Log timestamps to ActionLog sheet on status change. New "History" screen rendering from Sheets data. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-18 | Action Cards Should Show Dependencies | Yes | Add dependency field to action plan data model. Render "Blocked by" and "Enables" on cards. Gray out blocked items. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-01 | Document Vault | Partial | Can use Google Drive API for storage (GAS has DriveApp). File upload via HTML form. Tagging via Sheets metadata. Full-text search limited in GAS. | Very Large | DriveApp for storage. Limited search. Consider Algolia for full-text search. | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-02 | Appointment Tracker with Prep Checklists | Yes | Store appointments in Sheets. Render calendar view in HTML/JS. Google Calendar API for sync. Prep checklists as KB content. | Large | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-04 | Service Coordination Dashboard | Yes | New Sheets tab for services data. Render dashboard with HTML/JS visualization. Deadline tracking via GAS triggers. | Large | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-10 | Interactive Journey Timeline Visualization | Yes | Build with HTML5 Canvas or SVG in Index.html. Data from ActionLog + user profile. Export via html2canvas. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-04 | Multi-Child Support | Yes | Add child selector to profile. Separate action plans per child in Sheets. Unified dashboard view. | Large | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-07 | SMS Reminders Should Be Actual Reminders | Partial | GAS can't send SMS natively. Options: Twilio API via UrlFetchApp, or email-to-SMS gateways. Email reminders fully feasible. | Medium | Use Twilio API via GAS UrlFetchApp for SMS. Email reminders as fallback. | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-17 | Action Plan Sharing with Co-Parents/Advocates | Partial | Can generate shareable link (GAS doGet with token parameter). Full collaboration needs real-time sync GAS doesn't support well. Read-only sharing feasible. | Medium | Basic sharing via token URLs. Full collaboration needs external platform. | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-22 | Mobile Responsiveness and Accessibility Audit | Yes | Pure HTML/CSS/JS improvements. No GAS limitations. Fix contrast, add ARIA labels, test focus indicators. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-05 | Peer Connection Network | No | Real-time messaging, user moderation, and forum functionality exceed GAS capabilities. Would need separate platform (Firebase, Supabase) with GAS as data bridge. | Very Large | Build on Firebase/Supabase with real-time DB. GAS handles data bridge. | Limited - CoWork can plan architecture but deployment needs manual setup
FEAT-06 | Persistent Chat History | Yes | Already have ChatSessions sheet. Store full conversation history. Add chat list screen. Search via Apps Script string matching. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-12 | Family Delegation and Account Sharing | Partial | GAS lacks native user auth/roles. Can implement via shared access tokens + Sheets-based permission table. Limited but workable for basic delegation. | Large | Basic sharing via token URLs. Full collaboration needs external platform. | Yes - CoWork can write/edit Code.gs and Index.html directly
BUG-04 | No Offline Capability | No | GAS cannot serve offline. PWA service workers not supported in GAS HtmlService. Would require migration to standalone web app. | Very Large | Migrate frontend to standalone hosting (Vercel/Netlify) with GAS as API backend | Limited - CoWork can plan architecture but deployment needs manual setup
IMP-06 | Expand Calendar Integration | Yes | Generate .ics files server-side with GAS. Serve as downloadable blob. Works for all calendar apps. | Small | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
IMP-12 | Document Upload and Storage | Yes | GAS DriveApp creates folders per user. HTML file upload form. Store metadata in Sheets. Link files to actions. | Medium | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-03 | Multi-Child Support Dashboard | Yes | Multiple child profiles in Sheets. Child selector in UI. Separate action plan generation per child. Dashboard aggregation. | Very Large | N/A - fully supported in GAS | Yes - CoWork can write/edit Code.gs and Index.html directly
FEAT-11 | PWA / Offline Mode | No | GAS HtmlService does not support service workers or PWA manifest. Would need to migrate frontend to standalone hosting. | Very Large | Migrate frontend to standalone hosting (Vercel/Netlify) with GAS as API backend | Limited - CoWork can plan architecture but deployment needs manual setup
FEAT-13 | Integration with External Systems | No | External system APIs (school districts, RC) largely don't exist. Where APIs exist, GAS UrlFetchApp could connect. Mostly blocked by lack of partner APIs. | Very Large | Partner APIs largely don't exist. Monitor for future availability. | Limited - CoWork can plan architecture but deployment needs manual setup
SUMMARY
Fully GAS-Compatible | 33 | Can be built entirely in Code.gs + Index.html using CoWork
Partially GAS-Compatible | 6 | Core feature in GAS; some sub-features need external services
Not GAS-Compatible | 4 | Requires platform migration or separate supplemental system

## Priority Roadmap
Priority Rank | Phase | ID | Bucket | Title | Severity | Effort | GAS? | Personas Helped | Why This Rank
1 | Phase 1: Immediate (Weeks 1-4) | BUG-01 | 1. Rights & Process Information | Spanish i18n Only Covers Landing Page | Critical | Medium | Yes | 1, 5 | Highest barrier: 30% of CA population locked out after onboarding. Civil rights issue.
2 | Phase 1: Immediate (Weeks 1-4) | BUG-05 | 1. Rights & Process Information | Diagnosis-to-Eligibility Mapping Errors | Critical | Medium | Yes | 2, 3, 4 | Sends users on months-long wild goose chase to ineligible services. Actively harmful.
3 | Phase 1: Immediate (Weeks 1-4) | BUG-03 | 3. Service Access & Accountability | localStorage-Based Action State with No Persistence | Critical | Large | Yes | All | All users lose all progress on device switch. Destroys trust and weeks of work.
4 | Phase 1: Immediate (Weeks 1-4) | BUG-02 | 2. Advocacy & Conflict Resolution | Fragile Client-Side Email Analysis Regex | Critical | Small | Yes | All | Email misclassification leads to wrong escalation decisions. Quick fix, high impact.
5 | Phase 1: Immediate (Weeks 1-4) | IMP-01 | 1. Rights & Process Information | Add Vietnamese Language Support | High | Medium | Yes | 9 | Vietnamese grandparents at 10-day suspension threshold with zero language support.
6 | Phase 1: Immediate (Weeks 1-4) | IMP-03 | 1. Rights & Process Information | Expand Onboarding to Capture Key Demographics | High | Medium | Yes | 5, 6, 7, 9 | Missing immigration, military, kinship data = wrong action plans for 40% of personas.
7 | Phase 1: Immediate (Weeks 1-4) | BUG-06 | 3. Service Access & Accountability | Profile Save Destructively Regenerates Action Plan | High | Medium | Yes | All | Users avoid updating profile because it destroys progress. Locks users into stale data.
8 | Phase 1: Immediate (Weeks 1-4) | BUG-08 | 2. Advocacy & Conflict Resolution | Check-in Frustration Flow Actions Not Integrated into Dashboard | Medium | Medium | Yes | 1, 3, 5, 7, 9 | Escalation actions vanish after frustration flow. Defeats purpose of crisis support. Multi-child needed by 70% of personas.
8 | Phase 1: Immediate (Weeks 1-4) | IMP-04 | 4. Emotional & Community Support | Multi-Child Support | High | Large | Yes | 1, 2, 3, 4, 5, 6, 8 | Escalation actions vanish after frustration flow. Defeats purpose of crisis support. Multi-child needed by 70% of personas.
9 | Phase 2: Near-Term (Weeks 5-12) | IMP-13 | 2. Advocacy & Conflict Resolution | Expand Draft Generation Templates | High | Medium | Yes | 3, 8, 9, 10 | Missing: PWN request, 4731 complaint, IHSS appeal, MDR challenge. Critical advocacy gaps.
10 | Phase 2: Near-Term (Weeks 5-12) | IMP-19 | 2. Advocacy & Conflict Resolution | Emergency/Crisis Quick-Access | High | Small | Yes | 3, 8, 9 | No fast path during crisis. "My child was expelled" needs same-day response.
11 | Phase 2: Near-Term (Weeks 5-12) | BUG-07 | 3. Service Access & Accountability | No Session Timeout Handling | Medium | Small | Yes | All | Cryptic error on timeout loses mid-session work. Quick fix.
12 | Phase 2: Near-Term (Weeks 5-12) | IMP-02 | 1. Rights & Process Information | Add Tagalog, Mandarin, Cantonese Support | High | Large | Yes | Extended CA population | Covers 65% of non-English CA population. Same architecture as Spanish/Vietnamese.
13 | Phase 2: Near-Term (Weeks 5-12) | IMP-08 | 3. Service Access & Accountability | Add Proactive Notification/Reminder System | High | Medium | Partial | All | Users forget deadlines. Email reminders prevent missed authorization expirations.
14 | Phase 2: Near-Term (Weeks 5-12) | FEAT-02 | 3. Service Access & Accountability | Appointment Tracker with Prep Checklists | High | Large | Yes | 7, 8, 9 | Appointment-heavy personas (8-12/month) need centralized tracker. Document upload essential for appeals.
14 | Phase 2: Near-Term (Weeks 5-12) | IMP-12 | 5. Transition & Life Pathway | Document Upload and Storage | High | Medium | Yes | 3, 8, 10 | Appointment-heavy personas (8-12/month) need centralized tracker. Document upload essential for appeals.
15 | Phase 2: Near-Term (Weeks 5-12) | IMP-10 | 1. Rights & Process Information | Learn More Articles Should Link External Resources | Medium | Small | Yes | All | Most families have multiple children needing separate tracking.
15 | Phase 2: Near-Term (Weeks 5-12) | FEAT-03 | 5. Transition & Life Pathway | Multi-Child Support Dashboard | High | Very Large | Yes | 1, 2, 3, 4, 5, 6, 8 | Most families have multiple children needing separate tracking.
16 | Phase 2: Near-Term (Weeks 5-12) | IMP-15 | 1. Rights & Process Information | Surface Tone Escalation System in Chat UI | Medium | Small | Yes | 3, 8, 10 | Tone escalation is powerful but invisible. Quick UI fix.
17 | Phase 3: Medium-Term (Weeks 13-24) | IMP-05 | 3. Service Access & Accountability | Contextual Quick Actions Grid | Medium | Small | Yes | All | Dynamic quick actions increase engagement and reduce cognitive load.
18 | Phase 3: Medium-Term (Weeks 13-24) | IMP-20 | 1. Rights & Process Information | Regulatory/Procedural Quick-Reference Cards | Medium | Small | Yes | All | Quick-reference cards for IEP timelines, RC deadlines, suspension rules.
19 | Phase 3: Medium-Term (Weeks 13-24) | IMP-21 | 1. Rights & Process Information | Personalized Resource Recommendations | Medium | Medium | Yes | All | Relevant articles surface faster. Reduces information overwhelm.
20 | Phase 3: Medium-Term (Weeks 13-24) | IMP-16 | 1. Rights & Process Information | RC Reimbursable List Should Explain Process | Medium | Small | Yes | 1, 5, 7, 9 | Users don't know HOW to get reimbursed. Process explanation needed.
21 | Phase 3: Medium-Term (Weeks 13-24) | IMP-09 | 3. Service Access & Accountability | Agency Directory Should Filter by User Location | Medium | Small | Yes | 1, 8, 9 | Location-filtered agencies are more actionable than static list.
22 | Phase 3: Medium-Term (Weeks 13-24) | FEAT-08 | 1. Rights & Process Information | Benefit Eligibility Calculator | Medium | Large | Yes | 1, 5, 7, 9 | Families miss benefits they qualify for. Calculator prevents this.
23 | Phase 3: Medium-Term (Weeks 13-24) | FEAT-07 | 2. Advocacy & Conflict Resolution | Advocate and Attorney Directory | Medium | Large | Partial | 2, 3, 8, 10 | Attorney access critical for due process. .ics calendar universal.
23 | Phase 3: Medium-Term (Weeks 13-24) | IMP-06 | 5. Transition & Life Pathway | Expand Calendar Integration | Medium | Small | Yes | All | Attorney access critical for due process. .ics calendar universal.
24 | Phase 3: Medium-Term (Weeks 13-24) | IMP-11 | 3. Service Access & Accountability | Expand Follow-Up Outcome Tracking | Medium | Small | Yes | All | Nuanced outcomes improve follow-up quality.
25 | Phase 3: Medium-Term (Weeks 13-24) | IMP-14 | 3. Service Access & Accountability | Add Progress History and Timeline | Medium | Small | Yes | All | Progress visualization motivates continued engagement.
26 | Phase 4: Long-Term (Weeks 25+) | FEAT-01 | 3. Service Access & Accountability | Document Vault | High | Very Large | Partial | 3, 8, 10 | Document storage + SMS reminders. DriveApp makes this feasible.
26 | Phase 4: Long-Term (Weeks 25+) | IMP-07 | 4. Emotional & Community Support | SMS Reminders Should Be Actual Reminders | Medium | Medium | Partial | 7, 8, 9 | Document storage + SMS reminders. DriveApp makes this feasible.
27 | Phase 4: Long-Term (Weeks 25+) | IMP-18 | 3. Service Access & Accountability | Action Cards Should Show Dependencies | Medium | Small | Yes | All | Action sequencing reduces confusion for complex plans.
28 | Phase 4: Long-Term (Weeks 25+) | FEAT-09 | 1. Rights & Process Information | Military Family Module | Medium | Large | Yes | 6 | Military families (6) have zero content. Niche but critical.
29 | Phase 4: Long-Term (Weeks 25+) | FEAT-04 | 3. Service Access & Accountability | Service Coordination Dashboard | High | Large | Yes | 1, 5, 7, 8, 9 | Service coordination visual reduces appointment/authorization chaos.
30 | Phase 4: Long-Term (Weeks 25+) | FEAT-10 | 3. Service Access & Accountability | Interactive Journey Timeline Visualization | Medium | Medium | Yes | 4, 8 | Journey timeline helps long-term users see progress.
31 | Phase 4: Long-Term (Weeks 25+) | IMP-17 | 4. Emotional & Community Support | Action Plan Sharing with Co-Parents/Advocates | Medium | Medium | Partial | 2, 4, 6 | Co-parent sharing basic but valuable.
32 | Phase 4: Long-Term (Weeks 25+) | IMP-22 | 4. Emotional & Community Support | Mobile Responsiveness and Accessibility Audit | Medium | Medium | Yes | All | WCAG compliance is legal requirement for publicly-funded tools.
33 | Phase 4: Long-Term (Weeks 25+) | FEAT-06 | 4. Emotional & Community Support | Persistent Chat History | Medium | Medium | Yes | 2, 3, 8 | Chat history persistence. Already have ChatSessions sheet.
34 | Phase 4: Long-Term (Weeks 25+) | FEAT-12 | 4. Emotional & Community Support | Family Delegation and Account Sharing | Medium | Large | Partial | 2, 5, 6, 7, 9 | Family delegation complex but important for kinship/military.
35 | Phase 4: Long-Term (Weeks 25+) | FEAT-05 | 4. Emotional & Community Support | Peer Connection Network | Medium | Very Large | No | 1, 5, 7, 9 | Peer connection transformative but exceeds GAS capabilities.
36 | Phase 4: Long-Term (Weeks 25+) | BUG-04 | 5. Transition & Life Pathway | No Offline Capability | High | Very Large | No | 7, 8 | Offline mode critical for rural but requires platform migration.
37 | Phase 4: Long-Term (Weeks 25+) | FEAT-11 | 5. Transition & Life Pathway | PWA / Offline Mode | High | Very Large | No | 7, 8 | PWA requires leaving GAS. Plan for future.
38 | Phase 4: Long-Term (Weeks 25+) | FEAT-13 | 5. Transition & Life Pathway | Integration with External Systems | Medium | Very Large | No | All | External APIs don't exist yet. Monitor.

## Cross-Cutting Themes
Theme # | Theme Name | Mapped Memo Bucket(s) | Description | Related Finding IDs | Affected Personas | GAS Feasible? | Recommended Action
1 | Language Access Barriers | 1. Rights & Process Info | Spanish-only landing creates illusion of accessibility. Vietnamese, Tagalog, Mandarin, Cantonese speakers have zero access. 30%+ of CA population affected. | BUG-01, IMP-01, IMP-02 | 1, 5, 9 + extended CA | Yes | Full i18n implementation: EN, ES, VI minimum. Add TL, ZH in Phase 2.
2 | Data Persistence Failures | 3. Service Access | localStorage-only = device switch kills progress. No offline mode = rural users lose work. No session timeout handling. | BUG-03, BUG-04, BUG-07 | All 10 | Yes (persistence), No (offline) | Server-side sync to Sheets immediately. PWA requires platform migration.
3 | Diagnosis-to-Service Mapping | 1. Rights & Process Info | Action plans don't filter by diagnosis eligibility. ADHD→RC (wrong). Autism+normal IQ→RC denied (wrong). SLD gets minimal content. | BUG-05 | 2, 3, 4 | Yes | Build eligibility matrix in Code.gs. Filter generateRichPlan() output.
4 | Appointment/Service Coordination | 3. Service Access | Parents juggle 8+ appointments/month across RC, school, medical, therapy. No tracker, reminders, prep checklists. | FEAT-02, FEAT-04, IMP-08 | 7, 8, 9 | Yes | Appointment tracker + service dashboard + email reminders via GAS triggers.
5 | Escalation & Advocacy Navigation | 2. Advocacy & Conflict | Frustration flows generate actions that vanish. Missing draft templates for key complaints. Crisis mode absent. Tone escalation hidden. | BUG-08, IMP-13, IMP-15, IMP-19 | 3, 8, 9, 10 | Yes | Integrate frustration actions into dashboard. Add draft templates. Surface tone toggle.
6 | Demographic Blindness | 1. Rights & Process Info | Onboarding misses immigration, military, kinship, rural, language, family structure. Produces generic plans for diverse populations. | IMP-03, FEAT-09 | 5, 6, 7, 9 | Yes | Expand onboarding. Use demographics to customize plan generation and resource filtering.
7 | Multi-Child / Family Complexity | 4. Emotional & Community | Single-child assumption. 70% of personas have siblings. No way to track multiple children or share with co-parents. | IMP-04, FEAT-03, IMP-17, FEAT-12 | 1, 2, 3, 4, 5, 6, 8 | Yes (multi-child), Partial (sharing) | Add child profiles in Sheets. Separate action plans. Basic sharing via token URLs.
8 | SLD / Non-Autism Underrepresentation | 1. Rights & Process Info | SLD is largest SpEd category (35%) but app treats it as minor. No evidence-based reading content, no RTI delay proactive surfacing. | BUG-05, IMP-21 | 3, 4 | Yes | Add SLD-specific KB articles. Surface RTI delay info proactively. Add reading program guidance.
9 | Rural Service Delivery Gaps | 3. Service Access | Rural users face provider deserts, long travel, unreliable internet. App doesn't address telehealth options or rural-specific strategies. | BUG-04, FEAT-11 | 7, 8 | Partial | Add telehealth provider info. Rural strategy content. Offline requires platform migration.
10 | Trust & Safety for Vulnerable Populations | 4. Emotional & Community | Undocumented families fear government contact. Grandparent caregivers unsure of standing. Young single parents feel judged. No reassurance content. | IMP-03, FEAT-05 | 5, 7, 9 | Yes | Add immigration safety assurances. Kinship care rights content. Peer support (needs external platform).