## Master Action Items
WAYPOINT GTM — MASTER ACTION ITEMS
# | Phase | Week | Track | Action Item | Deliverable | Owner | Est Hours | Priority | Status | Notes
PHASE 0: PRE-LAUNCH FOUNDATION (Weeks 1–4)
Week 1: Infrastructure & Landing Page
1 | Phase 0 | Wk 1 | Ops | Register California LLC — file Articles of Organization online | LLC filing confirmation | Mike | 2 | P0 |  | CA Secretary of State ~$70
2 | Phase 0 | Wk 1 | Ops | Purchase domain (waypointfamilies.com or waypointnavigator.ai) | Domain registered + DNS configured | Mike | 1 | P0 |  | Namecheap or Cloudflare
3 | Phase 0 | Wk 1 | Ops | Set up Google Workspace (mike@waypoint.app) + business email | Email working | Mike | 1 | P0 |  | $7/mo
4 | Phase 0 | Wk 1 | Ops | Set up Vercel hosting + connect domain + SSL | waypointfamilies.com resolves | Mike | 1 | P0 |  | Free tier sufficient
5 | Phase 0 | Wk 1 | Ops | Apply for Apple Developer Program ($99/yr) | Apple Dev account pending | Mike | 1 | P0 |  | 24-48hr approval
6 | Phase 0 | Wk 1 | Dev | Deploy landing page to production (from React mockup) | Landing page live at production URL | Mike | 4 | P0 |  | GH Issue #1
7 | Phase 0 | Wk 1 | Dev | Set up Supabase project: org, project, pgvector extension | Supabase dashboard accessible | Mike | 2 | P0 | Complete | GH Issue #2
8 | Phase 0 | Wk 1 | Dev | Build waitlist email capture + connect to Supabase | Email signups stored in DB | Mike | 3 | P0 |  | GH Issue #3
9 | Phase 0 | Wk 1 | Dev | Set up Google Analytics + Plausible analytics | Traffic tracking live | Mike | 1 | P0
10 | Phase 0 | Wk 1 | Dev | Integrate email service (ConvertKit or Resend) for automation | Email platform connected | Mike | 2 | P0
11 | Phase 0 | Wk 1 | Marketing | Create Instagram account (@waypointfamilies) + bio + first 3 posts | IG account live, 3 posts scheduled | Mike | 2 | P1 |  | Problem-awareness focus, not product
12 | Phase 0 | Wk 1 | Marketing | Create Facebook page + LinkedIn company page | Social accounts live | Mike | 1 | P1
13 | Phase 0 | Wk 1 | Marketing | Join 15–20 CA parent FB groups (autism, ADHD, Down syndrome, special needs, IEP help) | Joined 15+ groups, introduce yourself | Mike | 2 | P1 |  | Provide value 2+ weeks before sharing Waypoint
14 | Phase 0 | Wk 1 | Partnerships | Identify 50 Bay Area therapy practices, pediatric offices, dev pediatricians | Outreach list in spreadsheet | Mike | 3 | P1 |  | ABA, OT/PT, speech, behavioral health
Week 2: Email Automation & App Scaffold
15 | Phase 0 | Wk 2 | Dev | Build 4-email welcome sequence: Confirmation → Day 3 Entity preview → Day 7 Founder story → Day 14 Early access | Email sequence live + tested | Mike | 4 | P0 |  | GH Issue #4
16 | Phase 0 | Wk 2 | Dev | Initialize Expo project (TypeScript) + monorepo setup | Expo app runs on simulator | Mike | 2 | P0 | Complete | GH Issue #5
17 | Phase 0 | Wk 2 | Dev | Configure Supabase Auth: email/password + Apple Sign-In + Google OAuth | Auth flow working in Expo | Mike | 3 | P0 | Complete | GH Issue #6
18 | Phase 0 | Wk 2 | Dev | Design database schema v1: families, children, diagnoses, services, documents, expenses | SQL migration committed | Mike | 4 | P0 | Complete | GH Issue #7
19 | Phase 0 | Wk 2 | Dev | Set up Row Level Security policies: families see only their data | RLS policies tested | Mike | 2 | P0 | Complete | GH Issue #8
20 | Phase 0 | Wk 2 | Content | Draft first 2 entity guides: Regional Center Complete Guide + IEP Rights & Process | 2 guides in draft (2,000–3,000 words each) | Mike | 6 | P0 |  | SEO-optimized, cite specific legal provisions
21 | Phase 0 | Wk 2 | Content | Plan 4 blog posts for Phase 0 | Blog content calendar | Mike | 1 | P1
22 | Phase 0 | Wk 2 | Marketing | Post 5 problem-awareness posts on social (IG + FB page) | 5 posts live | Mike | 2 | P1 |  | 'Did you know families interact with 23+ agencies?'
23 | Phase 0 | Wk 2 | Marketing | Begin providing genuine value in FB parent groups — answer questions, share tips | Active in 10+ groups | Mike | 3 | P1 |  | Never spam. Build trust first.
24 | Phase 0 | Wk 2 | Partnerships | Research RCEB vendor process and POS code requirements | Vendor process documented | Mike | 2 | P1 |  | POS 371 + 331
Week 3: AI Navigator MVP + Content
25 | Phase 0 | Wk 3 | Dev | Build onboarding flow: Welcome → Add Child → Diagnosis → State/RC → Insurance → Done (6 screens) | 6 onboarding screens navigable | Mike | 6 | P0 | Complete | GH Issue #9
26 | Phase 0 | Wk 3 | Dev | Connect onboarding to Supabase: write family + child profiles to DB | Data persists after onboarding | Mike | 3 | P0 | Complete | GH Issue #10
27 | Phase 0 | Wk 3 | Dev | Build AI Navigator: chunk Entity Matrix + legal docs into pgvector embeddings | KB indexed in pgvector | Mike | 4 | P0 | Complete | GH Issue #11
28 | Phase 0 | Wk 3 | Dev | Build chat interface + connect Claude API with system prompt + RAG context | AI Navigator responds to questions | Mike | 5 | P0 | Complete | GH Issue #12
29 | Phase 0 | Wk 3 | Dev | Build benefits checker: diagnosis → program eligibility list | Eligibility results display correctly | Mike | 4 | P0 | Not Started | GH Issue #13
30 | Phase 0 | Wk 3 | Content | Publish 2 entity guides (RC + IEP) on website | 2 guides live with SEO metadata | Mike | 3 | P0
31 | Phase 0 | Wk 3 | Content | Draft 2 more entity guides: SSI Application Step-by-Step + IHSS Application Guide | 2 guides in draft | Mike | 5 | P1
32 | Phase 0 | Wk 3 | Content | Publish blog #1: 'Complete Guide to Regional Center Services in 2026' | Blog post live | Mike | 3 | P1
33 | Phase 0 | Wk 3 | Marketing | Soft-launch landing page to personal network (50 contacts). Collect feedback. | 50 people see landing page, feedback collected | Mike | 2 | P1
34 | Phase 0 | Wk 3 | Partnerships | Draft RC one-pager: Waypoint overview + POS code justification + pilot proposal | One-pager PDF ready | Mike | 3 | P1 |  | Cite Lanterman Act §4648, §4685
Week 4: App Polish + Content + TestFlight
35 | Phase 0 | Wk 4 | Dev | Build home dashboard with 'Your Next Waypoint' proactive recommendation | Dashboard shows personalized next steps | Mike | 4 | P0 | Complete | GH Issue #14
36 | Phase 0 | Wk 4 | Dev | Build document vault (upload, categorize, store in Supabase Storage) | Documents upload + retrieve correctly | Mike | 4 | P0 | Complete | GH Issue #15
37 | Phase 0 | Wk 4 | Dev | Build expense tracker (log expenses, categorize by funding source) | Expenses save + display | Mike | 3 | P0 | Not Started | GH Issue #16
38 | Phase 0 | Wk 4 | Dev | Build provider directory (add/edit therapists, RC coordinator, school contacts) | Provider contacts save + display | Mike | 3 | P0 | Not Started | GH Issue #17
39 | Phase 0 | Wk 4 | Dev | Full QA across iPhone + Android simulator. Fix critical bugs. | No P0 bugs remaining | Mike | 4 | P0 | Not Started
40 | Phase 0 | Wk 4 | Dev | First TestFlight build — internal testing | TestFlight build live | Mike | 2 | P0 | Not Started
41 | Phase 0 | Wk 4 | Content | Publish 3 entity guides (SSI, IHSS, Medi-Cal for Children) | 5 total guides live | Mike | 6 | P0 |  | Exit criteria: 5 guides
42 | Phase 0 | Wk 4 | Content | Publish blog #2: 'Understanding Your IEP Rights in California' | Blog post live | Mike | 3 | P1
43 | Phase 0 | Wk 4 | Content | Draft 3 diagnosis landing pages: Autism, Down Syndrome, ADHD | 3 diagnosis pages in draft | Mike | 4 | P1 |  | Use Journey Map content from mockup
44 | Phase 0 | Wk 4 | Marketing | Share landing page in 5 FB groups (authentic, value-add post) | 5 group posts with link | Mike | 2 | P0
45 | Phase 0 | Wk 4 | Marketing | Launch email welcome sequence (activate automation) | Sequence sending to new signups | Mike | 1 | P0 |  | Test on personal email first
46 | Phase 0 | Wk 4 | Marketing | 3 more social posts: tips + founder story | 8+ total posts | Mike | 2 | P1
47 | Phase 0 | Wk 4 | Partnerships | Cold email 10 therapy practices with intro + Waypoint overview | 10 emails sent, track responses | Mike | 2 | P1
PHASE 1: SOFT LAUNCH & VALIDATION (Weeks 5–8)
Week 5: Beta Recruitment & Launch
48 | Phase 1 | Wk 5 | Dev | Beta onboarding: welcome 25–50 families. Monitor usage. Fix critical bugs daily. | 25+ families on TestFlight | Mike | 6 | P0 |  | White-glove support for every user
49 | Phase 1 | Wk 5 | Dev | Set up analytics dashboard: activation rate, session count, features used | Analytics dashboard live | Mike | 3 | P0 |  | Supabase + custom queries
50 | Phase 1 | Wk 5 | Dev | Build feedback mechanism: in-app thumbs up/down on AI responses | Feedback logging to Supabase | Mike | 2 | P0 |  | GH Issue #18
51 | Phase 1 | Wk 5 | Marketing | Beta recruitment email to waitlist: 'You're invited to early access' | Recruitment emails sent, 60% from waitlist | Mike | 2 | P0 |  | Personal email, not blast
52 | Phase 1 | Wk 5 | Marketing | Post in 5+ FB groups: 'Dad building app, looking for 10 parents to try it' | 5 group posts, 25% of beta from groups | Mike | 2 | P0 |  | Authentic ask, not marketing
53 | Phase 1 | Wk 5 | Marketing | Instagram: founder story series (3 posts about why you're building Waypoint) | 3 story posts live | Mike | 2 | P1
54 | Phase 1 | Wk 5 | Content | Publish 3 diagnosis landing pages (Autism, Down Syndrome, ADHD) | 3 diagnosis pages live | Mike | 4 | P0
55 | Phase 1 | Wk 5 | Content | Publish blog #3: '2026 Federal Policy Changes for Disability Families' | Blog post live | Mike | 3 | P1
56 | Phase 1 | Wk 5 | Partnerships | Reach out to 10 therapy practices: 'We built a free tool for your clients' families' | 10 outreach emails/calls, 3 calls scheduled | Mike | 3 | P1 |  | 15% of beta from provider referrals
57 | Phase 1 | Wk 5 | Equity | Build equity pricing model: free tier for Medi-Cal, RC-referred, and income-qualified families | Pricing logic documented + implemented | Mike | 3 | P0 |  | See Equity Pricing sheet
Week 6: Iterate & Improve
58 | Phase 1 | Wk 6 | Dev | Iterate on AI Navigator based on beta feedback. Improve response quality. | Top 5 issues fixed, response quality improved | Mike | 6 | P0 |  | Review every low-rated response
59 | Phase 1 | Wk 6 | Dev | Add 3 most-asked topics to KB based on beta questions | KB expanded with new content | Mike | 3 | P0
60 | Phase 1 | Wk 6 | Dev | Implement equity verification: Medi-Cal CIN check, RC referral code, income attestation | Equity access flow working | Mike | 4 | P0 |  | GH Issue #19
61 | Phase 1 | Wk 6 | Marketing | Day 7 NPS survey to beta users. Collect testimonials. | NPS score calculated, 3+ testimonials | Mike | 2 | P0 |  | Target NPS > 50
62 | Phase 1 | Wk 6 | Marketing | Social: share beta user quote (with permission) | 1 testimonial post | Mike | 1 | P1
63 | Phase 1 | Wk 6 | Content | Publish 2 entity guides: CCS + CalABLE | 7 total guides live | Mike | 5 | P1
64 | Phase 1 | Wk 6 | Content | Publish blog #4: 'What Is the Self-Determination Program?' | Blog post live | Mike | 3 | P1
65 | Phase 1 | Wk 6 | Partnerships | Meet with 2–3 therapy practices. Propose referral partnership. | 2+ meetings completed | Mike | 3 | P1
Week 7: Retention & WTP Testing
66 | Phase 1 | Wk 7 | Dev | Build 'Next Steps' engine: proactive recommendations based on profile + completed actions | Personalized next waypoints showing | Mike | 6 | P0 |  | GH Issue #20 — the quarterback moment
67 | Phase 1 | Wk 7 | Dev | Push notifications: deadline alerts, next waypoint reminders | Notifications working on iOS | Mike | 3 | P0 |  | GH Issue #21
68 | Phase 1 | Wk 7 | Dev | In-app feedback form + bug reporting | Feedback form accessible from every screen | Mike | 2 | P1
69 | Phase 1 | Wk 7 | Marketing | Day 14 WTP survey: 'Would you pay $9.99/mo for this? What features matter most?' | WTP data collected from 20+ users | Mike | 2 | P0 |  | Target > 40% yes
70 | Phase 1 | Wk 7 | Marketing | Re-engagement email to inactive beta users | Reactivation emails sent | Mike | 1 | P1
71 | Phase 1 | Wk 7 | Marketing | Social: tips from beta learnings (3 posts) | 3 posts live | Mike | 2 | P1
72 | Phase 1 | Wk 7 | Content | Draft 3 more entity guides (Section 504, DOR, Self-Determination) | 3 guides in draft | Mike | 5 | P1
73 | Phase 1 | Wk 7 | Partnerships | Research RCEB vendor requirements. Draft pilot proposal. | Pilot proposal draft complete | Mike | 3 | P1 |  | 20 families, 3 months, $100/user/mo
Week 8: App Store Prep & Decision Gate
74 | Phase 1 | Wk 8 | Dev | Polish app for App Store: screenshots (6.7" + 6.5"), app preview video (30s), privacy labels | App Store submission package ready | Mike | 5 | P0 | Partial
75 | Phase 1 | Wk 8 | Dev | Submit to App Review with notes explaining AI Navigator | App submitted to Apple | Mike | 2 | P0 | Not Started
76 | Phase 1 | Wk 8 | Dev | Build Spanish language toggle for core UI (Phase 2 prep) | Spanish strings file started | Mike | 3 | P1 | Complete | Equity: CA's largest non-English group
77 | Phase 1 | Wk 8 | Marketing | Phase 1 → 2 decision gate review: NPS, retention, WTP | Go/no-go decision documented | Mike | 2 | P0 |  | GREEN: NPS>50, ret>30%, WTP>40%
78 | Phase 1 | Wk 8 | Marketing | Plan App Store launch campaign: emails, social, personal outreach | Launch plan document | Mike | 2 | P1
79 | Phase 1 | Wk 8 | Content | Publish remaining entity guides (target 10 total) | 10 entity guides live | Mike | 6 | P0
80 | Phase 1 | Wk 8 | Content | Publish 3 more diagnosis pages (CP, Epilepsy, ID) | 6 diagnosis pages live | Mike | 4 | P1
81 | Phase 1 | Wk 8 | Partnerships | Submit RCEB pilot proposal. Follow up with therapy practice partners. | Proposal submitted, 2+ practice partnerships active | Mike | 3 | P1
82 | Phase 1 | Wk 8 | Equity | Publish equity commitment page on website: 'Waypoint is free for families who need it most' | Equity page live, linked from pricing | Mike | 2 | P0
PHASE 2: GROWTH & CONTENT MOAT (Weeks 9–16)
Week 9–10: App Store Launch
83 | Phase 2 | Wk 9 | Dev | App Store launch + Google Play launch (Expo EAS) | App live on both stores | Mike | 4 | P0
84 | Phase 2 | Wk 9 | Dev | Implement subscription infrastructure: Apple IAP + Google Play Billing | Subscription purchase flow working | Mike | 6 | P0 |  | GH Issue #22
85 | Phase 2 | Wk 9 | Dev | Build equity access flow: Medi-Cal verification, RC referral codes, income attestation → auto-grant free access | Equity users get full access automatically | Mike | 4 | P0 |  | GH Issue #23
86 | Phase 2 | Wk 10 | Dev | Build RC referral tracking: unique codes per RC, usage analytics | RC can see how many families they referred | Mike | 3 | P0 |  | GH Issue #24
87 | Phase 2 | Wk 9 | Marketing | Launch announcement: email full waitlist + social + personal outreach to 20 most engaged beta users | Launch emails sent, 15+ App Store reviews requested | Mike | 3 | P0 |  | Target 15+ 5-star reviews in first week
88 | Phase 2 | Wk 9 | Content | Publish 5 new entity guides: CCS, CalABLE, SDP, DOR, Section 504 | 15 entity guides live | Mike | 6 | P0
89 | Phase 2 | Wk 10 | Content | Publish 4 diagnosis pages: Cerebral Palsy, Epilepsy, Intellectual Disability, Multiple Disabilities | 10 diagnosis pages live (all 7 from mockup + 3 more) | Mike | 6 | P0
90 | Phase 2 | Wk 10 | Marketing | ASO: optimize title, keywords, subtitle for discoverability | ASO implemented | Mike | 2 | P0 |  | 'Waypoint — Disability Services Navigator'
91 | Phase 2 | Wk 10 | Equity | Partner with 2+ community orgs serving BIPOC disability families for distribution | Partnership agreements in place | Mike | 4 | P0 |  | FRCs, DREDF, community health centers
Week 11–12: Tools & Viral Loops
92 | Phase 2 | Wk 11 | Dev | Build interactive RC lookup tool (by county/zip) | RC lookup live on website | Mike | 4 | P0 |  | GH Issue #25
93 | Phase 2 | Wk 11 | Dev | Build IEP rights quiz ('Do You Know Your Rights?') | Quiz live, shareable results | Mike | 3 | P0 |  | GH Issue #26
94 | Phase 2 | Wk 12 | Dev | Build full eligibility checker (all diagnoses × entities) with shareable results | Checker live, generates OG share images | Mike | 5 | P0 |  | GH Issue #27
95 | Phase 2 | Wk 12 | Dev | Implement referral program: 'Give a month, get a month' with unique codes | Referral system working end-to-end | Mike | 4 | P0 |  | GH Issue #28
96 | Phase 2 | Wk 11 | Content | Blog: 'The 10 IEP Rights Every Parent Should Know' | Blog post live | Mike | 3 | P1
97 | Phase 2 | Wk 12 | Content | Blog: 'Your Regional Center: What They Must Provide' | Blog post live | Mike | 3 | P1
98 | Phase 2 | Wk 11 | Marketing | Promote RC lookup tool across all FB groups + social | Tool shared in 10+ groups | Mike | 2 | P0
99 | Phase 2 | Wk 12 | Marketing | Promote eligibility checker: 'Your child may be eligible for 14 programs. Find out.' | Viral share campaign launched | Mike | 2 | P0 |  | Share URL with OG images
100 | Phase 2 | Wk 12 | Equity | Implement Spanish language support for eligibility checker + RC lookup tools | Tools available in Spanish | Mike | 4 | P0 |  | Equity: reach non-English families
Week 13–14: Community & Age Tools
101 | Phase 2 | Wk 13 | Dev | Build age milestone timeline tool | Timeline tool live on website | Mike | 4 | P1 |  | GH Issue #29
102 | Phase 2 | Wk 13 | Dev | Build expense calculator by diagnosis | Calculator live | Mike | 3 | P1 |  | GH Issue #30
103 | Phase 2 | Wk 14 | Dev | Build provider co-marketing pages: 'yourpractice.waypoint.app' | White-label pages for partners | Mike | 4 | P1 |  | GH Issue #31
104 | Phase 2 | Wk 13 | Marketing | Recruit parent advisory board (5–8 beta power users) | Advisory board formed, first call scheduled | Mike | 3 | P0 |  | Monthly calls, title + recognition
105 | Phase 2 | Wk 13 | Marketing | Launch private community (FB group or Discord) for Waypoint families | Community live, 25+ members | Mike | 2 | P1
106 | Phase 2 | Wk 14 | Content | Blog: 'What to Expect at Every Age: A Disability Family Timeline' | Blog post live | Mike | 3 | P1
107 | Phase 2 | Wk 14 | Content | Blog: 'The True Cost of Raising a Child with Disabilities' | Blog post live | Mike | 3 | P1 |  | Media pitch angle
108 | Phase 2 | Wk 13 | Partnerships | Present Waypoint at first SELPA conference or RC family event | Presentation delivered, leads collected | Mike | 4 | P1 |  | $200–500/event
109 | Phase 2 | Wk 14 | Equity | Publish 'Waypoint Para Familias' — full Spanish language marketing page | Spanish landing page live | Mike | 3 | P0
Week 15–16: Content Moat & Scale Prep
110 | Phase 2 | Wk 15 | Dev | Build IEP upload + AI review feature (MVP): upload IEP, AI flags gaps | IEP review feature in beta | Mike | 8 | P0 |  | GH Issue #32 — press-worthy feature
111 | Phase 2 | Wk 16 | Dev | Build insurance appeal letter generator (MVP) | Appeal generator in beta | Mike | 6 | P0 |  | GH Issue #33
112 | Phase 2 | Wk 15 | Content | Resource roundup: 'Every Program Your Family Needs in One Place' | Comprehensive resource page live | Mike | 4 | P1
113 | Phase 2 | Wk 16 | Content | Social sharing optimization: OG images, meta descriptions for all pages | All pages optimized for social sharing | Mike | 3 | P1
114 | Phase 2 | Wk 15 | Marketing | Invite parents to write guest posts: 'How I Got IHSS Approved' | 2+ guest posts scheduled | Mike | 2 | P1 |  | Co-create content with community
115 | Phase 2 | Wk 16 | Marketing | Phase 2 → 3 decision gate: 1K+ downloads, 25K organic visitors, community forming | Go/no-go decision documented | Mike | 2 | P0
116 | Phase 2 | Wk 16 | Partnerships | Follow up with RCEB on pilot proposal. Prepare for meeting. | RCEB meeting scheduled or proposal status known | Mike | 3 | P1
117 | Phase 2 | Wk 16 | Equity | Track equity access metrics: % users on free tier, demographics, geographic distribution | Equity dashboard created | Mike | 2 | P0 |  | Report to advisory board
PHASE 3: MONETIZATION & RC CHANNEL (Weeks 17–26)
Week 17–20: Subscriptions + RC Pilot
118 | Phase 3 | Wk 17 | Dev | Launch paid subscriptions: Free, Plus ($9.99/mo), Pro ($19.99/mo) | Subscription tiers live + billing working | Mike | 4 | P0 |  | Apple Small Business Program 15%
119 | Phase 3 | Wk 17 | Dev | Implement equity access: auto-grant Plus to Medi-Cal, RC-referred, and income-qualified users | Equity users get Plus features at no cost | Mike | 3 | P0 |  | GH Issue #34
120 | Phase 3 | Wk 18 | Dev | Build RC admin dashboard: family count, usage metrics, outcome reports | RC-facing dashboard live | Mike | 5 | P0 |  | GH Issue #35
121 | Phase 3 | Wk 19 | Dev | Financial planning dashboard: CalABLE guidance, SNT vs ABLE, tax deductions | Financial tools in beta | Mike | 5 | P1 |  | GH Issue #36
122 | Phase 3 | Wk 20 | Dev | Launch provider directory: searchable DB with free + paid ($99–299/mo) listings | Directory live on website + in app | Mike | 5 | P0 |  | GH Issue #37
123 | Phase 3 | Wk 17 | Marketing | Convert beta users: offer 3 months free Plus, personal email | Conversion campaign sent, target 30–40% conversion | Mike | 3 | P0
124 | Phase 3 | Wk 18 | Marketing | Push annual plans aggressively (25% discount) | Annual plan messaging in app + email | Mike | 2 | P0 |  | Reduces churn dramatically
125 | Phase 3 | Wk 19 | Marketing | PR pitch to local media: 'Oakland dad builds AI platform to help disability families' | 3+ media pitches sent | Mike | 3 | P1 |  | SF Chronicle, East Bay Times, Disability Scoop
126 | Phase 3 | Wk 20 | Marketing | Launch paid social ads ($500–1K/mo): target CA parents with disability interests | Ad campaigns live on FB/IG | Mike | 3 | P1 |  | Only if CAC < $30
127 | Phase 3 | Wk 18 | Partnerships | RCEB pilot kickoff: onboard 20 families, weekly check-ins with RC contact | 20 families active in pilot | Mike | 4 | P0 |  | White-glove support
128 | Phase 3 | Wk 20 | Partnerships | Sales outreach to 50 Bay Area therapy practices for directory listings | 10+ practices contacted, 3+ paid listings | Mike | 4 | P0 |  | $99–299/mo per listing
129 | Phase 3 | Wk 19 | Equity | Launch Community Navigator volunteer program: trained parents help new families | 5+ volunteer navigators recruited | Mike | 3 | P0 |  | Parents who've been through the system
130 | Phase 3 | Wk 20 | Equity | Build BIPOC Family Resource Hub: culturally competent guides in 4 languages | Hub page live with 10+ resources | Mike | 4 | P0 |  | English, Spanish, Mandarin, Vietnamese
Week 21–26: Scale Revenue + Expand
131 | Phase 3 | Wk 21 | Dev | Multi-language support MVP: Spanish UI + AI responses | Spanish language toggle working | Mike | 6 | P0 |  | GH Issue #38
132 | Phase 3 | Wk 22 | Dev | Transition planning module: 14+ age guidance, DOR, conservatorship vs SDM | Transition module in beta | Mike | 5 | P1 |  | GH Issue #39
133 | Phase 3 | Wk 23 | Dev | RC reimbursement request drafter: auto-generate POS reimbursement forms | Reimbursement drafter working | Mike | 4 | P0 |  | GH Issue #40
134 | Phase 3 | Wk 24 | Dev | Email action drafting: AI writes emails to RC, school district, insurer — parent reviews + sends | Email drafter working end-to-end | Mike | 6 | P0 |  | GH Issue #41 — the quarterback feature
135 | Phase 3 | Wk 25 | Dev | IEP redlining feature: upload IEP, AI reviews goals, suggests modifications, drafts parent concerns | IEP redlining in beta | Mike | 8 | P0 |  | GH Issue #42
136 | Phase 3 | Wk 22 | Marketing | Conference presentations: 2+ events (SELPA, RC family, disability expo) | 2 presentations delivered | Mike | 4 | P1
137 | Phase 3 | Wk 24 | Marketing | Email campaign: 'New feature: AI drafts your emails to the school district' | Feature announcement email sent | Mike | 2 | P0
138 | Phase 3 | Wk 26 | Marketing | Phase 3 → 4 gate: 200+ paid subs, 3+ RC approvals, $3K+ MRR | Go/no-go decision + metrics report | Mike | 3 | P0
139 | Phase 3 | Wk 23 | Partnerships | RCEB pilot results presentation. Propose scaling to 50–100 families. | Results presented, expansion decision | Mike | 4 | P0
140 | Phase 3 | Wk 24 | Partnerships | Approach San Andreas RC + Alta California RC with RCEB pilot data | 2 new RC conversations started | Mike | 4 | P0
141 | Phase 3 | Wk 25 | Partnerships | Partner with 1+ ABA provider network for co-distribution | Partnership agreement signed | Mike | 4 | P1 |  | Single partnership can drive 100+ signups
142 | Phase 3 | Wk 26 | Equity | Quarterly equity report: % free-tier users, BIPOC reach, language coverage, geographic equity | Report published to website + advisory board | Mike | 3 | P0 |  | Transparency builds trust
PHASE 4: SCALE & MARKET LEADERSHIP (Weeks 27–52)
Months 7–9: Accelerate Growth
143 | Phase 4 | Mo 7 | Dev | Build Waypoint API for partner integrations (RC systems, EHR) | API v1 documented + live | Mike | 8 | P1
144 | Phase 4 | Mo 7 | Dev | Performance optimization: caching, RAG improvements, reduce AI latency | AI response time < 3 seconds | Mike | 4 | P1
145 | Phase 4 | Mo 8 | Dev | Multi-child support: families manage multiple children's services in one account | Multi-child feature live | Mike | 5 | P0
146 | Phase 4 | Mo 8 | Dev | Mandarin + Vietnamese UI translations | 3 non-English languages supported | Mike | 6 | P0 |  | Equity priority
147 | Phase 4 | Mo 9 | Dev | SOC 2 Type II preparation: security audit, policy documentation | SOC 2 readiness assessment complete | Mike | 8 | P1 |  | Required for enterprise
148 | Phase 4 | Mo 7 | Marketing | Content authority push: 4+ articles/week, guest posting on disability blogs | Waypoint #1 for 5+ target keywords | Mike | 6 | P0
149 | Phase 4 | Mo 8 | Marketing | Press coverage: pitch to The Mighty, Disability Scoop, Understood | 2+ media placements | Mike | 3 | P1
150 | Phase 4 | Mo 9 | Marketing | Hire first employee: part-time content/community manager | First hire onboarded | Mike | 4 | P0 |  | $3K–5K/mo, prioritize BIPOC candidates
151 | Phase 4 | Mo 7 | Partnerships | Expand RC partnerships: target 5+ by end of Month 9 | 3+ new RC conversations, 2+ agreements | Mike | 6 | P0
152 | Phase 4 | Mo 8 | Partnerships | Community Navigator program: 15+ trained volunteer parents | Navigators active, helping 50+ families | Mike | 4 | P0 |  | Equity multiplier
153 | Phase 4 | Mo 9 | Equity | Grant applications: apply to 3+ disability/health equity foundations | 3 applications submitted | Mike | 4 | P1 |  | Fund equity access expansion
Months 10–12: Enterprise Prep & Profitability
154 | Phase 4 | Mo 10 | Dev | Employer benefits module: company admin dashboard, bulk enrollment | Employer module in beta | Mike | 8 | P1 |  | Year 2 revenue channel
155 | Phase 4 | Mo 11 | Dev | School district portal: parent-facing IEP support branded for district | District portal MVP | Mike | 6 | P1
156 | Phase 4 | Mo 12 | Dev | Full platform audit: security, performance, accessibility (WCAG AA) | Audit report + fixes complete | Mike | 6 | P0
157 | Phase 4 | Mo 10 | Marketing | Weekly 'Office Hours' AMAs with special ed attorneys, RC coordinators, tax pros | 4+ AMAs hosted, recorded as content | Mike | 4 | P1
158 | Phase 4 | Mo 11 | Marketing | Annual report: impact metrics, families served, money recovered, equity data | Impact report published | Mike | 4 | P0 |  | Use for fundraising + press
159 | Phase 4 | Mo 12 | Marketing | Phase 4 → 5 gate: 2K+ paid subs, 10+ RC partnerships, $25K+ MRR | Fundraise decision + metrics package | Mike | 3 | P0
160 | Phase 4 | Mo 10 | Partnerships | Pitch to 3+ large CA employers (Kaiser, Google, State of CA) as benefits partner | 3+ employer conversations started | Mike | 4 | P1 |  | $5–10/employee/mo
161 | Phase 4 | Mo 11 | Partnerships | Partner with 2+ pediatric hospitals (UCSF, Children's Oakland) | Hospital referral partnerships | Mike | 4 | P1 |  | Diagnosis → Waypoint referral
162 | Phase 4 | Mo 12 | Equity | Year-end equity audit: % free users, demographic analysis, language equity, underserved RC coverage | Annual equity report published | Mike | 3 | P0 |  | Public accountability

## Marketing Strategy
WAYPOINT MARKETING STRATEGY — CHANNEL PLAYBOOK
Channel | Phase | Cost/Month | Est. Conv % | Est. Volume | Target CAC | Actions | Equity Impact
ORGANIC CHANNELS (Primary — 70%+ of acquisition)
SEO / Content Marketing | Phase 0+ | $0–500 | 1–3% | High | <$5 | Publish 23 entity guides, 13 diagnosis pages, 6 age pages, weekly blog. Target 'CA disability benefits,' 'IEP rights,' 'Regional Center services.' Build topical authority. Internal linking strategy. | All content free. Spanish + 3 languages. Serve underserved searches.
Facebook Parent Groups | Phase 0+ | $0 | 5–8% | High | $0 | Join 20+ CA groups (autism, ADHD, DS, special needs, IEP). Provide genuine value for 2 weeks before sharing. Answer questions. Share tools. Never spam. Build reputation as trusted resource. | Groups serve all income levels. Build trust in BIPOC parent communities specifically.
Provider Referrals | Phase 1+ | $0 | 10–15% | Medium | $0 | Partner with ABA practices, OT/PT/speech, dev pediatricians. Flyers in waiting rooms. Mention at diagnosis. Co-branded family portal. Track referral source. | Providers serve all families. Ask partners to specifically recommend to underserved families.
RC Coordinator Referrals | Phase 3+ | $0 | 15–20% | High | $0 | Once RC partnership established, coordinators refer families directly. Zero CAC, highest conversion. Build training materials for coordinators. | RC serves predominantly low-income and BIPOC families. This channel IS the equity channel.
App Store Organic (ASO) | Phase 2+ | $0 | 2–4% | High | $0 | Optimize title: 'Waypoint — Disability Services Navigator.' Keywords: disability benefits, IEP help, special needs, Regional Center. 100+ reviews target. A+ screenshots. | Free app listing reaches everyone. Spanish app description.
Email Marketing | Phase 0+ | $50–100 | 3–5% | High | <$2 | 4-email welcome sequence. Weekly tips newsletter. Feature announcements. Referral campaigns. Reactivation sequences. Segmented by diagnosis + age. | Email reaches families without social media. Include Spanish-language option.
Word of Mouth / Referrals | Phase 2+ | $0 | 8–12% | Medium | $0 | 'Give a month, get a month' referral program. Shareable eligibility results. Journey maps designed for screenshots. Community ambassador program. | Referrals spread within communities naturally. BIPOC ambassador track.
Community Navigator Ambassadors | Phase 3+ | $0 | 10–15% | Medium | $0 | Train 15+ parent volunteers who've navigated the system. They introduce Waypoint to new families at RC offices, support groups, community events. | Recruit navigators from underserved communities. Stipends for navigators from equity fund.
PAID CHANNELS (Phase 3+ — 20–25% of acquisition)
Facebook / Instagram Ads | Phase 3+ | $500–2K | 2–4% | Medium | $15–30 | Target CA parents with interests: autism, IEP, special needs, disability rights. Lookalike audiences from email list. Creative: parent testimonials, eligibility tool preview. Kill campaigns > $40 CAC. | Geo-target underserved zip codes. Creative featuring diverse families. Spanish-language ad sets.
Google Ads (Search) | Phase 3+ | $500–1.5K | 3–6% | Medium | $20–40 | Bid on high-intent: 'disability benefits California,' 'IEP help near me,' 'Regional Center application.' Long-tail only. No broad match. | Bid on underserved queries: 'ayuda discapacidad California,' 'recursos en español.'
Conference / Events | Phase 2+ | $200–500/ea | 3–5% | Low–Med | $25–50 | SELPA conferences, RC family events, disability expos, parent support groups. Table + demo. Collect emails. Follow up within 24 hours. | Attend events in underserved communities. Partner with BIPOC-led orgs for co-sponsorship.
INSTITUTIONAL CHANNELS (Phase 3+ — highest volume, zero CAC)
Regional Center Distribution | Phase 3+ | $0 | 15–20% | Very High | $0 | RC refers families directly. Include Waypoint in IPP/SDP planning. Coordinator training on when/how to refer. Quarterly reports to RC on outcomes. | RC population is predominantly low-income and BIPOC. This is the equity engine.
Family Resource Centers | Phase 3+ | $0 | 10–15% | High | $0 | 21 FRCs across CA, one per RC catchment. Co-branded materials. Training for FRC staff. Waypoint kiosk in FRC lobbies. | FRCs specifically serve newly-diagnosed and underserved families.
Health System Referrals | Phase 4+ | $0 | 8–12% | High | $0 | Partner with children's hospitals. Social workers refer at diagnosis. NICU follow-up programs. Developmental pediatric clinics. | Hospital populations include all demographics. Ensure referral in all languages.
Employer Benefits Channel | Phase 5+ | $0 | N/A | Very High | $0 | Pitch to HR/benefits at large CA employers. $5–10/employee/mo. Unlimited family access. Similar to Carrot (fertility) or Cariloop (caregiving). | Employers cover cost. Employees access free regardless of income.
CONTENT MARKETING (Ongoing — the growth engine)
Entity Guides (23 pages) | Phase 0–2 | $0 | SEO | Ongoing | $0 | One guide per entity in the Matrix. 2,000–3,000 words. Cite specific legal provisions. Embedded eligibility checker. Internal links. | All free. Available in Spanish. Written at accessible reading level.
Diagnosis Journey Maps (13 pages) | Phase 1–2 | $0 | Social + SEO | Ongoing | $0 | One journey map per diagnosis. Empathetic descriptions. Entity list by age. Links to entity guides. Designed for sharing. | All 13 diagnoses including those disproportionately affecting BIPOC communities.
Interactive Tools (5+ tools) | Phase 2+ | $0 | Viral | Ongoing | $0 | Eligibility checker, RC lookup, IEP rights quiz, expense calculator, age timeline. Generate backlinks, social shares, and email signups. | All tools free, no paywall. Available in 4 languages.
Blog / Policy Updates | Phase 0+ | $0 | SEO + Social | Ongoing | $0 | 2–4 posts/week. CA budget changes, DDS directives, federal policy. Position as go-to for disability policy intelligence. | Cover equity-specific topics: language access, racial disparities in services.
Guest Posts / Community Content | Phase 2+ | $0 | Community | Ongoing | $0 | Invite parents to write: 'How I Got IHSS Approved,' 'My IEP Meeting Checklist.' Co-create with community. | Actively recruit BIPOC parent voices. Compensate guest writers from equity fund.
SOCIAL MEDIA STRATEGY (Ongoing)
Instagram (@waypointfamilies) | Phase 0+ | $0–200 | 1–2% | Medium | $0 | Content mix: 40% tips/education, 30% founder story, 20% community features, 10% product. Reels: 60-second explainers. Stories: polls, Q&A. Post 5x/week. | Feature diverse families. Multilingual captions. Partner with BIPOC disability influencers.
Facebook (Page + Groups) | Phase 0+ | $0 | 2–4% | High | $0 | Page: share blog posts, tools, policy updates. Groups: genuine participation, not promotion. Build Waypoint community group. | Be present in BIPOC-led disability groups. Respect community norms.
TikTok / Short Video | Phase 2+ | $0 | 1–3% | High | $0 | 60-second explainers: 'You might not know your child qualifies for...' Founder story. Parent stories. System explainers. | Video reaches audiences that text content doesn't. Multilingual videos.
LinkedIn | Phase 2+ | $0 | 1–2% | Low | $0 | B2B focus: thought leadership on disability services, health equity. Target RC directors, school admins, employer benefits managers. | Equity thought leadership builds institutional credibility.

## Equity Pricing Model
WAYPOINT EQUITY PRICING MODEL — 'Nobody Gets Left Behind'
Tier | Price | Eligibility | Features | Verification Method | Revenue Source | Equity Rationale
CORE PRINCIPLE: Full access for families who can't afford it. Fair pricing for families who can.
Community Access (Free) | $0/forever | Medi-Cal recipients, RC-referred families, income < 200% FPL, or self-attestation of financial hardship | FULL Plus features: unlimited AI Navigator, eligibility tools, IEP review, expense tracker, document vault, deadline alerts, all content | Medi-Cal CIN # verification, RC referral code, income self-attestation (honor system), or referral from partner org | Regional Center POS reimbursement ($100/user/mo paid by RC), grant funding, cross-subsidized by paid tiers | Disability disproportionately affects low-income and BIPOC families. The families who need Waypoint most can least afford it. RC reimbursement means the system pays, not the family.
Community Access — Spanish | $0/forever | Any Spanish-speaking family (no income verification required) | Same as Community Access + full Spanish UI + Spanish AI responses + Spanish entity guides | Language preference selection during onboarding | RC reimbursement + grant funding | Language barriers compound disability barriers. 39% of CA's population speaks Spanish. Zero-friction access removes the biggest barrier.
Community Access — Partner Org | $0/forever | Families referred by partner community organizations serving BIPOC families | Same as Community Access | Partner org referral code (unique per org) | Partner org may pay bulk rate or grant-funded | Meet families where they already are. DREDF, Black disability orgs, Asian family health centers, Latinx community centers.
Plus ($9.99/mo) | $9.99/mo or $89.99/yr | Any family not eligible for Community Access, or who prefers to pay | Unlimited AI Navigator, full eligibility results, expense tracker, document vault, deadline alerts, IEP/IPP prep, tax reports | Credit card / Apple Pay / Google Pay | Subscription revenue | Fair price for families who can afford it. Priced below Undivided ($99/mo) to keep accessible.
Pro ($19.99/mo) | $19.99/mo or $179.99/yr | Families wanting premium features | Everything in Plus + insurance appeal automation, RC reimbursement drafting, multi-child, priority AI, vetted attorney/advocate connections | Credit card / Apple Pay / Google Pay | Subscription revenue | Premium features for families who need and can afford more. Revenue cross-subsidizes Community Access.
Employer-Sponsored | $0 to employee | Employees at partnered companies with disabled dependents | Full Pro features | Employer SSO / benefits enrollment | Employer pays $5–10/employee/mo | Employer covers cost. Employee gets full access regardless of income. Removes financial barrier entirely.
RC-Funded | $0 to family | Families with RC-funded IPP or SDP including Waypoint | Full Plus features | RC referral code + POS authorization | RC pays $50–150/user/mo under POS 371/331 | The system that should be serving these families pays for the tool. Family pays nothing. Highest equity impact.
EQUITY COMMITMENTS & ACCOUNTABILITY
Equity Target: 40%+ Free | — | At least 40% of all Waypoint users access the platform for free through Community Access, RC-funded, or employer-sponsored tiers | This is a floor, not a ceiling. If fewer than 40% are on free tiers, actively expand outreach to underserved communities. | Quarterly reporting on % free users by tier | N/A | If the majority of users are paying subscribers, Waypoint isn't reaching the families who need it most.
Language Access Commitment | — | Spanish at launch, Mandarin + Vietnamese + Tagalog by Month 12. All tools, all content, all AI responses. | Full parity between English and non-English experience. Not a translation afterthought — a core commitment. | User language preference tracking, content coverage audit | N/A | CA is 39% Spanish-speaking. Non-English families face compounded barriers. Language access is equity.
Geographic Equity | — | Track adoption by RC catchment area. Target outreach to RCs serving highest-need populations (NLACRC, Harbor, Inland). | If adoption is concentrated in wealthy Bay Area, expand outreach to Central Valley, Inland Empire, rural CA. | Adoption heat map by zip code, RC catchment coverage | N/A | Don't just serve Oakland. Serve Stockton, Bakersfield, El Centro.
BIPOC Representation | — | Advisory board: 50%+ BIPOC members. Community Navigators: prioritize recruitment from BIPOC communities. Content: amplify BIPOC parent voices. | Guest posts, AMAs, testimonials actively feature diverse families. Marketing creative features diverse families. | Demographic tracking (voluntary), advisory board composition | N/A | Black and Latinx children are diagnosed later, referred less, and receive fewer services. Waypoint must actively counteract this.
No Paywall on Critical Info | — | Entity guides, diagnosis pages, eligibility tools, RC lookup, IEP rights quiz — ALWAYS free, never gated | Information about your child's rights and available programs should never cost money. Ever. Period. | Content audit — zero critical resources behind paywall | N/A | Paywalling information that helps families access their legal rights is antithetical to the mission.
Transparency Reporting | — | Publish quarterly equity reports: user demographics, free tier %, language coverage, geographic distribution, BIPOC reach | Post on website. Share with advisory board. Include in annual impact report. Public accountability. | Automated analytics dashboard + manual review | N/A | You can't improve what you don't measure. Public reporting creates accountability.
Grant Funding for Equity | — | Apply to disability, health equity, and social impact foundations to fund Community Access expansion | Target: $25K–100K in Year 1 grant funding specifically for equity access. | Grant applications to 5+ foundations | Grant revenue earmarked for equity | Don't rely solely on cross-subsidy. Actively fund equity access through dedicated grants.

## Weekly Targets
WAYPOINT — WEEKLY TARGETS & METRICS DASHBOARD
Week | Phase | Waitlist | Beta Users | App Downloads | Paid Subs | Free (Equity) Users | MRR | Organic Traffic | Key Milestone
1 | Phase 0 | 50 | — | — | — | — | $0 | — | LLC registered, domain live, landing page deployed
2 | Phase 0 | 100 | — | — | — | — | $0 | 200 | Email sequence live, Expo app initialized
3 | Phase 0 | 200 | — | — | — | — | $0 | 500 | AI Navigator MVP working, 2 entity guides live
4 | Phase 0 | 350 | — | — | — | — | $0 | 1000 | MVP on TestFlight, 5 entity guides live
GATE: Phase 0 → 1: 500 waitlist, MVP on TestFlight, 5 guides live
5 | Phase 1 | 500 | 25 | — | — | — | $0 | 1500 | Beta launched, 25 families onboarded
6 | Phase 1 | 600 | 35 | — | — | — | $0 | 2000 | NPS survey sent, AI quality improving
7 | Phase 1 | 750 | 45 | — | — | — | $0 | 3000 | 'Next Steps' engine shipped, WTP survey sent
8 | Phase 1 | 1000 | 50 | — | — | — | $0 | 4000 | App submitted to App Review, 10 guides live
GATE: Phase 1 → 2: NPS > 50, 30%+ retention, 40%+ WTP
9 | Phase 2 | 1500 | 50 | 200 | — | — | $0 | 6000 | App Store + Google Play live
10 | Phase 2 | 2000 | 50 | 400 | — | — | $0 | 8000 | 10 diagnosis pages live, ASO implemented
12 | Phase 2 | 3000 | 50 | 700 | — | — | $0 | 12000 | Eligibility checker viral, referral program live
14 | Phase 2 | 4000 | 50 | 1000 | — | 100 | $0 | 18000 | Advisory board formed, Spanish tools live
16 | Phase 2 | 5000 | 50 | 1500 | — | 200 | $0 | 25000 | IEP review + appeal generator in beta
GATE: Phase 2 → 3: 1K+ downloads, 25K organic visitors
18 | Phase 3 | — | — | 2000 | 50 | 300 | $500 | 30000 | Paid subscriptions live, equity access flow working
20 | Phase 3 | — | — | 3000 | 100 | 500 | $1,200 | 40000 | RC pilot active, provider directory live
22 | Phase 3 | — | — | 4000 | 150 | 700 | $2,000 | 50000 | 2+ RC conversations, Spanish UI live
24 | Phase 3 | — | — | 5000 | 200 | 900 | $3,000 | 60000 | Email drafter + IEP redlining in beta
26 | Phase 3 | — | — | 6000 | 250 | 1100 | $4,000 | 75000 | RCEB pilot results presented
GATE: Phase 3 → 4: 200+ paid subs, 3+ RC approvals, $3K+ MRR
30 | Phase 4 | — | — | 10000 | 500 | 2000 | $8,000 | 100000 | Content authority established
35 | Phase 4 | — | — | 15000 | 1000 | 3500 | $14,000 | 150000 | 5+ RC partnerships active
40 | Phase 4 | — | — | 25000 | 1500 | 5000 | $20,000 | 200000 | First hire onboarded, 4 languages live
45 | Phase 4 | — | — | 40000 | 2000 | 7000 | $25,000 | 250000 | Employer pilot conversations active
52 | Phase 4 | — | — | 60000 | 2500 | 10000 | $30,000+ | 300000 | Series-ready metrics, multi-state prep

## Content Calendar
WAYPOINT — CONTENT CALENDAR (First 16 Weeks)
Week | Content Type | Title / Topic | Target Keywords | Channel | Status | Equity / Language
ENTITY GUIDES (23 total — primary SEO engine)
Wk 2 | Entity Guide | The Complete Guide to Regional Center Services in California (2026) | regional center services california | SEO / Blog |  | English + Spanish by Wk 12
Wk 2 | Entity Guide | IEP Rights & Process: Everything California Parents Need to Know | iep rights california parents | SEO / Blog |  | English + Spanish by Wk 12
Wk 3 | Entity Guide | SSI for Children with Disabilities: Application Step by Step | ssi disability child application | SEO / Blog |  | English + Spanish by Wk 12
Wk 3 | Entity Guide | IHSS Application Guide: Getting In-Home Support Services | ihss application california | SEO / Blog |  | English + Spanish by Wk 12
Wk 4 | Entity Guide | Medi-Cal for Children with Disabilities: What's Covered | medi-cal disability children | SEO / Blog |  | English + Spanish by Wk 12
Wk 6 | Entity Guide | California Children's Services (CCS): Eligibility & Benefits | ccs eligibility california | SEO / Blog |  | English + Spanish
Wk 6 | Entity Guide | CalABLE Account Guide: Tax-Free Savings for Disability | calable account california | SEO / Blog |  | English + Spanish
Wk 7 | Entity Guide | Self-Determination Program: Your Complete Guide | self determination program california | SEO / Blog |  | English + Spanish
Wk 7 | Entity Guide | Department of Rehabilitation (DOR) Services Guide | dor services california disability | SEO / Blog |  | English + Spanish
Wk 8 | Entity Guide | Section 504 Plans: How They Differ from IEPs | section 504 vs iep california | SEO / Blog |  | English + Spanish
Wk 9 | Entity Guide | Special Needs Trust (SNT) Guide: Protecting Benefits | special needs trust california | SEO / Blog
Wk 9 | Entity Guide | Lanterman Act: Your Rights Under California Law | lanterman act rights | SEO / Blog
Wk 10 | Entity Guide | Respite Care in California: What's Available | respite care california disability | SEO / Blog
Wk 10 | Entity Guide | Conservatorship vs SDM: Protecting Your Adult Child | conservatorship vs sdm california | SEO / Blog
Wk 11 | Entity Guide | Wraparound Services: Mental Health Support for Families | wraparound services california | SEO / Blog
DIAGNOSIS JOURNEY PAGES (13 total)
Wk 5 | Diagnosis Page | Autism Spectrum Disorder: Your Complete Navigation Guide | autism resources california | SEO / Social |  | English + Spanish by Wk 12
Wk 5 | Diagnosis Page | Down Syndrome: Every Program & Service Your Family Needs | down syndrome resources california | SEO / Social |  | English + Spanish by Wk 12
Wk 5 | Diagnosis Page | ADHD: Navigating Services & Support in California | adhd resources california children | SEO / Social |  | English + Spanish by Wk 12
Wk 8 | Diagnosis Page | Cerebral Palsy: Services, Benefits & Family Support | cerebral palsy resources california | SEO / Social
Wk 8 | Diagnosis Page | Epilepsy: Navigating Care & Services for Your Child | epilepsy resources children california | SEO / Social
Wk 8 | Diagnosis Page | Intellectual Disability: Every Service Available to Your Family | intellectual disability services california | SEO / Social
Wk 10 | Diagnosis Page | Multiple Disabilities: Coordinating Complex Care | multiple disabilities services | SEO / Social
BLOG POSTS (2–4/week ongoing)
Wk 3 | Blog Post | Complete Guide to Regional Center Services in 2026 | regional center 2026 | SEO
Wk 4 | Blog Post | Understanding Your IEP Rights in California | iep rights california | SEO / Social
Wk 5 | Blog Post | 2026 Federal Policy Changes: What Disability Families Need to Know | disability policy changes 2026 | SEO
Wk 6 | Blog Post | What Is the Self-Determination Program? | self determination program | SEO
Wk 8 | Blog Post | Your Regional Center: What They Must Provide by Law | regional center legal requirements | SEO
Wk 11 | Blog Post | The 10 IEP Rights Every California Parent Should Know | iep rights parents list | SEO / Social |  | Shareworthy — quiz format
Wk 14 | Blog Post | What to Expect at Every Age: A Disability Family Timeline | disability timeline children | SEO
Wk 15 | Blog Post | The True Cost of Raising a Child with Disabilities in California | cost raising child disabilities | SEO / Media |  | Press pitch angle
Wk 16 | Blog Post | Every Program Your CA Family Needs in One Place | california disability programs list | SEO
INTERACTIVE TOOLS (viral + lead gen)
Wk 11 | Tool | Regional Center Lookup (by county/zip code) | regional center by county | SEO / Viral |  | Free, no login required
Wk 12 | Tool | IEP Rights Quiz: 'Do You Know Your Rights?' | iep rights quiz | Social / Viral |  | Free, shareable results
Wk 12 | Tool | Full Eligibility Checker (all diagnoses × all entities) | disability benefits checker | Viral / Lead gen |  | Free, shareable results with OG images
Wk 13 | Tool | Age Milestone Timeline Tool | disability services by age | SEO |  | Free
Wk 15 | Tool | Expense Calculator by Diagnosis | disability expense calculator | SEO / Social |  | Free
EQUITY-SPECIFIC CONTENT
Wk 10 | Equity Content | Waypoint Para Familias: Spanish-language complete landing page | recursos discapacidad california español | SEO (Spanish) |  | Full Spanish experience
Wk 13 | Equity Content | Racial Disparities in CA Disability Services: What the Data Shows | racial disparities disability services | Blog / Social |  | Positions Waypoint as equity-first
Wk 14 | Equity Content | Language Access Rights: Services You're Entitled to in Your Language | language access disability services | Blog / SEO |  | Multilingual: EN/ES/ZH/VI
Wk 16 | Equity Content | BIPOC Family Resource Hub: Culturally Responsive Disability Resources | bipoc disability resources | Hub page |  | Curated resources, diverse voices