## Focus 90 Plan
Week | Track | Priority | Task | Deliverable | Hours | Status | Why This Matters
1 | Ship | P0 | Migrate GAS prototype to Next.js/Supabase | Deployable skeleton w/ auth | 12 | Complete | Foundation for everything
1 | Ship | P0 | Claude API integration + RAG pipeline | Working AI endpoint | 8 | Complete | Core product functionality
1 | Ship | P0 | User onboarding (child profile + diagnosis) | Working onboarding flow | 6 | Complete | First-run experience
1 | Valid | P0 | Recruit 5 beta families from personal network | 5 families committed to test | 3 | Not Started | Friends, Embracing Autism, RCEB contacts
2 | Ship | P0 | Action cards engine + benefits checker | Cards + eligibility from profile | 12 | Complete | Key value prop: personalized guidance
2 | Ship | P0 | RC zip code lookup + agency finder | Working lookup from GAS port | 4 | Not Started | Proven feature from prototype
2 | Valid | P0 | Onboard first 5 beta families | 5 families using product | 4 | Not Started | Real usage data starts here
2 | Valid | P0 | Set up feedback pipeline (NPS + feature reqs) | Tally form + Airtable | 2 | Not Started | Target NPS > 40
3 | Ship | P0 | AI navigator chat with source citations | Full chat with RAG grounding | 10 | Complete | Core differentiator vs generic AI
3 | Ship | P1 | Document vault (IEP/eval upload) | Working upload to Supabase | 6 | Complete | High-value for IEP prep users
3 | Valid | P0 | Recruit 10 more families via Oakland networks | 10 new beta families committed | 4 |  | BIA, Piedmont adaptive, FB support group
3 | Valid | P0 | First NPS survey from initial 5 families | NPS score + qualitative feedback | 2 | Not Started | GO/NO-GO signal for product-market fit
4 | Ship | P1 | SMS integration (Twilio) | Deadline/action reminders | 4 | Not Started | Retention driver
4 | Ship | P1 | Landing page + waitlist (waypointfamilies.com) | Live page + Tally form | 3 | Not Started | Public-facing for organic growth
4 | Valid | P0 | All 15 beta families onboarded + active | 15 families w/ 2+ sessions each | 4 |  | Validation milestone
4 | Valid | P0 | Collect 3 specific outcome stories | Documented: time saved, $ found, action taken | 3 | Not Started | Proof for pitch deck + marketing
5 | IEP | P0 | Launch IEPClarity.ai landing page | Live page + Tally intake form | 4 |  | Cheapest paid validation test
5 | IEP | P0 | Build IEP doc prep automation pipeline | Working intake-to-output flow | 8 |  | Shared infra with Waypoint
5 | IEP | P1 | Post in 5 FB groups + 2 Reddit subs | First organic traffic | 3 |  | Oakland Autism Parents, RCEB group, r/specialeducation
5 | Valid | P0 | Compile beta family validation report | NPS, quotes, outcomes, feature reqs | 4 | Not Started | Decision doc: what to build next
6 | IEP | P0 | First 5 IEPClarity paying customers | 5 paid @ $29-69 | 3 |  | Revenue validation!
6 | Ship | P1 | IEP redline engine (stretch) | Upload IEP, get AI suggestions | 10 |  | Only if core product stable
6 | Valid | P1 | Email nurture: IEPClarity → Waypoint | 4-email conversion sequence | 2 |  | Test 5% conversion assumption
7 | RC | P0 | Map RCEB decision-makers + procurement | Contact list + process doc | 3 |  | Who approves vendor pilots?
7 | RC | P0 | Ask beta families for SC introductions | At least 1 warm intro | 2 |  | Families ARE the warm channel
7 | Ship | P1 | Expense tracker module | Expense logging + RC flags | 8 |  | Directly supports RC pitch
7 | IEP | P1 | 10+ IEPClarity customers | Growing paid base | 2 |  | Proves willingness to pay
8 | RC | P0 | Demo to 1 RCEB service coordinator | Completed demo + feedback | 3 |  | Key milestone
8 | Ship | P1 | Next Steps engine (proactive recs) | Personalized action items | 8 |  | The 'quarterback' feature
8 | Valid | P0 | 60-day review: all metrics | Decision doc: double down or pivot | 4 |  | Honest assessment
9-12 | Backlog | P2 | Multi-language support (Spanish) |  |  |  | Equity priority, defer if not validated
9-12 | Backlog | P2 | Financial planner (CalABLE, SNT) |  |  |  | Complex; build after core stable
9-12 | Backlog | P2 | Provider directory + B2B listings |  |  |  | Need user base first
9-12 | Backlog | P2 | Appeal letter generator |  |  |  | High value but complex
9-12 | Backlog | P2 | RC pilot formal proposal |  |  |  | Only after warm SC relationship
9-12 | Backlog | P2 | Paid social testing ($200 budget) |  |  |  | Only after organic channels validated
9-12 | Backlog | P2 | Mobile PWA optimization |  |  |  | After core desktop experience solid
9-12 | Backlog | P2 | NY knowledge base research |  |  |  | Multi-state = Phase 2+

## Validation Plan
Milestone | Target | Timeline | How to Measure | GO Signal | NO-GO Signal | Source / Channel
5 beta families onboarded | 5 families, 2+ sessions each | Week 2 | Usage logs + check-in calls | All 5 engaged after 1 week | <3 return after first session | Personal network: friends, Embracing Autism Collaborative, Piedmont Rec adaptive program
15 beta families active | 15 families total | Week 4 | Active users in Supabase | NPS > 40, 10+ active weekly | NPS < 20 or <5 active | Add: BIA Oakland, RCEB parent groups, local FB support group, friends & family referrals
3 documented outcomes | Time saved, $ found, or action taken | Week 4-6 | Family interviews (15 min each) | 3 specific, quotable outcomes | No family can name a concrete benefit | Beta family follow-up interviews
IEPClarity first 5 paid | 5 customers @ $29-69 | Week 6 | Stripe/Tally payments | 5 paid in first 2 weeks of launch | <2 paid in 4 weeks | FB groups, Reddit, advocate shares
IEP→WP conversion test | ≥1 conversion (5% of 20) | Week 8 | Nurture email → WP signup | Any conversions happen | Zero interest after email sequence | IEPClarity customer email nurture
1 RC service coordinator demo | Completed demo + feedback | Week 8 | Meeting happened, notes taken | SC expresses interest in pilot | SC says 'not a fit' or no meeting secured | Beta family SC introductions
60-day validation report | Comprehensive assessment | Week 8 | All metrics compiled | Positive signals on 4+ of 6 milestones | Negative signals on 3+ milestones | All above sources
Willingness-to-pay confirmed | 5 beta families would pay $10/mo | Week 6 | Direct ask in interviews | 5 say yes at $9.99 | <2 say yes | Beta family interviews

## Weekly Targets
Week | Beta Users | IEPClarity Cust | Paid WP Subs | NPS Score | Key Ship | Key Validation
1 | 0 | 0 | 0 | — | Scaffold + auth + AI endpoint | Recruit first 5 families
2 | 5 | 0 | 0 | — | Onboarding + action cards | First 5 families onboarded
3 | 10 | 0 | 0 | — | AI chat + doc vault | Recruit 10 more from Oakland networks
4 | 15 | 0 | 0 | Target >40 | SMS + landing page | NPS survey + 3 outcome stories
5 | 15 | 0 | 0 |  | IEPClarity launch | Validation report compiled
6 | 15 | 5 | 0 |  | IEP redline (stretch) | First IEPClarity revenue!
7 | 15 | 8 | 0 |  | Expense tracker | Map RC contacts, get 1 warm intro
8 | 15 | 10 | 0 |  | Next Steps engine | SC demo + 60-day review
9-12 | 15 | 15+ | 3-5 |  | Phase 2 backlog items | Convert validated learnings

## Oakland Networks
Network / Organization | Type | Est. Reach | How to Engage | Timeline
Friends & family (personal) | Personal | 10-15 families | Direct outreach, demo over coffee | Week 1
Embracing Autism Collaborative | Community | 50-100 families | Attend meetings, offer free beta | Week 1-2
RCEB parent support groups | RC Community | 100+ families | Attend monthly meetings, present demo | Week 2-3
BIA Oakland | Advocacy | 50-80 families | Partnership pitch, co-marketing | Week 3-4
Piedmont Recreation adaptive program | Recreation | 30-50 families | Volunteer + demo at program events | Week 2-4
Local FB support group | Online | 200-500 members | Post with permission, offer beta spots | Week 1-2
Oakland SELPA parent advisory | School | 40-60 families | Present at advisory meeting | Week 4-6
Teddy's school parent network | School | 15-25 families | Word of mouth, playground convos | Week 1-3
RCEB service coordinators (via families) | Professional | SC caseloads | Warm intros from beta families | Week 6-8