## Sprint Overview
WAYPOINT 2.0 — PORT-FIRST SPRINT PLAN
Strategy: Port GAS MVP core → Ship to App Store → Layer 2.0 features (Calendar/Deadline Engine + Google Integrations)
Sprint | Name | Duration | Key Deliverables | Exit Criteria | Dependencies | Risk Level
Sprint 1 | Foundation & Auth | Week 1-2 (10 days) | • Supabase project setup + schema migration • Apple Sign-In + Google Sign-In (OAuth) • Onboarding flow (6 screens: Welcome → AddChild → Diagnosis → StateAndRC → Insurance → Complete) • User profile persistence to Supabase • Bottom tab navigator (Home, Navigator, Actions, Profile) | • User can sign in with Apple/Google • Complete onboarding saves to DB • Tab navigation works • Profile data persists across sessions | • Supabase project created • Apple Dev account configured • Google Cloud Console OAuth setup | Medium
Sprint 2 | AI Navigator Port | Week 3-4 (10 days) | • Port AI Navigator chat UI (message bubbles, typing indicator, follow-up suggestions) • Supabase Edge Function for Claude API calls (replaces GAS UrlFetchApp) • Port question classification system (7 categories + urgency + emotional state) • Port tone calibration engine (collaborative → assertive → adversarial) • Chat session persistence (chat_sessions + chat_messages tables) • Port system prompts and context injection logic | • User can chat with AI Navigator • Responses include empathy, actions, legal citations • Tone adjusts based on user preference • Chat history persists across sessions | • Sprint 1 complete (auth + onboarding) • Anthropic API key in Supabase secrets • System prompts migrated | High
Sprint 3 | Knowledge Base + Action Plan Port | Week 5-6 (10 days) | • Migrate 49 KB articles to Supabase + pgvector embeddings • Build RAG retrieval pipeline (embed question → vector similarity → context injection) • Port action plan engine (priority cards, status tracking, save-from-chat) • Port draft generation (12 templates with tone calibration) • Action plan UI (card view, status toggles, expand/collapse) • Port email analyzer feature | • AI responses grounded in KB via RAG (not just prompt) • Users can save AI suggestions to action plan • Action cards show priority, scripts, drafts • Email analyzer returns red flags + action items | • Sprint 2 complete (AI chat working) • OpenAI API key for embeddings • KB articles cleaned for embedding | High
Sprint 4 | Calendar/Deadline Engine + Google Calendar | Week 7-8 (10 days) | • Build deadline engine (auto-calculate legal deadlines from onboarding data) • Deadline types: IEP review, RC IPP, insurance appeal window, SSI redetermination, authorization expiry • Calendar UI screen (react-native-calendars or react-native-big-calendar) • Google Calendar sync via OAuth + Calendar API (read existing events + write deadlines) • Push notification setup (expo-notifications) for deadline reminders • Reminder preferences (7-day, 3-day, 1-day, day-of) • ICS file generation for manual calendar add (fallback) | • Deadlines auto-populate from user profile data • Deadlines sync to Google Calendar • Push notifications fire for upcoming deadlines • Calendar screen shows all appointments + deadlines • Users can manually add appointments | • Sprint 1 complete (user profile with RC/IEP status) • Google OAuth configured with calendar scope • expo-notifications configured • EAS development build (not Expo Go) | Medium
Sprint 5 | Gmail Integration + Email Drafts | Week 9-10 (10 days) | • Google OAuth scope expansion (gmail.send + gmail.readonly) • Email draft composer (pre-populated from AI draft templates) • "Send via Gmail" button (Gmail API send) • Email inbox reader (gmail.readonly) for email analyzer feature • Pull emails from RC/school/insurance senders for analysis • Draft review screen (edit before sending) • Email history log (track what was sent, when, to whom) | • Users can send AI-drafted emails directly from app • Users can pull emails from Gmail for analysis • Email analyzer works without copy-paste • Sent email history tracked in app | • Sprint 4 complete (Google OAuth already configured) • Gmail API enabled in Google Cloud Console • Backend token exchange for security | Medium
Sprint 6 | Agency Directory + i18n + Polish | Week 11-12 (10 days) | • Port agency directory (21 RCs, school districts, insurance, SSA, IHSS, DOR) • Port RC reimbursable services guide • Port Learn More modals (16+ reference cards) • Port i18n framework (1,000+ keys: Spanish + Vietnamese) • Language switcher in profile settings • Port journey maps (7 diagnosis-specific visual roadmaps) • Loading states, error handling, empty states for all screens | • Full agency directory searchable by ZIP • All 16+ reference modals accessible • App fully usable in Spanish and Vietnamese • Journey maps render for all 7 diagnoses • No loading/error UX gaps | • Sprint 3 complete (KB + action plan) • Translation strings exported from GAS • Agency data structured for Supabase | Low
Sprint 7 | QA, Accessibility + TestFlight | Week 13-14 (10 days) | • Port QA test framework (adapt 1,000+ test cases for mobile) • Run classification accuracy tests (target >85%) • WCAG AA accessibility audit (VoiceOver, Dynamic Type, contrast) • Cross-device testing (iPhone SE, iPhone 15, iPad) • Performance optimization (lazy loading, image caching, response caching) • Bug fixes from QA + beta feedback • App Store metadata (screenshots, description, privacy policy) • TestFlight submission to 100 beta families | • Classification accuracy >85% • VoiceOver fully functional • No critical bugs on target devices • TestFlight build distributed • 100 beta testers onboarded | • Sprints 1-6 complete • Apple App Store Connect configured • Privacy policy + terms written • Beta tester list from FB groups | Low
Sprint 8 | Beta Feedback + App Store Submit | Week 15-16 (10 days) | • Daily feedback triage from 100 beta families • Priority bug fixes and UX improvements • Response quality tuning based on real questions • KB gap analysis (what questions aren't being answered well?) • Add 10-15 new KB articles based on beta feedback • Analytics dashboard (usage patterns, popular features, drop-off points) • App Store submission (iOS) • Begin RC outreach to RCEB with beta outcome data | • App Store approved and live • 70%+ beta retention (users returning weekly) • 5+ published user testimonials • RCEB pilot conversation initiated • KB expanded to 60+ articles | • Sprint 7 complete (TestFlight live) • 2+ weeks of beta usage data • Outcome metrics documented • RCEB contact identified | Low

## Task Breakdown
DETAILED TASK BREAKDOWN — All 8 Sprints
ID | Sprint | Task | Description | Priority | Effort (hours) | Status | GAS Source File | New File(s) | Notes
SPRINT 1: Foundation & Auth (Weeks 1-2)
S1-01 | Sprint 1 | Create Supabase project + run migration | Set up Supabase project, enable pgvector, run 001_schema_v1.sql to create all 13 tables | Critical | 3 | Not Started | gas-mvp/Code.gs | supabase/migrations/001_schema_v1.sql (exists) | Schema already written; just needs deployment
S1-02 | Sprint 1 | Configure Apple Sign-In | Set up expo-apple-authentication, configure App ID + Provisioning Profile, wire to Supabase Auth | Critical | 6 | Not Started | N/A (new) | src/lib/auth.ts, App.tsx updates | Requires Apple Dev account; EAS build required
S1-03 | Sprint 1 | Configure Google Sign-In | Set up @react-native-google-signin, OAuth credentials in Google Cloud Console, wire to Supabase Auth | Critical | 6 | Not Started | N/A (new) | src/lib/auth.ts, src/lib/google.ts | Request calendar + gmail scopes now (used in Sprint 4-5)
S1-04 | Sprint 1 | Build onboarding flow (6 screens) | Port multi-step intake: parent name, child info, diagnosis, RC status, IEP status, insurance, tone pref, language | High | 12 | Not Started | gas-mvp/Index.html (onboarding section) | src/screens/onboarding/*.tsx (6 files) | Port intake fields; save to families + children + diagnoses tables
S1-05 | Sprint 1 | Build bottom tab navigator | Create MainTabNavigator with 5 tabs: Home, Navigator, Actions, Calendar, Profile | High | 4 | Not Started | gas-mvp/Index.html (nav section) | src/navigation/MainTabs.tsx | Use @react-navigation/bottom-tabs
S1-06 | Sprint 1 | Build Home dashboard screen | Port home screen with greeting, quick stats, emotional check-in, recent actions | Medium | 6 | Scaffolded | gas-mvp/Index.html (screen-home) | src/screens/main/HomeScreen.tsx (update) | Currently placeholder; needs real content
S1-07 | Sprint 1 | User profile persistence | CRUD operations for families, children, diagnoses tables via Supabase client | High | 4 | Not Started | gas-mvp/Code.gs (user mgmt functions) | src/hooks/useFamily.ts, useChildren.ts | Create reusable hooks for all screens
S1-08 | Sprint 1 | Profile settings screen | Port profile editing: diagnosis, RC status, tone setting, language preference | Medium | 4 | Not Started | gas-mvp/Index.html (screen-profile) | src/screens/main/ProfileScreen.tsx | Include language switcher + tone preference
SPRINT 2: AI Navigator Port (Weeks 3-4)
S2-01 | Sprint 2 | Create Supabase Edge Function for Claude API | Serverless function that receives question + context, calls Claude API, returns structured JSON response | Critical | 8 | Not Started | gas-mvp/Code.gs (askWaypoint function) | supabase/functions/ask-waypoint/index.ts | Port the full askWaypoint pipeline; API key in Supabase secrets
S2-02 | Sprint 2 | Port question classification system | 7 categories (regional-center, iep, insurance, benefits, education, transition, navigation) + urgency + emotional state | Critical | 4 | Not Started | gas-mvp/Code.gs (classifyQuestion) | supabase/functions/ask-waypoint/classify.ts | Port regex patterns + keyword lists
S2-03 | Sprint 2 | Port tone calibration engine | Collaborative → assertive → adversarial logic with user override and claim context detection | High | 4 | Not Started | gas-mvp/Code.gs (tone logic in askWaypoint) | supabase/functions/ask-waypoint/tone.ts | Port tone rules + prompt templates
S2-04 | Sprint 2 | Build chat UI screen | Message bubbles (user/assistant), typing indicator, follow-up suggestions, scroll-to-bottom, rich text rendering | Critical | 10 | Not Started | gas-mvp/Index.html (screen-chat) | src/screens/main/NavigatorScreen.tsx | Use FlatList with inverted; handle keyboard avoidance
S2-05 | Sprint 2 | Port system prompts | Migrate all 7 category-specific system prompts + persona prompt + context injection template | High | 3 | Not Started | gas-mvp/Code.gs (system prompts) | supabase/functions/ask-waypoint/prompts.ts | Store in code, not DB (version controlled)
S2-06 | Sprint 2 | Chat session persistence | Save/load chat sessions to chat_sessions + chat_messages tables; session list UI | High | 5 | Not Started | gas-mvp/Code.gs (chat session functions) | src/hooks/useChat.ts, src/screens/main/ChatHistoryScreen.tsx | Port conversational continuity logic
S2-07 | Sprint 2 | Port context injection | Inject user profile, child diagnosis, action history, chat history into AI prompts for personalization | High | 4 | Not Started | gas-mvp/Code.gs (context building in askWaypoint) | supabase/functions/ask-waypoint/context.ts | Critical for response quality
SPRINT 3: Knowledge Base + Action Plan (Weeks 5-6)
S3-01 | Sprint 3 | Migrate KB articles to Supabase | Load 49 KB articles into knowledge_embeddings table with metadata (category, diagnosis, entity) | Critical | 4 | Not Started | gas-mvp/Code.gs (seedKnowledgeBase) | scripts/seed-kb.ts | Export from Google Sheets → structured JSON → Supabase insert
S3-02 | Sprint 3 | Generate pgvector embeddings | Embed all KB articles using OpenAI text-embedding-3-small (1536d), store in knowledge_embeddings | Critical | 4 | Not Started | N/A (new capability) | scripts/embed-kb.ts | Batch embed; ~$0.10 total cost for 49 articles
S3-03 | Sprint 3 | Build RAG retrieval pipeline | On each question: embed query → vector similarity search → inject top-K articles into prompt context | Critical | 6 | Not Started | gas-mvp/Code.gs (keyword-based retrieval) | supabase/functions/ask-waypoint/rag.ts | Upgrade from keyword match to semantic search
S3-04 | Sprint 3 | Port action plan engine | Action cards with priority levels, status tracking (completed/started/dismissed), save-from-chat, follow-ups | High | 10 | Not Started | gas-mvp/Index.html (screen-dashboard) + Code.gs (action functions) | src/screens/main/ActionsScreen.tsx, src/hooks/useActions.ts | Port action state persistence + follow-up logic
S3-05 | Sprint 3 | Port draft generation (12 templates) | Appeal letters, IEP emails, RC requests, complaints, assessment requests, records requests, PWN, CDE, 4731 | High | 6 | Not Started | gas-mvp/Code.gs (generateDraft) | supabase/functions/generate-draft/index.ts | Port all 12 template types + tone variants
S3-06 | Sprint 3 | Port email analyzer | Paste or import email → AI analysis returning summary, red flags, action items, rights at stake, draft response | Medium | 6 | Not Started | gas-mvp/Code.gs (analyzeEmailAI) + Index.html (screen-email) | src/screens/main/EmailAnalyzerScreen.tsx, supabase/functions/analyze-email/index.ts | Will integrate with Gmail in Sprint 5
SPRINT 4: Calendar/Deadline Engine + Google Calendar (Weeks 7-8)
S4-01 | Sprint 4 | Build deadline calculation engine | Auto-calculate legal deadlines from user profile: IEP review dates, RC IPP timelines, insurance appeal windows, SSI redetermination, auth expiry | Critical | 8 | Not Started | gas-mvp/Index.html (timeline cards modal) | src/lib/deadlines.ts, src/hooks/useDeadlines.ts | Port all deadline rules from timeline cards; use deadlines table
S4-02 | Sprint 4 | Build calendar UI screen | Monthly/weekly calendar view showing deadlines + appointments; color-coded by type; tap to view details | High | 8 | Not Started | N/A (new screen) | src/screens/main/CalendarScreen.tsx | Use react-native-calendars (Wix); or react-native-big-calendar
S4-03 | Sprint 4 | Google Calendar API: read events | Read user's existing Google Calendar events via Calendar API; display in-app alongside Waypoint deadlines | High | 6 | Not Started | N/A (new capability) | src/lib/googleCalendar.ts | Uses Google OAuth from Sprint 1 (calendar.readonly scope)
S4-04 | Sprint 4 | Google Calendar API: write deadlines | Sync Waypoint-generated deadlines to user's Google Calendar; include description with legal context + action items | High | 6 | Not Started | gas-mvp/Code.gs (ICS generation) | src/lib/googleCalendar.ts (extend) | Uses calendar scope; add reminders (7d, 3d, 1d)
S4-05 | Sprint 4 | Push notification system | Configure expo-notifications for deadline reminders; reminder preferences (7-day, 3-day, 1-day, day-of) | High | 6 | Not Started | gas-mvp/Code.gs (sendDeadlineReminders) | src/lib/notifications.ts, src/hooks/useNotifications.ts | Requires EAS build + push notification certs
S4-06 | Sprint 4 | ICS fallback generation | Generate .ics calendar files for users who don't connect Google Calendar; share via native share sheet | Low | 3 | Not Started | gas-mvp/Code.gs (ICS generation) | src/lib/ics.ts | Port existing ICS logic from GAS
S4-07 | Sprint 4 | Manual appointment creation | Users can add therapy appointments, IEP meetings, evaluations manually; saves to appointments table + Google Calendar | Medium | 4 | Not Started | N/A (new capability) | src/components/AddAppointmentModal.tsx | Appointment types enum from database.ts
SPRINT 5: Gmail Integration + Email Drafts (Weeks 9-10)
S5-01 | Sprint 5 | Gmail OAuth scope expansion | Add gmail.send + gmail.readonly scopes to existing Google OAuth flow; handle incremental authorization | High | 4 | Not Started | N/A (new capability) | src/lib/google.ts (extend) | Must handle users who decline Gmail permission gracefully
S5-02 | Sprint 5 | Email draft composer screen | Pre-populated email editor from AI draft templates; editable To/Subject/Body; preview before sending | High | 8 | Not Started | gas-mvp/Index.html (draft viewer modal) | src/screens/main/DraftComposerScreen.tsx | Rich text editor for email body; [BRACKET] field highlighting
S5-03 | Sprint 5 | Send via Gmail API | Send drafted emails through Gmail API; confirm sent; log to email history | High | 6 | Not Started | N/A (new capability) | src/lib/gmail.ts | Supabase Edge Function for token exchange (security)
S5-04 | Sprint 5 | Gmail inbox reader for email analyzer | Pull recent emails from RC/school/insurance senders; show list; tap to analyze | Medium | 8 | Not Started | N/A (new — replaces copy-paste) | src/screens/main/EmailInboxScreen.tsx | Filter by known sender domains; paginate
S5-05 | Sprint 5 | Email history log | Track sent emails: date, recipient, subject, draft type, outcome; searchable list | Medium | 4 | Not Started | gas-mvp/Code.gs (DraftLog) | src/hooks/useEmailHistory.ts, src/screens/main/EmailHistoryScreen.tsx | New table or extend existing
S5-06 | Sprint 5 | Fallback: expo-mail-composer | For users who don't connect Gmail: open native email app with pre-filled fields | Low | 2 | Not Started | N/A (fallback) | src/lib/mailFallback.ts | Uses expo-mail-composer; always available
SPRINT 6: Agency Directory + i18n + Polish (Weeks 11-12)
S6-01 | Sprint 6 | Port agency directory | 21 RCs with ZIP lookup, school districts, insurance, SSA, IHSS, DOR; searchable cards | High | 6 | Not Started | gas-mvp/Index.html (screen-agencies) | src/screens/main/AgencyDirectoryScreen.tsx | Port agency data to Supabase or local JSON
S6-02 | Sprint 6 | Port RC reimbursable services guide | 11 service categories with process flows, required docs, dispute resolution language | Medium | 4 | Not Started | gas-mvp/Index.html (screen-reimburse) | src/screens/main/ReimbursableServicesScreen.tsx | Port all 11 service detailed breakdowns
S6-03 | Sprint 6 | Port Learn More modals (16+) | SSI, IHSS, IEP, IPP, RC, Medi-Cal, CalABLE, DOR, Fair Hearing, 4731, Lanterman, CDE, IMR, EPSDT, SB 946 | Medium | 6 | Not Started | gas-mvp/Index.html (learn-more modals) | src/components/LearnMoreModal.tsx + content files | 16+ content modules; port HTML → React Native
S6-04 | Sprint 6 | Port i18n framework | 1,000+ translation keys for Spanish + Vietnamese; language switcher; AI responses in selected language | High | 8 | Not Started | gas-mvp/Index.html (i18n object) | src/lib/i18n.ts, src/locales/*.json | Use react-native-i18n or i18next; export keys from GAS
S6-05 | Sprint 6 | Port journey maps | 7 diagnosis-specific visual roadmaps with milestones, legal timelines, age bands | Medium | 6 | Not Started | gas-mvp/Index.html (screen-journey) | src/screens/main/JourneyMapScreen.tsx | Visual timeline component; diagnosis-aware rendering
S6-06 | Sprint 6 | Loading states + error handling | Skeleton screens, error boundaries, empty states, retry logic for all screens | Medium | 4 | Not Started | N/A (new — polish) | src/components/ErrorBoundary.tsx, SkeletonLoader.tsx | Critical for production quality
SPRINT 7: QA, Accessibility + TestFlight (Weeks 13-14)
S7-01 | Sprint 7 | Port QA test framework | Adapt 1,000+ test cases for mobile; run classification accuracy tests | High | 6 | Not Started | gas-mvp/Code.gs (QA functions) | scripts/qa-tests.ts | Target >85% classification accuracy
S7-02 | Sprint 7 | Accessibility audit (WCAG AA) | VoiceOver testing, Dynamic Type support, contrast ratios, 44pt touch targets, reduced motion | High | 8 | Not Started | gas-mvp/Index.html (WP-028 accessibility) | All screen files (updates) | Table stakes for a disability services app
S7-03 | Sprint 7 | Cross-device testing | Test on iPhone SE (small), iPhone 15 (standard), iPad; fix layout issues | Medium | 4 | Not Started | N/A | N/A (bug fixes) | Use Xcode simulator + physical devices
S7-04 | Sprint 7 | Performance optimization | Lazy loading, image caching, response caching, bundle size analysis, Hermes engine verification | Medium | 4 | Not Started | N/A | Various (optimizations) | Profile with React Native Perf Monitor
S7-05 | Sprint 7 | App Store metadata | Screenshots (6.7" + 5.5"), description, keywords, privacy policy, terms of service | High | 4 | Not Started | N/A | App Store Connect | Privacy policy must cover AI + data handling
S7-06 | Sprint 7 | TestFlight submission | Build + submit to TestFlight; invite 100 beta families from FB groups + personal network | Critical | 3 | Not Started | N/A | EAS Build → TestFlight | Recruit from autism, ADHD, Down syndrome FB groups
SPRINT 8: Beta Feedback + App Store Submit (Weeks 15-16)
S8-01 | Sprint 8 | Daily beta feedback triage | Collect, categorize, prioritize feedback from 100 beta families; daily fix cycles | Critical | 10 | Not Started | N/A | N/A (process) | Use Discord/Slack channel for real-time feedback
S8-02 | Sprint 8 | Priority bug fixes | Fix critical bugs from beta testing; UX improvements based on real usage | Critical | 10 | Not Started | N/A | Various (fixes) | Expect 15-25 bugs in first week
S8-03 | Sprint 8 | KB gap analysis + expansion | Identify questions beta users ask that KB can't answer well; write 10-15 new articles | High | 8 | Not Started | N/A | New KB articles in Supabase | Target 60+ articles by end of sprint
S8-04 | Sprint 8 | Response quality tuning | Refine system prompts based on real questions; improve classification edge cases | High | 6 | Not Started | supabase/functions/ask-waypoint/* | Prompt updates | Use QA test framework to measure improvements
S8-05 | Sprint 8 | Analytics dashboard | Usage patterns, popular features, drop-off points, response quality ratings | Medium | 6 | Not Started | N/A (new) | src/screens/admin/AnalyticsScreen.tsx or Supabase Dashboard | Use Supabase built-in analytics + custom queries
S8-06 | Sprint 8 | App Store submission | Submit to iOS App Store; address any review feedback | Critical | 4 | Not Started | N/A | App Store Connect | Allow 2-5 days for Apple review
S8-07 | Sprint 8 | Begin RCEB outreach | Prepare demo + outcome data from beta; schedule meeting with RCEB; create Service Coordinator one-pager | High | 6 | Not Started | N/A | Outreach materials | Use beta testimonials + usage metrics
|  |  |  | TOTAL | 305

## Tech Stack
TECHNOLOGY STACK & DEPENDENCIES
Category | Technology | Version | Purpose | Sprint Needed | Notes
Runtime | Expo SDK | ~52.0.0 | React Native framework + build tooling | Sprint 1 | Already in package.json
Runtime | React Native | 0.76.9 | Mobile UI framework | Sprint 1 | Already in package.json
Runtime | TypeScript | ~5.3.0 | Type safety (strict mode) | Sprint 1 | Already configured
Backend | Supabase | ^2.45.0 | Auth + Postgres DB + Edge Functions + Storage | Sprint 1 | Already in package.json; need project setup
Backend | Supabase Edge Functions | Deno | Serverless API for Claude/OpenAI calls | Sprint 2 | Deploy via Supabase CLI
AI | Anthropic Claude API | claude-sonnet-4-6 | AI Navigator responses (Sonnet for most, Opus for complex) | Sprint 2 | API key in Supabase secrets
AI | OpenAI Embeddings | text-embedding-3-small | KB article embeddings for RAG (1536d) | Sprint 3 | ~$0.10 total for 49 articles
AI | pgvector | 0.5+ | Vector similarity search in Postgres | Sprint 3 | Already enabled in schema
Auth | expo-apple-authentication | ~7.1.0 | Apple Sign-In | Sprint 1 | Already in package.json
Auth | @react-native-google-signin | latest | Google Sign-In + OAuth for Calendar/Gmail | Sprint 1 | Request calendar + gmail scopes upfront
Navigation | @react-navigation/native | ^7.0.0 | Stack + tab navigation | Sprint 1 | Already in package.json
Navigation | @react-navigation/bottom-tabs | ^7.0.0 | Bottom tab navigator | Sprint 1 | Need to install
Calendar | react-native-calendars | latest | Calendar UI component (Wix) | Sprint 4 | Monthly/weekly views; dot indicators
Calendar | Google Calendar API | v3 | Read/write events to Google Calendar | Sprint 4 | Via google-signin OAuth token
Notifications | expo-notifications | latest | Push notifications for deadline reminders | Sprint 4 | Requires EAS build + push certs
Email | Gmail API | v1 | Send drafts + read inbox | Sprint 5 | Via google-signin OAuth token; needs backend token exchange
Email | expo-mail-composer | latest | Fallback: native email compose | Sprint 5 | Works without Google auth
i18n | i18next + react-i18next | latest | Internationalization framework | Sprint 6 | 1,000+ keys; Spanish + Vietnamese
Storage | @react-native-async-storage | 1.23.1 | Local session persistence | Sprint 1 | Already in package.json
Storage | expo-secure-store | ~14.0.0 | Secure credential storage (tokens) | Sprint 1 | Already in package.json
Build | EAS Build | latest | Cloud builds for TestFlight/App Store | Sprint 1 | Required for native modules (no Expo Go)
Analytics | Supabase Analytics | built-in | Usage tracking, query analytics | Sprint 8 | Supplement with custom event logging
Testing | Jest + React Native Testing Library | latest | Unit + component tests | Sprint 7 | Port QA test cases

## Effort Summary
EFFORT SUMMARY BY SPRINT
Sprint | Name | Weeks | Tasks | Total Hours | Key Risk | Google Integration?
Sprint 1 | Foundation & Auth | 1-2 | 8 | 45 | Apple/Google OAuth complexity; EAS build setup | Yes (Google Sign-In setup)
Sprint 2 | AI Navigator Port | 3-4 | 7 | 38 | Claude API response quality in new architecture | No
Sprint 3 | KB + Action Plan Port | 5-6 | 6 | 36 | RAG retrieval quality; embedding accuracy | No
Sprint 4 | Calendar/Deadline Engine + Google Calendar | 7-8 | 7 | 41 | Google Calendar API token management; push notification certs | Yes (Calendar API read/write)
Sprint 5 | Gmail Integration + Email Drafts | 9-10 | 6 | 32 | Gmail API rate limits; token refresh; security | Yes (Gmail API send/read)
Sprint 6 | Agency Directory + i18n + Polish | 11-12 | 6 | 34 | i18n string completeness; content volume | No
Sprint 7 | QA, Accessibility + TestFlight | 13-14 | 6 | 29 | Accessibility compliance gaps; App Store rejection | No
Sprint 8 | Beta Feedback + App Store Submit | 15-16 | 7 | 50 | Beta user feedback volume; Apple review timeline | No
TOTALS |  |  | 53 | 305
Timeline: | 16 weeks (4 months) from start to App Store submission
Pace: | ~19 hours/week average (part-time, evenings + weekends feasible)
Key Milestone: | TestFlight to 100 families by Week 14; App Store live by Week 16
Google Scope: | Calendar read/write (Sprint 4) + Gmail send/read (Sprint 5). Request all scopes in Sprint 1 OAuth setup.