## 12-Week Master Plan
WAYPOINT — 12-Week Execution Plan
Your child's unexpected journey. Every step, mapped. ¦ Phase 1: Seed & Build → Beta Launch → Public Launch
Week | Day | Track | Task | Deliverable / Output | Owner | Hours | Status | GitHub Issue / Notes
PHASE 1: FOUNDATION — Weeks 1–4
Week 1 (Mar 2–6)
| Mon | Ops | Register LLC (California) — file Articles of Organization online | LLC filing confirmation | Mike | 2 |  | Ca Secretary of State online filing ~$70
| Mon | Ops | Purchase domain: waypointfamilies.com (or similar available) | Domain registered | Mike | 1 |  | Namecheap or Cloudflare
| Mon | Ops | Set up business email: mike@waypoint.app | Email working | Mike | 1 |  | Google Workspace $7/mo
| Mon | Dev | Create GitHub org + monorepo: waypoint-app/waypoint | Repo created with README, .gitignore, LICENSE | Mike | 1 |  | Private repo, main + dev branches
| Tue | Dev | Initialize Expo project: npx create-expo-app waypoint --template blank-typescript | Expo app runs on simulator | Mike | 2 |  | GH Issue: #1 Project scaffold
| Tue | Dev | Set up Supabase project: create org, project, enable pgvector extension | Supabase dashboard accessible, pgvector enabled | Mike | 1 |  | GH Issue: #2 Supabase setup
| Tue | Dev | Configure Supabase Auth: email/password + Apple Sign-In + Google OAuth | Auth flow working in Expo app | Mike | 3 |  | GH Issue: #3 Auth setup
| Wed | Dev | Design database schema v1: families, children, diagnoses, services, documents, expenses | SQL migration file committed | Mike | 4 |  | GH Issue: #4 Schema v1
| Wed | Dev | Set up Row Level Security policies: families can only see their own data | RLS policies tested | Mike | 2 |  | GH Issue: #5 RLS policies
| Thu | Dev | Build onboarding flow screens: Welcome → Add Child → Diagnosis → State/RC → Insurance → Done | 6 onboarding screens navigable | Mike | 6 |  | GH Issue: #6 Onboarding flow
| Thu | Ops | Apply for Apple Developer Program ($99/year) | Apple Dev account pending | Mike | 1 |  | Takes 24-48hrs to approve
| Fri | Dev | Connect onboarding to Supabase: write family profile + child profile to DB on completion | Data persists in Supabase after onboarding | Mike | 4 |  | GH Issue: #7 Onboarding→DB
| Fri | Sales/Mktg | Create Waypoint Instagram account + bio + first 3 posts (problem awareness) | IG account live with 3 posts | Mike | 2 |  | Focus: parent pain points, not product
| Fri | Sales/Mktg | Join 10 Facebook groups: autism parents Bay Area, ADHD parents CA, special needs parents Oakland, etc. | List of 10 groups with join status | Mike | 1 |  | Observe only — don't pitch yet
|  | MILESTONE | ✓ WEEK 1 GATE: Expo app with auth + onboarding writes to Supabase | Working app on simulator, LLC filed | Mike
Week 2 (Mar 9–13)
| Mon | Dev | Build home screen shell: tab navigation (Home, Navigator, Tracker, Documents, Profile) | 5-tab app structure navigable | Mike | 4 |  | GH Issue: #8 Tab navigation
| Mon | Dev | Set up Anthropic Claude API: create account, get API key, build edge function for chat | Supabase edge function calls Claude and returns response | Mike | 3 |  | GH Issue: #9 Claude API integration
| Tue | Dev | Build AI Navigator chat UI: message input, streaming response display, conversation history | Chat interface working with Claude responses | Mike | 6 |  | GH Issue: #10 Chat UI
| Tue | Ops | Set up EIN (IRS) — apply online, instant for LLC | EIN confirmation letter | Mike | 1 |  | IRS.gov — free, instant
| Wed | Dev | Build system prompt v1: inject family profile context (child diagnosis, age, state, RC, insurance) into every Claude request | AI responses reference the family's specific situation | Mike | 4 |  | GH Issue: #11 System prompt + context injection
| Wed | Dev | Implement conversation persistence: store chat history in Supabase, load on app open | Conversations persist across sessions | Mike | 3 |  | GH Issue: #12 Chat persistence
| Thu | Dev | Begin knowledge base v1: create Supabase table for KB articles, write ingestion script | KB table schema + ingestion script working | Mike | 4 |  | GH Issue: #13 Knowledge base infrastructure
| Thu | Ops | Open business bank account (Mercury or Relay — free for startups) | Bank account open | Mike | 1
| Fri | Dev | Ingest first KB content: Lanterman Act key provisions (§4512 eligibility, §4646 IPP rights, §4648 services, §4731 complaints) | 20+ Lanterman Act articles in KB | Mike | 5 |  | GH Issue: #14 Lanterman Act KB
| Fri | Sales/Mktg | Write first 2 value-add comments in FB groups (answer a question, share a resource — NO product mention) | 2 helpful comments posted | Mike | 1 |  | Build credibility before pitching
|  | MILESTONE | ✓ WEEK 2 GATE: AI Navigator chat working with family context + Lanterman Act knowledge | Chat with Claude that knows your child's diagnosis | Mike
Week 3 (Mar 16–20)
| Mon | Dev | Ingest IDEA key provisions: Part B (school-age IEP), Part C (Early Start/IFSP), Section 504 | 30+ IDEA articles in KB | Mike | 5 |  | GH Issue: #15 IDEA KB
| Mon | Dev | Ingest SSI/SSDI rules: eligibility criteria, income limits, application process, childhood disability evaluation | 15+ SSI articles in KB | Mike | 3 |  | GH Issue: #16 SSI/SSDI KB
| Tue | Dev | Set up pgvector embeddings pipeline: OpenAI text-embedding-3-small → Supabase pgvector | Embeddings generated and stored for all KB articles | Mike | 4 |  | GH Issue: #17 Embeddings pipeline
| Tue | Dev | Build RAG retrieval: on user question, embed query → cosine similarity search → inject top 5 matches into Claude context | AI answers grounded in KB sources | Mike | 5 |  | GH Issue: #18 RAG retrieval
| Wed | Dev | Add source citations to AI responses: display Lanterman Act §, IDEA Part, SSI regulation references | Every AI answer shows its sources | Mike | 3 |  | GH Issue: #19 Source citations
| Wed | Dev | Build benefits eligibility checker v1: structured Q&A flow → personalized program list based on diagnosis + state + income | Eligibility flow: 8 questions → generates list of 5-15 programs | Mike | 6 |  | GH Issue: #20 Eligibility checker
| Thu | Dev | Ingest Regional Center data: all 21 CA Regional Centers — names, counties, contact info, intake process | RC directory table populated | Mike | 3 |  | GH Issue: #21 RC directory
| Thu | Sales/Mktg | Identify 5 East Bay OT/ABA/speech practices for partnership outreach | Spreadsheet: name, contact, specialty, size, notes | Mike | 2 |  | Focus: practices with 3+ therapists
| Fri | Dev | Build RC-specific guidance: when user's RC is known, tailor advice to that center's Purchase of Service standards | AI gives RC-specific answers (e.g., 'RCEB covers up to X hours of respite') | Mike | 5 |  | GH Issue: #22 RC-specific guidance
| Fri | Partnerships | Send outreach emails to 5 OT/ABA practices: introduce Waypoint, request 15-min call | 5 emails sent, track responses | Mike | 2 |  | Template: 'Building a tool to help your clients' families...'
|  | MILESTONE | ✓ WEEK 3 GATE: RAG-powered AI Navigator with Lanterman + IDEA + SSI knowledge, source citations | AI that cites law when answering parent questions | Mike
Week 4 (Mar 23–27)
| Mon | Dev | Ingest Medi-Cal waiver programs, CCS eligibility, IHSS basics into KB | 25+ articles on CA health/support programs | Mike | 4 |  | GH Issue: #23 Medi-Cal/CCS/IHSS KB
| Mon | Dev | Ingest ABLE account rules + tax deduction guidance (medical expense threshold, EITC, Dependent Care Credit) | 15+ financial planning articles in KB | Mike | 3 |  | GH Issue: #24 Financial KB
| Tue | Dev | Build document vault: upload screen, Supabase Storage integration, file categorization (IEP, evaluation, insurance, medical, other) | Users can upload + categorize documents | Mike | 6 |  | GH Issue: #25 Document vault
| Tue | Dev | Build document list view: sorted by date, filterable by category, tap to preview | Document library browsable | Mike | 3 |  | GH Issue: #26 Document list
| Wed | Dev | Build provider directory: add/edit contacts for therapists, RC coordinator, school SPED, insurance, pediatrician | Provider contact book functional | Mike | 4 |  | GH Issue: #27 Provider directory
| Wed | Partnerships | Follow up on practice outreach — schedule calls with any responders | 1-3 calls scheduled | Mike | 1
| Thu | Dev | Build appointment tracker: add appointment (date, time, provider, type), calendar list view, basic reminders | Users can log and view upcoming appointments | Mike | 5 |  | GH Issue: #28 Appointment tracker
| Thu | Dev | Implement push notifications via Expo: appointment reminders (1 day before, 1 hour before) | Push notifications working on device | Mike | 3 |  | GH Issue: #29 Push notifications
| Fri | Dev | QA + bug fixes: test full flow from onboarding → AI chat → document upload → appointments | All core flows working end-to-end | Mike | 4 |  | GH Issue: #30 QA Sprint 1
| Fri | Sales/Mktg | Create Waypoint landing page (Carrd or simple React): email waitlist capture | Landing page live with waitlist form | Mike | 3 |  | Link from IG bio + FB group posts
| Fri | Ops | Purchase Apple Developer enrollment if not yet approved; set up TestFlight | TestFlight ready for beta distribution | Mike | 1
|  | MILESTONE | ✓ PHASE 1 COMPLETE: MVP with AI Navigator (RAG), document vault, provider directory, appointments | Full app ready for beta testers via TestFlight | Mike
PHASE 2: BETA LAUNCH — Weeks 5–8
Week 5 (Mar 30–Apr 3)
| Mon | Dev | TestFlight build: create App Store Connect app, configure signing, submit first build | TestFlight build available for internal testing | Mike | 4 |  | GH Issue: #31 TestFlight setup
| Mon | Dev | Build feedback mechanism: in-app 'Report Issue' button → Supabase feedback table + email to mike@ | Users can submit bugs/feedback from within app | Mike | 2 |  | GH Issue: #32 Feedback system
| Tue | Sales/Mktg | Write beta recruitment post for FB groups: 'Looking for 50 Bay Area parents to test a free tool...' | Post draft ready, approved by group admins | Mike | 2 |  | Personal, authentic tone — not corporate
| Tue | Sales/Mktg | Post beta recruitment in 5 highest-engagement FB groups | Posts live in 5 groups | Mike | 1 |  | Track signups per group
| Tue | Partnerships | Conduct partnership calls with responding OT/ABA practices: demo Waypoint, discuss referral model | 1-3 practices have seen demo | Mike | 3 |  | Bring iPad with TestFlight build
| Wed | Dev | Onboard first 10 beta users: send TestFlight invites, provide onboarding guide | 10 families actively using Waypoint | Mike | 3 |  | Personal welcome email to each
| Wed | Dev | Set up Mixpanel: track key events (onboarding_complete, ai_question_asked, document_uploaded, appointment_added) | Analytics flowing into Mixpanel | Mike | 3 |  | GH Issue: #33 Analytics setup
| Thu | Dev | Monitor AI quality: review first 50 user questions, identify where AI struggles or hallucinates | List of 10+ AI improvement areas | Mike | 4 |  | GH Issue: #34 AI quality review
| Thu | Ops | Draft Terms of Service + Privacy Policy (use template, customize for disability data sensitivity) | ToS + Privacy Policy drafts | Mike | 3 |  | Highlight: no data sold, HIPAA-grade security
| Fri | Dev | Fix top 5 issues from beta feedback + AI quality review | 5 bug fixes / AI improvements deployed | Mike | 5 |  | GH Issue: #35 Beta fixes sprint 1
| Fri | Sales/Mktg | Respond to all waitlist signups: send personal email with TestFlight link | All waitlist → TestFlight conversion | Mike | 2
|  | MILESTONE | ✓ WEEK 5 GATE: 10+ families actively using Waypoint via TestFlight | Real families asking real questions | Mike
Week 6 (Apr 6–10)
| Mon | Dev | Build IEP/IPP preparation assistant: user selects upcoming meeting type → AI generates parent agenda + preparation checklist | IEP prep flow: select meeting → get agenda + talking points | Mike | 6 |  | GH Issue: #36 IEP/IPP prep assistant
| Mon | Dev | Add deadline engine v1: calculate IEP annual review date (based on last IEP date), insurance appeal windows | Automated deadline reminders based on user's document dates | Mike | 3 |  | GH Issue: #37 Deadline engine
| Tue | Dev | Build funding waterfall visualization: show which entity pays first for each service type (insurance → Medi-Cal → CCS → RC) | Visual funding order per service | Mike | 5 |  | GH Issue: #38 Funding waterfall
| Tue | Partnerships | Send outreach to 3 Family Resource Centers in Alameda + Contra Costa counties | 3 FRC emails sent | Mike | 1 |  | Introduce Waypoint as complementary tool
| Wed | Dev | Expand to 25 beta users: second wave of TestFlight invites from waitlist + FB groups | 25 active beta users | Mike | 2
| Wed | Dev | Ingest top 5 CA insurer denial patterns: Kaiser, Blue Shield, Anthem, United, Aetna — common OT/ABA/speech denial reasons + appeal strategies | Insurance intelligence KB populated | Mike | 5 |  | GH Issue: #39 Insurance KB
| Thu | Dev | Build appeal letter generator v1: user inputs service denied + insurer → AI generates appeal letter template with legal citations | Generates customizable appeal letter PDF | Mike | 6 |  | GH Issue: #40 Appeal letter generator
| Thu | Sales/Mktg | Post 3 value-add IG stories: 'Did you know your child may be eligible for...' (IHSS, respite, ABLE accounts) | 3 educational IG stories | Mike | 1
| Fri | Dev | Review beta feedback week 2: categorize all feedback, prioritize next sprint | Prioritized backlog in GitHub Projects | Mike | 3
| Fri | Partnerships | Follow up with FRCs + confirm 1 partnership call | 1 FRC relationship initiated | Mike | 1
|  | MILESTONE | ✓ WEEK 6 GATE: 25 beta users, IEP prep assistant live, appeal letter generator working | Core value features live with real users | Mike
Week 7 (Apr 13–17)
| Mon | Dev | Build expense tracker v1: add expense (amount, date, provider, category, funding source), list view | Users can log disability-related expenses | Mike | 5 |  | GH Issue: #41 Expense tracker
| Mon | Dev | Add expense categories: therapy, medical equipment, transportation, co-pays, evaluations, adaptive tech, respite | Predefined categories with custom option | Mike | 2 |  | GH Issue: #42 Expense categories
| Tue | Dev | Build insurance claim tracker: log claim (service, date, amount, insurer, status: submitted/approved/denied/appealed) | Claims dashboard with status tracking | Mike | 5 |  | GH Issue: #43 Insurance claim tracker
| Tue | Sales/Mktg | Contact 3 special education attorneys in East Bay for referral directory | 3 attorney outreach emails | Mike | 1 |  | Offer: free listing in exchange for referrals
| Wed | Dev | Build expense summary dashboard: total by category, total by month, total by funding source, out-of-pocket running total | Visual expense dashboard | Mike | 5 |  | GH Issue: #44 Expense dashboard
| Wed | Partnerships | Confirm 1 paying therapy practice partnership ($99-149/mo for featured listing in future provider directory) | 1 verbal commitment from OT/ABA practice | Mike | 2
| Thu | Dev | Expand beta to 50 users: third wave, include families from different RCs and diagnoses | 50 active beta users across multiple profiles | Mike | 2
| Thu | Dev | Build profile settings: edit child info, update insurance, add/remove children, notification preferences | Full profile management | Mike | 4 |  | GH Issue: #45 Profile settings
| Fri | Dev | QA sprint 2: test expense tracker, claim tracker, IEP prep, appeal letters end-to-end | All week 6-7 features stable | Mike | 4 |  | GH Issue: #46 QA Sprint 2
| Fri | Ops | Research Regional Center reimbursement process: identify which RCs have approved similar tools, document POS code 371/331 requirements | RC reimbursement feasibility memo | Mike | 3
|  | MILESTONE | ✓ WEEK 7 GATE: 50 beta users, expense + insurance tracking live, 1 B2B partner committed | Financial tools working, first revenue in sight | Mike
Week 8 (Apr 20–24)
| Mon | Dev | Set up RevenueCat: configure Plus ($9.99/mo) and Pro ($19.99/mo) subscription tiers | RevenueCat integrated, paywall screens built | Mike | 4 |  | GH Issue: #47 RevenueCat setup
| Mon | Dev | Build paywall UI: feature comparison table, subscription selection, purchase flow | Paywall screen with tier comparison | Mike | 4 |  | GH Issue: #48 Paywall UI
| Tue | Dev | Implement entitlements: gate appeal letter generator + multi-child + priority AI behind Pro tier | Free/Plus/Pro feature gating working | Mike | 4 |  | GH Issue: #49 Entitlements
| Tue | Dev | Build Stripe integration for B2B: create customer portal, invoice generation for practice listings | B2B billing infrastructure ready | Mike | 3 |  | GH Issue: #50 Stripe B2B
| Wed | Dev | App Store preparation: screenshots (6.7" + 6.5"), app description, keywords, privacy nutrition labels | All App Store assets created | Mike | 5 |  | GH Issue: #51 App Store prep
| Wed | Ops | Finalize Terms of Service + Privacy Policy — publish to website | Legal pages live on waypointfamilies.com | Mike | 2
| Thu | Dev | Submit to App Store review (allow 3-5 days for review) | App submitted to Apple | Mike | 2 |  | GH Issue: #52 App Store submission
| Thu | Sales/Mktg | Prepare launch announcement: IG post, FB group posts, email to waitlist, personal network | Launch assets ready to deploy | Mike | 3
| Fri | Dev | Beta user conversion: email all 50 beta users with launch timeline + early adopter discount (30% off first 3 months) | 50 conversion emails sent | Mike | 2
| Fri | Partnerships | Onboard first paying B2B partner: create their listing, set up Stripe subscription | First B2B MRR: $99-149 | Mike | 2
|  | MILESTONE | ✓ PHASE 2 COMPLETE: App submitted to App Store, subscriptions ready, 50 beta users, 1 paying B2B partner | Ready for public launch | Mike
PHASE 3: PUBLIC LAUNCH — Weeks 9–12
Week 9 (Apr 27–May 1)
| Mon | Dev | Address any App Store review feedback — fix rejections if needed, resubmit | App approved or fixes in progress | Mike | 4 |  | Common rejections: privacy labels, screenshots
| Mon | Dev | Build tax optimization report v1: year-to-date deductible expenses, 7.5% AGI threshold tracker, ABLE contribution tracker | Tax report generation from expense data | Mike | 5 |  | GH Issue: #53 Tax optimization report
| Tue | Sales/Mktg | Launch day (assuming approval): publish all launch content simultaneously | App live on App Store + all announcements posted | Mike | 3 |  | IG post, 10 FB groups, email blast, personal LinkedIn
| Tue | Sales/Mktg | Email all waitlist subscribers: 'Waypoint is live' + App Store link + early bird pricing | Waitlist conversion campaign sent | Mike | 1
| Wed | Dev | Monitor launch metrics: downloads, signups, onboarding completion, first AI question, subscription starts | Day 1-2 dashboard in Mixpanel | Mike | 2
| Wed | Sales/Mktg | Respond to every App Store review within 24 hours | All reviews responded to | Mike | 1
| Thu | Dev | Hotfix sprint: fix any launch-day bugs reported by new users | Critical bugs resolved | Mike | 5 |  | GH Issue: #54 Launch hotfixes
| Thu | Partnerships | Send outreach to 5 more therapy practices with App Store link: 'We're live — here's what families are saying' | 5 new practice emails | Mike | 2
| Fri | Dev | Build community-sourced knowledge: allow users to upvote/flag AI responses, surface common questions | Feedback loop on AI quality | Mike | 4 |  | GH Issue: #55 AI feedback loop
| Fri | Sales/Mktg | Post first user testimonial (with permission) on IG + FB | 1 testimonial post | Mike | 1
|  | MILESTONE | ✓ WEEK 9 GATE: App live on App Store, first paid subscribers, launch metrics tracked | Waypoint is public | Mike
Week 10 (May 4–8)
| Mon | Dev | Build provider directory v2 (B2B): featured listings with practice info, specialties, insurance accepted, verified reviews | B2B provider directory browsable in app | Mike | 6 |  | GH Issue: #56 B2B provider directory
| Mon | Partnerships | Outreach to 3 disability financial planners + 2 special needs trust attorneys for directory listings | 5 professional services outreach emails | Mike | 2
| Tue | Dev | Add multi-child support (Pro tier): switch between child profiles, separate service records per child | Multi-child profile switching | Mike | 5 |  | GH Issue: #57 Multi-child support
| Tue | Sales/Mktg | Write and publish first blog post on landing page: '5 Benefits Most Disability Families Don't Know About' | Blog post live, shared in FB groups | Mike | 3 |  | SEO play: target 'disability benefits for families'
| Wed | Dev | Ingest remaining 21 RC Purchase of Service Standards: detailed per-center service availability and limits | Complete CA RC coverage in knowledge base | Mike | 6 |  | GH Issue: #58 Full RC KB
| Wed | Partnerships | Schedule calls with any responding financial planners/attorneys | 1-2 calls scheduled | Mike | 1
| Thu | Dev | Build RC reimbursement request helper: generate letter requesting Waypoint be added to IPP/SDP as parent training | User can generate RC reimbursement request letter | Mike | 4 |  | GH Issue: #59 RC reimbursement helper
| Thu | Sales/Mktg | IG Reel: '3 things I wish I knew when my child was diagnosed' (personal story or user story with permission) | 1 Reel posted | Mike | 2
| Fri | Dev | Performance optimization: app load time, chat response speed, image compression for documents | App performance improved | Mike | 4 |  | GH Issue: #60 Performance sprint
| Fri | Ops | Week 10 metrics review: users, subscribers, MRR, churn, top AI questions, NPS from feedback | Metrics dashboard populated | Mike | 2
|  | MILESTONE | ✓ WEEK 10 GATE: B2B directory live, multi-child support, full RC knowledge base, RC reimbursement flow | Platform deepening + second revenue stream | Mike
Week 11 (May 11–15)
| Mon | Dev | Build SELPA/school district integration: user enters school district → AI tailors IEP advice to that district's known practices | District-aware IEP guidance | Mike | 5 |  | GH Issue: #61 School district context
| Mon | Dev | Build notification center: centralized view of all upcoming deadlines, appointments, and action items | Notification dashboard in app | Mike | 4 |  | GH Issue: #62 Notification center
| Tue | Dev | Build 'Next Steps' engine: based on family profile + completed actions, proactively suggest what to do next | 'Your next waypoint: Apply for IHSS' — proactive recommendations | Mike | 6 |  | GH Issue: #63 Next Steps engine — THE QUARTERBACK
| Tue | Partnerships | Pitch Waypoint to 2 East Bay SELPA family liaisons as a resource for their families | 2 SELPA outreach contacts | Mike | 2 |  | Offer free accounts for their families
| Wed | Dev | Build email digest: weekly summary of upcoming deadlines, new AI insights, expense totals | Weekly email digest via SendGrid | Mike | 4 |  | GH Issue: #64 Weekly digest
| Wed | Sales/Mktg | PR outreach: pitch story to 3 disability parenting publications (Exceptional Parent, Special Needs Resource Foundation, Disability Scoop) | 3 PR pitches sent | Mike | 2 |  | Angle: 'AI quarterback for disability families'
| Thu | Dev | Build sharing: allow users to share specific AI answers or checklists with partners, co-parents, or advocates | Share via text/email from within app | Mike | 3 |  | GH Issue: #65 Share feature
| Thu | Sales/Mktg | Second blog post: 'How to Prepare for Your Child's IEP Meeting: A Step-by-Step Guide' | Blog post live | Mike | 2
| Fri | Dev | QA Sprint 3: full regression test of all features before Week 12 push | All features stable | Mike | 4 |  | GH Issue: #66 QA Sprint 3
| Fri | Partnerships | Onboard 2nd and 3rd B2B partners (therapy practices or professional services) | 3 total B2B partners paying | Mike | 2
|  | MILESTONE | ✓ WEEK 11 GATE: 'Next Steps' quarterback engine live, notification center, 3 B2B partners | Waypoint proactively drives the journey | Mike
Week 12 (May 18–22)
| Mon | Dev | Build onboarding v2: faster flow for returning users, 'Quick Setup' for users who want to skip details initially | Streamlined second onboarding path | Mike | 4 |  | GH Issue: #67 Onboarding v2
| Mon | Dev | Implement app rating prompt: after 5th AI question answered, prompt for App Store rating | Smart rating prompt | Mike | 2 |  | GH Issue: #68 Rating prompt
| Tue | Dev | Build referral system: 'Invite a parent' → both get 1 month free of Plus tier | Referral link generation + tracking | Mike | 4 |  | GH Issue: #69 Referral system
| Tue | Sales/Mktg | Launch referral campaign in FB groups: 'Know a parent who could use this?' | Referral campaign posts in 10 groups | Mike | 2
| Wed | Dev | Prepare multi-state foundation: abstract state-specific data layer so KB can support NY, TX, IL without refactoring | State abstraction layer in code | Mike | 5 |  | GH Issue: #70 Multi-state architecture
| Wed | Ops | 12-week retrospective: compile all metrics, user feedback themes, revenue, costs, key learnings | 12-week retro document | Mike | 3
| Thu | Dev | Knowledge base expansion: begin research on New York disability services system (OPWDD, CPSE, CSE) | NY research notes + KB structure planned | Mike | 4 |  | GH Issue: #71 NY research
| Thu | Partnerships | Submit Waypoint to 2 Regional Centers as recommended parent training resource (RCEB + Golden Gate RC) | 2 RC submissions | Mike | 3 |  | Include user testimonials + outcomes data
| Fri | Sales/Mktg | Compile and publish 'Waypoint Impact Report': families served, questions answered, benefits discovered, money saved | Impact report for marketing + fundraising | Mike | 3
| Fri | Ops | Plan Phase 4 (Months 4-6): prioritize backlog, set OKRs, decide on fundraise timing | Phase 4 plan document | Mike | 3
|  | MILESTONE | ✓ PHASE 3 COMPLETE: Public app, paying subscribers, 3+ B2B partners, RC reimbursement submitted, multi-state prep begun | Waypoint is live, generating revenue, and scaling | Mike

## Weekly Targets
Weekly Target Metrics
Week | Phase | Beta Users | Paid Subs | B2B Partners | MRR | KB Articles | Key Feature Ship
Wk 1 | Foundation | 0 | 0 | 0 | $0 | 0 | Expo + Auth + Onboarding
Wk 2 | Foundation | 0 | 0 | 0 | $0 | 20 | AI Navigator chat
Wk 3 | Foundation | 0 | 0 | 0 | $0 | 65 | RAG + Eligibility checker
Wk 4 | Foundation | 0 | 0 | 0 | $0 | 105 | Doc vault + Appointments
Wk 5 | Beta | 10 | 0 | 0 | $0 | 105 | TestFlight + Beta wave 1
Wk 6 | Beta | 25 | 0 | 0 | $0 | 130 | IEP prep + Appeal letters
Wk 7 | Beta | 50 | 0 | 1 | $99 | 130 | Expense + Claims tracking
Wk 8 | Beta | 50 | 0 | 1 | $99 | 130 | Subscriptions + App Store
Wk 9 | Launch | 50 | 15 | 1 | $249 | 130 | Public launch
Wk 10 | Launch | 50 | 40 | 2 | $698 | 160 | B2B directory + Multi-child
Wk 11 | Launch | 50 | 70 | 3 | $1,147 | 160 | Next Steps engine
Wk 12 | Launch | 50 | 100 | 3 | $1,396 | 160 | Referrals + Multi-state prep

## GitHub Issues
GitHub Issues — Ready to Create
Issue # | Title | Label | Milestone | Week | Priority | Acceptance Criteria
1 | Project scaffold: Expo + TypeScript | setup | Phase 1 | 1 | P0 | Expo app runs on iOS simulator
2 | Supabase project setup + pgvector | setup | Phase 1 | 1 | P0 | Supabase dashboard accessible, pgvector enabled
3 | Auth: email + Apple + Google OAuth | auth | Phase 1 | 1 | P0 | User can sign up and sign in via all 3 methods
4 | Database schema v1 | backend | Phase 1 | 1 | P0 | Migration file runs, all tables created
5 | Row Level Security policies | backend | Phase 1 | 1 | P0 | User A cannot read User B's data
6 | Onboarding flow (6 screens) | frontend | Phase 1 | 1 | P0 | Complete flow from welcome to done
7 | Onboarding → Supabase write | frontend | Phase 1 | 1 | P0 | Family + child profile persists in DB
8 | Tab navigation (5 tabs) | frontend | Phase 1 | 2 | P0 | All 5 tabs navigable with placeholder screens
9 | Claude API edge function | ai | Phase 1 | 2 | P0 | Edge function returns Claude response
10 | AI Navigator chat UI | ai | Phase 1 | 2 | P0 | Messages display with streaming, scroll works
11 | System prompt + family context injection | ai | Phase 1 | 2 | P0 | AI references child's diagnosis, RC, insurance
12 | Chat conversation persistence | ai | Phase 1 | 2 | P1 | Conversations survive app close/reopen
13 | Knowledge base infrastructure | ai | Phase 1 | 2 | P0 | KB table + ingestion script working
14 | Lanterman Act KB content | content | Phase 1 | 2 | P0 | 20+ articles ingested and retrievable
15 | IDEA KB content | content | Phase 1 | 3 | P0 | 30+ articles covering Part B, Part C, Section 504
16 | SSI/SSDI KB content | content | Phase 1 | 3 | P0 | 15+ articles on eligibility, application, appeals
17 | Embeddings pipeline (OpenAI → pgvector) | ai | Phase 1 | 3 | P0 | All KB articles have embeddings stored
18 | RAG retrieval system | ai | Phase 1 | 3 | P0 | User question → top 5 relevant KB articles → Claude
19 | Source citations in AI responses | ai | Phase 1 | 3 | P1 | Citations displayed with law/regulation references
20 | Benefits eligibility checker | feature | Phase 1 | 3 | P0 | 8 questions → personalized program list
21 | Regional Center directory | content | Phase 1 | 3 | P1 | All 21 CA RCs with contact info
22 | RC-specific guidance | ai | Phase 1 | 3 | P1 | AI tailors answers to user's specific RC
23 | Medi-Cal / CCS / IHSS KB | content | Phase 1 | 4 | P0 | 25+ articles on CA health programs
24 | Financial planning KB (ABLE, taxes) | content | Phase 1 | 4 | P1 | 15+ articles on financial benefits
25 | Document vault (upload + categorize) | feature | Phase 1 | 4 | P0 | Upload files, assign category, persist in storage
26 | Document list view | feature | Phase 1 | 4 | P1 | Sort by date, filter by category, tap to preview
27 | Provider directory (personal contacts) | feature | Phase 1 | 4 | P1 | Add/edit/delete provider contacts
28 | Appointment tracker | feature | Phase 1 | 4 | P1 | Add appointments, list view, basic reminders
29 | Push notifications (Expo) | infra | Phase 1 | 4 | P0 | Appointment reminders 1 day + 1 hour before
30 | QA Sprint 1 | qa | Phase 1 | 4 | P0 | All Phase 1 features stable end-to-end
31 | TestFlight build + distribution | infra | Phase 2 | 5 | P0 | Build available for external testers
32 | In-app feedback system | feature | Phase 2 | 5 | P1 | Bug reports write to Supabase + email
33 | Mixpanel analytics | infra | Phase 2 | 5 | P0 | Key events tracked and visible in dashboard
34 | AI quality review (first 50 questions) | ai | Phase 2 | 5 | P0 | 10+ improvement areas identified
35 | Beta fixes sprint 1 | bug | Phase 2 | 5 | P0 | Top 5 user-reported issues resolved
36 | IEP/IPP preparation assistant | feature | Phase 2 | 6 | P0 | Select meeting → get agenda + checklist
37 | Deadline engine v1 | feature | Phase 2 | 6 | P0 | Auto-calculated deadlines from document dates
38 | Funding waterfall visualization | feature | Phase 2 | 6 | P1 | Visual funding order per service type
39 | Insurance denial patterns KB (top 5 CA insurers) | content | Phase 2 | 6 | P0 | Denial patterns + appeal strategies
40 | Appeal letter generator | feature | Phase 2 | 6 | P0 | AI generates customizable appeal letter PDF
41 | Expense tracker v1 | feature | Phase 2 | 7 | P0 | Add expense with amount, date, provider, category
42 | Expense categories | feature | Phase 2 | 7 | P1 | Predefined categories + custom option
43 | Insurance claim tracker | feature | Phase 2 | 7 | P0 | Log claims with status tracking
44 | Expense summary dashboard | feature | Phase 2 | 7 | P1 | Totals by category, month, funding source
45 | Profile settings | feature | Phase 2 | 7 | P1 | Edit child info, insurance, notifications
46 | QA Sprint 2 | qa | Phase 2 | 7 | P0 | All Phase 2 features stable
47 | RevenueCat subscription setup | infra | Phase 2 | 8 | P0 | Plus + Pro tiers configured
48 | Paywall UI | frontend | Phase 2 | 8 | P0 | Feature comparison + purchase flow
49 | Feature entitlements (Free/Plus/Pro) | frontend | Phase 2 | 8 | P0 | Pro features gated correctly
50 | Stripe B2B billing | infra | Phase 2 | 8 | P1 | B2B invoicing working
51 | App Store assets + submission prep | infra | Phase 2 | 8 | P0 | Screenshots, description, keywords ready
52 | App Store submission | infra | Phase 2 | 8 | P0 | Build submitted to Apple review
53 | Tax optimization report | feature | Phase 3 | 9 | P1 | YTD deductible expenses + threshold tracker
54 | Launch hotfixes | bug | Phase 3 | 9 | P0 | All critical launch bugs resolved <24hrs
55 | AI feedback loop (upvote/flag) | ai | Phase 3 | 9 | P1 | Users can rate AI answer quality
56 | B2B provider directory (in-app) | feature | Phase 3 | 10 | P0 | Featured listings with practice info
57 | Multi-child support (Pro) | feature | Phase 3 | 10 | P1 | Switch between child profiles
58 | Full RC KB (all 21 POS standards) | content | Phase 3 | 10 | P0 | Complete CA RC coverage
59 | RC reimbursement request helper | feature | Phase 3 | 10 | P1 | Generate RC reimbursement request letter
60 | Performance optimization sprint | infra | Phase 3 | 10 | P1 | Load time, chat speed, image compression
61 | School district context for IEP | ai | Phase 3 | 11 | P1 | District-aware IEP guidance
62 | Notification center | feature | Phase 3 | 11 | P0 | Centralized deadlines + action items view
63 | Next Steps engine (THE QUARTERBACK) | feature | Phase 3 | 11 | P0 | Proactive recommendations based on profile
64 | Weekly email digest | feature | Phase 3 | 11 | P1 | SendGrid weekly summary email
65 | Share AI answers / checklists | feature | Phase 3 | 11 | P1 | Share via text/email from app
66 | QA Sprint 3 | qa | Phase 3 | 11 | P0 | Full regression test
67 | Onboarding v2 (streamlined) | frontend | Phase 3 | 12 | P1 | Quick setup path for impatient users
68 | Smart App Store rating prompt | frontend | Phase 3 | 12 | P1 | Prompt after 5th AI question
69 | Referral system | feature | Phase 3 | 12 | P0 | Invite → both get 1 month free
70 | Multi-state architecture | backend | Phase 3 | 12 | P0 | State abstraction layer for KB expansion
71 | New York research + KB planning | content | Phase 3 | 12 | P1 | NY programs documented, structure planned